## FrontPage
OpenProjectAPI.xlsm
Project Number & Name |  |  |  | Review | Document state | Date of release
Process and method |  |  |  | To be fullfilled | Template released | 2022-03
Document id | Document title |  |  |  | Template | Revision |  | Version
TBD | Project feasibility analysis |  |  |  | TEM578 | TBD |  | TBD
Author |  |  | Review |  | Approval
Title: |  | TBD | See Project Master Document for the roles and Project Members List for the name of people |  | See Project Master Document for the roles and Project Members List for the name of people
Distribution *
See Project Master Document for the roles and Project Members List for the name of people
Executive summary | This document facilitates the analysis of the project feasibility within the project constraints with repsect to time, cost and available resources.
Project feasibility analysis
Note on R5: Fill here the reference of the project review findings : peer review workbook or equivalent
Note on AB6: This field is only for PLM document
Note on W7: Template from process AEM_PROCESS_1.21.00 Last change : AEM_PROCESS_1.20.00
Note on L9: If the document Project list members (TEM461) is not used, please write the reviewers names
Note on W9: If the document Project list members (TEM461) is not used, please write the reviewers names

## General info
OpenProjectAPI.xlsm
Project Number & Name | [6 empty] | Document state |  | Date of release
Process and method | [6 empty] | Template released |  | 2022-03
Document id |  | Document title |  |  |  |  | Template |  | Revision |  | Version
TBD |  | Project feasibility analysis |  |  |  |  | TEM578 |  | TBD |  | TBD
Tab Name
TAB - General Information
1. General Information
1.1. Table of content
| Tab |  | Description/comment
| FrontPage |  | The front page contains information about the document. Note : o the blue cells are automatically filled by PLM and/or formula
| General info |  | This sheet : contains history, reference, purpose, scope, definition and guide
| Content |  | General info, revision history and guideline (how to).
1.2. Revision History *
| Revision | Date |  |  | Author(s) | Description/Comment
| 000 | 27.01.2022 |  |  | Daniel Andris | First document version
* Template history is found in the CM tool used for templates
1.3. References
1.3.1. Referenced documents
| ID | Title | [5 empty] | Reference & revision
1.3.2. Applicable documents
| ID | Title | [5 empty] | Reference & revision
1.5. Terminology and definitions
Terminology
| Generic terminology |  |  | See acronyms in AEM process wiki
2. Guide (help)
The orange text in the 'Feature Feasbility' and 'Resource & Cost Feasibility' sheets is only for guidence and should be replaced by the project specific content. Feature Feasibility sheet To start, fill in each feature (Feature Name, Feature Content and Description columns) the project needs (the information could be typically found in a Project Feature Release Plan). After this, fill in the 'Feasible within Project Constraints' column by deciding if each feature is technically feasible for the project within the project constraints or not. If the feature is not technically feasible because of the complexity or because of the project constraints (like short development time, limited resources, lack of team knowledge etc) a countermeasure must be implemented . For this case the 'Countermeasure' and 'Due date' columns must be filled in. Countermeasure examples are: implementation by the Platform team, agreement from the customer to reduce the feature complexity to the feasible content, management commitment to staff the project with people who have the competence/knowledge to implement the feature etc. The next step is to estimate the required effort for each feature per discipline/area. For this, it is important to ensure that either an appropriate estimation method or similar project estimate records are used in order to show the the detailed figures as breakdown/evidence of the rough estimates.
Resource & Cost Feasibility sheet Before filling in this sheet make sure all the estimated effort is filled in in the 'Feature Feasibility' sheet. The 'Project Length' column (in months) must be provided first. The template assumes 146 working hours per month. More or less can be used by modifying the 'Required' column (although it is not recommended to change it). The number of available resources must then be provided for each type of resource in the 'Available' column. If there are additional resources needed by the project please insert additional rows at the end of the table. The template will compute the feasibility of the resources by its own based on the 'Project Length' and the number of available resources. Again, if any type of resource is not feasible it is mandatory to define a countermeasure and a due date. Next, the 'Hourly Cost' in €/h must be filled in for each type of resource. The 'Required' column is computed automatically except for the resources which are not effort-related (for those a cost must be inserted). Finally, the 'Total Available' budget must be provided and the template will compute the 'Cost Feasibile' cell.
3. Parameters / database
<If you have some generic parameters / database, please add them here>
Note on B15: Insert name of tabs included in the document
Note on G15: Describe each Tab.
Note on B22: The revision number of the document 000, 001, 002 etc. No version number to be handled in the table.
Note on E22: Date when the Revision is released
Note on I22: Author of the document. Authors if several.
Note on R22: Description or comment on the version. E.g. updated after meeting etc.
Note on B32: ID of possible reference documents. Any ID can be used, suggestion is [Int1], [Int2] etc. for internal references and [Ext1], [Ext2] etc. for external references
Note on E32: Title of reference documents.
Note on Y32: Reference number, e.g. E123456 and revision of the reference.
Note on B38: ID of possible reference documents. Any ID can be used, suggestion is [Int1], [Int2] etc. for internal references and [Ext1], [Ext2] etc. for external references
Note on E38: Title of reference documents.
Note on Y38: Reference number, e.g. E123456 and revision of the reference.

## Feature_Plan
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[7 empty] | Features/release > | 9 | 17 | 15 | 11 | 14 | 13 | 9 | 20 | 27 | 17
|  |  |  | Phase: |  |  |  | Concept | R1 | R1.1 | R1.2 | R2 | R2.1 | R2.2 | R3 | R3.1 | R3.2
|  |  |  | Months: |  |  | Duration (monts) > | 3 | 3.5 | 2 | 1 | 3 | 4 | 3 | 5 | 4 | 3
|  |  |  | SW Dev: |  |  |  | 4.8682 | 7.784 | 10.9913 | 8.7099 | 7.4308 | 5.344 | 6.833 | 6.1886 | 6.3495 | 6.5539
|  |  |  | SW Release Name: |  | SW Release Name > |  | Concept SW 0 | SW 1 | SW 1.1 | SW 1.2 | SW 2 | SW 2.1 | SW 2.2 | SW 3 | SW 3.1 | SW 3.2
|  |  |  | HW Release Name: |  | HW Release Name > |  | HW A2 | HW B1 | HW B1 | HW B1 | HW B2 | HW B2 | HW B2 | HW C1 | HW C1 | HW C1
|  |  |  | Release Date: |  |  |  | 2022-10-12 | 2023-01-18 | 2023-03-01 | 2023-03-29 | 2023-06-21 | 2023-10-11 | 2024-01-03 | 2024-05-29 | 2024-09-18 | 2024-12-04
100% SW | Notes | SW Module | Status 2022-09-20 vs. Concept | Feature Name | Feature Content | Description | Feature ID / System CR | Rel Content | Rel Content | Rel Content | Rel Content | Rel Content | Rel Content | Rel Content | Rel Content | Rel Content | Rel Content
1 |  | ACC; SpiIf; Spi; Port | on track | Accelerometer driver implementation |  | 6 axis to 3 axis |  | 2022-10-12: 100%; 2023-01-18: 110%; 2024-09-18: 120%
1 |  | eCS | on track | eCS Algo |  | > Acceleration evaluation > Crash signal evaluation |  | 40% | 60% | 80% | 90% | 100% |  |  |  | 110% | 120%
1 | old HW 2022-08-01: Rework needed for new HW | FSM; SAD; Port; Pwm; MMG | SW-HW Integration for RBE HW completed. Functional | Solenoid control |  | > Lock/Unlock implementation > Lock/Unlock counters |  | 40% | 60% | 80% | 90% | 100% |  |  |  | 110% | 120%
1 | old HW | SAD |  | Solenoid Diagnostic |  | > Failure detection mechanism for solenoid |  | 2023-01-18: 70%; 2023-03-01: 80%; 2023-06-21: 100%; 2024-09-18: 110%; 2024-12-04: 120%
1 | especially seat occupancy information (> impact on safety belt warnings) | LPM; EcuMIf;BswMIf; NmIf; Nm; BswM;EcuM; Mcu;SBC; Spi;SpiIf | on track | Wake-up by wire | Buckle+SBR | > Wake-up/Sleep strategy > Compute seat occupancy information |  | 20% | 40% | 70% | 80% |  | 100% |  |  | 110% | 120%
1 | 2022-08-01: For SW 1 Flashing available based on TR6 BL |  | on track | Bootloader |  |  |  | 20% |  | 35% |  |  | 50% | 80% | 100% | 110% | 120%
1 | 2022-08-17 VW: K-Matrix/ARXML will be shared in CW35 2022-08-01: Draft version integration in SW 1. (Released version announced for mid november 2022, with no major differences - decission for the SW to be integrated in, to be taken based on the differences.) | ComStack; CIL | started in advance | COM Matrix integration |  | > OEM arxml / com matrix integration > eCS status information based on the com matrix > SBR & Buckle Status |  |  | 15% | 25% |  |  | 30% | 60% | 80% | 100% | 120%
1 |  | ComStack | started in advance | CAN Stack |  | Implementation according to Autosar 4.3 CAN FD specification. |  | 2023-01-18: 50%; 2023-03-29: 80%; 2023-10-11: 100%; 2024-09-18: 110%
1 |  | ComStack | started in advance | Network Management |  |  |  | 2023-01-18: 30%; 2023-03-01: 100%; 2024-05-29: 110%; 2024-12-04: 120%
1 |  |  | started in advance (GDP version) | AUTOSAR & OS |  | Implementation according to Autosar 4.3 specification. |  | 2023-01-18: 50%; 2023-03-01: 60%; 2023-06-21: 70%; 2023-10-11: 100%; 2024-09-18: 110%
DV |  | PhysCIf:AdcIf;Adc;SAD;ATM |  | Self-Tests |  |  |  |  | 30% | 50% | 55% | 60% |  | 80% | 100% | 110% | 120%
DV |  | Dem |  | ECU Fault Detection |  | Fault handling |  |  | 30% | 50% | 55% | 60% |  | 80% | 100% | 110% | 120%
|  | DIA;Dcm;DcmIf |  | ECU-External Specific Diag |  | (UDS) > eCS specific diag services > Identifikation > Messwerte |  | 2023-06-21: 30%; 2023-10-11: 40%; 2024-05-29: 60%; 2024-09-18: 100%; 2024-12-04: 120%
1 |  | DIA;Dcm;DcmIf | started in advance | ECU-Internal Specific Diag |  | (UDS) > ALV internal diagnostic services vs mem by address? |  | 2023-06-21: 30%; 2024-05-29: 80%; 2024-09-18: 100%; 2024-12-04: 120%
1 |  | CIL |  | Error mapping strategy |  |  |  | 2023-03-01: 70%; 2023-03-29: 90%; 2023-10-11: 100%; 2024-09-18: 110%
|  | PhysCIf | started in advance | Temperature Sensor | Accuracy Calibration Error detection |  |  | 2023-01-18: 20%; 2023-06-21: 50%; 2024-01-03: 80%; 2024-05-29: 100%; 2024-09-18: 110%
|  |  |  | Temperature adaptation |  |  |  |  | 20% |  |  | 50% |  | 80% | 100% | 110% | 120%
|  |  |  | Ageing compensation |  |  |  | 2023-06-21: 50%; 2024-01-03: 80%; 2024-05-29: 100%; 2024-09-18: 110%; 2024-12-04: 120%
|  |  | started in advance | Nachlauf | Low Power Mode | Full functionality according to Audi requirements. |  | 2023-01-18: 20%; 2023-06-21: 100%; 2024-09-18: 110%; 2024-12-04: 120%
|  |  |  | Coding parameters |  |  |  | 2023-10-11: 50%; 2024-01-03: 100%; 2024-09-18: 110%
|  |  |  | Calibrateable ECU |  |  |  | 2023-10-11: 50%; 2024-05-29: 100%; 2024-09-18: 110%
|  |  |  | Variant handling |  | Handling of NVM data for different OEMs (Audi, VW) |  | 2023-10-11: 50%; 2024-05-29: 100%; 2024-09-18: 110%
|  |  |  | UNECE |  |  |  | 2023-06-21: 40%; 2023-10-11: 80%; 2024-05-29: 100%; 2024-09-18: 110%
|  |  |  | Knockout |  | Knockout feature implementation based on Autoliv proposal |  | 2024-05-29: 100%; 2024-09-18: 110%; 2024-12-04: 120%
| Further discussion |  |  | System context |  |  |  | 2023-10-11: 40%; 2024-05-29: 100%; 2024-09-18: 110%
|  |  |  | Flash lock |  | Flash locking for serial life |  | 2024-05-29: 90%; 2024-09-18: 100%; 2024-12-04: 120%
|  |  | started in advance | Safety mechanisms
|  |  |  | SW Bug-Fix |  |  |  | 10% | 20% | 25% | 35% | 50% | 60% | 70% | 80% | 90% | 100%
| HW/Mechanics will be delayed due to connector change |  |  | HW Development |  |  |  | 40% | 70% | 100% | 100% |  |  |  | 110% | 115%
| HW/Mechanics will be delayed due to connector change |  |  | Mechanical |  |  |  | 10%: 40%; 20%: 70%; 25%: 100%; 35%: 100%; 80%: 110%
|  |  |  | Product Validation |  |  |  | 10%: 80%; 25%: 100%; 35%: 100%; 80%: 110%
Note on E1: Daniel Balanean: Update Formula on row 1 if columns change (ex. no. of releases). Start with 1 at column C.
Note on J16: Daniel Balanean: 100% K-Matrix First Release / integration Deadline for K-Matrix availability: xx.yy.zz

## Sheet2
3.1077 | 6.8308 | 6.7945 | 6.4748 | 5.9055 | 5.7198 | 5.3627 | 5.1693 | 5.5187 | 5.2286

## Detailed estimation
[6 empty] | Initial estimation | Complexity applied | Concept | R1 | R1.1 | R1.2 | R2 | R2.1 | R2.2 | R3 | R3.1 | R3.2 | AVERAGE/Month | Total estimated hours | Forecasted hours | Initial Forecasted hours
[5 empty] | Months | 31.5 | 31.5 | 3 | 3.5 | 2 | 1 | 3 | 4 | 3 | 5 | 4 | 3 | 31.5
[5 empty] | Hours / Month | 151.666 | 151.666 | 151.666 | 151.666 | 151.666 | 151.666 | 151.666 | 151.666 | 151.666 | 151.666 | 151.666 | 151.666 | 151.666
[5 empty] | TOTAL (h) | 73931.64 | 55937.56 | 6206 | 9886 | 8295 | 2320 | 6650 | 6861 | 6382 | 10509 | 8372 | 6179 | 2274.9206 | 71660 | 67622.6371 | 83484.7371
[5 empty] | Res. Required | 15.475 | 11.7086 | 13.6396 | 18.6236 | 27.3463 | 15.2968 | 14.6154 | 11.3094 | 14.0264 | 13.8581 | 13.8001 | 13.5803 | 14.9995 |  |  |  | 84849.5437
[5 empty] | Sys Eng (h) | 8874.88 | 7453.32 | 581 | 1234 | 1037 | 304 | 909 | 937 | 869 | 1413 | 1203 | 884 | 297.4921 | 9371 | 7616.6665 | 9403.292 |  | Program Management
[5 empty] | No. Sys Eng | 1.8576 | 1.5601 | 1.2769 | 2.3247 | 3.4187 | 2.0044 | 1.9978 | 1.5445 | 1.9099 | 1.8633 | 1.983 | 1.9429 | 1.9615 |  |  |  | 5004.978 | RBE |  | Project Manager | Appl. Project specific
[5 empty] | SW Dev (h) | 46381.48 | 27895.52 | 2215 | 4132 | 3334 | 1321 | 3381 | 3242 | 3109 | 4693 | 3852 | 2982 | 1024.1587 | 32261 | 29975.2682 | 37006.504 | 0 | FCE |  | Purchaser | Appl. Project specific
[5 empty] | No. SW Eng | 9.7084 | 5.839 | 4.8682 | 7.784 | 10.9913 | 8.7099 | 7.4308 | 5.344 | 6.833 | 6.1886 | 6.3495 | 6.5539 | 6.7527 |  |  |  | 659.7471 | RBE |  | Purchaser | Appl. Project specific
[5 empty] | Testing (h) | 16079.28 | 16458.72 | 1192 | 2673 | 2314 | 504 | 1836 | 1983 | 1880 | 3107 | 2458 | 1789 | 626.5397 | 19736 | 20393.0104 | 25176.556 | 9403.292 | System Engineering
[5 empty] | No. Test Eng | 3.3656 | 3.4451 | 2.6198 | 5.0355 | 7.6286 | 3.3231 | 4.0352 | 3.2687 | 4.1319 | 4.0972 | 4.0517 | 3.9319 | 4.131 |  |  |  | 5004.978 | RBE |  | Design Leader | Appl. Project specific
[5 empty] | P. Validation (h) | 264 | 198 | 165 | 0 | 48 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 7.619 | 240 | 196.83 | 243 | 1971.658 | RBE |  | System Engineer | Appl. Project specific
[5 empty] | No. Valid Eng. | 0.055259 | 0.041444 | 0.36264 | 0 | 0.15824 | 0 | 0 | 0 | 0 | 0.035605 | 0 | 0 | 0.050236 |  |  |  | 1364.994 | RBE |  | FUSA | Appl. Project specific
[5 empty] | Hardware (h) | 1600 | 3200 | 1280 | 960 | 960 | 0 | 0 | 0 | 0 | 321 | 160 | 0 | 116.8571 | 3681 | 2702.97 | 3337 | 2426.656 | RBE |  | System Engineer | Appl. Project specific
[5 empty] | No. HW Eng. | 0.3349 | 0.66981 | 2.8132 | 1.8085 | 3.1648 | 0 | 0 | 0 | 0 | 0.4233 | 0.26374 | 0 | 0.77049 |  |  |  | 0 | FCE |  | Optical Engineer | Appl. Project specific
[5 empty] | Mechanical (h) | 732 | 732 | 294 | 222 | 222 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 25.8095 | 813 | 920.97 | 1137
[5 empty] | No. Mech Eng. | 0.15322 | 0.15322 | 0.64616 | 0.41821 | 0.73187 | 0 | 0 | 0 | 0 | 0.098902 | 0 | 0 | 0.17017
[5 empty] | Project Manager (%) |  |  | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80%
[5 empty] | Project Manager (h) |  |  | 364 | 425 | 243 | 122 | 364 | 486 | 364 | 607 | 486 | 364 | 121.4286 | 3825 | 4054.0322 | 5004.978
[5 empty] | Quality (%) |  |  | 10% | 30% | 30% | 30% | 20% | 20% | 20% | 20% | 20% | 20%
[5 empty] | Quality (h) |  |  | 46 | 160 | 91 | 46 | 91 | 122 | 91 | 152 | 122 | 91 | 32.127 | 1012 | 1228.4946 | 1516.66
[5 empty] | Purchasing (%) |  |  | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15%
[5 empty] | Purchasing (h) |  |  | 69 | 80 | 46 | 23 | 69 | 91 | 69 | 114 | 91 | 69 | 22.8889 | 721 | 534.3952 | 659.7471
[22 empty] | 0 | AEF
[22 empty] | 3336.652 | Hardware
[22 empty] | 3260.819 | RBE | HW Engineer | HW Engineer | Appl. Project specific
[22 empty] | 75.833 | FCE | HW Engineer | HW Engineer | Appl. Project specific
[22 empty] | 1137.495 | FCE | Mechanical Engineer
[22 empty] | 37006.504 | Software
[22 empty] | 4853.312 | RBE | STL | STL | Appl. Project specific
[22 empty] | 5459.976 | RBE | Software Development | SW Engineer | Appl. Project specific
[22 empty] | 5459.976 | RBE | Software Development | SW Engineer | Appl. Project specific
[22 empty] | 5459.976 | RBE | Software Development | SW Engineer | Appl. Project specific
[22 empty] | 5459.976 | RBE | Software Development | SW Engineer | Appl. Project specific
[22 empty] | 5459.976 | RBE | Software Development | SW Engineer | Appl. Project specific
[22 empty] | 4853.312 | RBE | Software Development | SW Engineer | Appl. Project specific
[22 empty] | 25176.556 | Verification
[22 empty] | 3943.316 | RBE | VTL | SVTL | Appl. Project specific
[22 empty] | 5459.976 | RBE | Software Test | Test Eng | Appl. Project specific
[22 empty] | 5459.976 | RBE | Software Test | Test Eng | Appl. Project specific
[22 empty] | 5459.976 | RBE | Software Test | Test Eng | Appl. Project specific
[22 empty] | 242.6656 | RBE | Product Validation Eng | Test Eng | Appl. Project specific
[22 empty] | 4853.312 | RBE | Software Test | Test Eng | Appl. Project specific
[22 empty] | 0 | Quality
[22 empty] | 1516.66 | RBE | SQA | SQA | Appl. Project specific
|  | Feature Name | Task | Requirements | Complexity f. | Effort | Effort | Effort | Effort | Effort | Effort | Effort | Effort | Effort | Effort | Effort | Effort |  |  | Current Release - OpenProject Sync |  |  | R1.1 Archive- OpenProject Sync |  |  | R1.2 Release - OpenProject Sync
Feature | 1 | Accelerometer driver implementation |  | 50 | 1 |  |  | 100% | 110% | [6 empty] | 120% |  |  |  | OpenProject Task ID1 | OpenProject Release |  | OpenProject Task ID2 | OpenProject Release |  | OpenProject Task ID3 | OpenProject Release
Proc | 2 | [6 empty] | 100% | 10% | [6 empty] | 10%
Sum | 3 |  |  |  |  | 552 | 552 | 552 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 692
Sys Eng | 4 | Accelerometer driver implementation\Sys Eng |  |  |  | 84 | 84 | 84 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 116
SW Dev | 5 | Accelerometer driver implementation\SW Dev |  |  |  | 264 | 264 | 264 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 324
Testing | 6 | Accelerometer driver implementation\Testing |  |  |  | 204 | 204 | 204 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 252
1 | 7 |  | Customer Req Analysis | 50 | 1 | 4 | 4 | 4 | 1 | [6 empty] | 1 |  |  | 0.08
2 | 8 |  | Sys Requirements Creation | 50 | 1 | 8 | 8 | 8 | 1 | [6 empty] | 1 |  |  | 0.16
3 | 9 |  | Sys Requirements Verification Criteria | 50 | 1 | 2 | 2 | 2 | 1 | [6 empty] | 1 |  |  | 0.04
4 | 10 |  | Sys Requirements Review | 50 | 1 | 4 | 4 | 4 | 1 | [6 empty] | 1 |  |  | 0.08
5 | 11 |  | Sys Requirements Update after Review | 50 | 1 | 2 | 2 | 2 | 1 | [6 empty] | 1 |  |  | 0.04
6 | 12 |  | Sys Architecture Creation/Update | 50 | 1 | 6 | 6 | 6 | 1 | [6 empty] | 1 |  |  | 0.12
7 | 13 |  | Sys Arch Traceability | 50 | 1 | 4 | 4 | 4 | 1 | [6 empty] | 1 |  |  | 0.08
8 | 14 |  | Sys Architecture Review | 50 | 1 | 4 | 4 | 4 | 1 | [6 empty] | 1 |  |  | 0.08
9 | 15 |  | Sys Architecture Update after Review | 50 | 1 | 2 | 2 | 2 | 1 | [6 empty] | 1 |  |  | 0.04
10 | 16 |  | SW Requirements Creation | 50 | 1 | 24 | 24 | 24 | 3 | [6 empty] | 3 |  |  | 0.48
11 | 17 |  | SW Requirements Verification Criteria | 50 | 1 | 6 | 6 | 6 | 1 | [6 empty] | 1 |  |  | 0.12
12 | 18 |  | SW Requirements Review | 50 | 1 | 12 | 12 | 12 | 2 | [6 empty] | 2 |  |  | 0.24
13 | 19 |  | SW Requirements Update after Review | 50 | 1 | 6 | 6 | 6 | 1 | [6 empty] | 1 |  |  | 0.12
14 | 20 |  | SW Architecture Specification | 50 | 1 | 24 | 24 | 24 | 3 | [6 empty] | 3 |  |  | 0.48
15 | 21 |  | SW Architecture Specification Review | 50 | 1 | 8 | 8 | 8 | 1 | [6 empty] | 1 |  |  | 0.16
16 | 22 |  | Design Specification | 50 | 1 | 24 | 24 | 24 | 3 | [6 empty] | 3 |  |  | 0.48
17 | 23 |  | Design Specification Review | 50 | 1 | 8 | 8 | 8 | 1 | [6 empty] | 1 |  |  | 0.16
18 | 24 |  | Code Implementation | 50 | 1 | 40 | 40 | 40 | 4 | [6 empty] | 4 |  |  | 0.8
19 | 25 |  | QAC/Code Metrics Verification | 50 | 1 | 8 | 8 | 8 | 1 | [6 empty] | 1 |  |  | 0.16
20 | 26 |  | Code Review | 50 | 1 | 16 | 16 | 16 | 2 | [6 empty] | 2 |  |  | 0.32
21 | 27 |  | Unit Test Specification | 50 | 1 | 40 | 40 | 40 | 4 | [6 empty] | 4 |  |  | 0.8
22 | 28 |  | Unit Test Specification Review | 50 | 1 | 8 | 8 | 8 | 1 | [6 empty] | 1 |  |  | 0.16
23 | 29 |  | Unit Test Execution | 50 | 1 | 8 | 8 | 8 | 1 | [6 empty] | 1 |  |  | 0.16
24 | 30 |  | SW Integration Test Specification | 50 | 1 | 40 | 40 | 40 | 4 | [6 empty] | 4 |  |  | 0.8
25 | 31 |  | SW Integration Test Specification Review | 50 | 1 | 16 | 16 | 16 | 2 | [6 empty] | 2 |  |  | 0.32
26 | 32 |  | SW Integration Test Execution | 50 | 1 | 24 | 24 | 24 | 3 | [6 empty] | 3 |  |  | 0.48
27 | 33 |  | SW Qualification Test Specification | 50 | 1 | 40 | 40 | 40 | 4 | [6 empty] | 4 |  |  | 0.8
28 | 34 |  | SW Qualification Test Specification Review | 50 | 1 | 10 | 10 | 10 | 1 | [6 empty] | 1 |  |  | 0.2
29 | 35 |  | SW Qualification Test Execution | 50 | 1 | 24 | 24 | 24 | 3 | [6 empty] | 3 |  |  | 0.48
30 | 36 |  | Sys Integration Test Specification | 50 | 1 | 40 | 40 | 40 | 4 | [6 empty] | 4 |  |  | 0.8
31 | 37 |  | Sys Integration Test Specification Review | 50 | 1 | 16 | 16 | 16 | 2 | [6 empty] | 2 |  |  | 0.32
32 | 38 |  | Sys Integration Test Execution | 50 | 1 | 32 | 32 | 32 | 4 | [6 empty] | 4 |  |  | 0.64
33 | 39 |  | Sys Qualification Test Specification | 50 | 1 | 24 | 24 | 24 | 3 | [6 empty] | 3 |  |  | 0.48
34 | 40 |  | Sys Qualification Test Specification Review | 50 | 1 | 6 | 6 | 6 | 1 | [6 empty] | 1 |  |  | 0.12
35 | 41 |  | Sys Qualification Test Execution | 50 | 1 | 12 | 12 | 12 | 2 | [6 empty] | 2 |  |  | 0.24
Feature | 42 | eCS Algo |  | 100 | 2 |  |  | 40% | 60% | 80% | 90% | 100% |  |  |  | 110% | 120% |  |  | 929731;50%;930406;50% | R1.1 |  | 929731;50%;930406;50% | R1.1 |  | 1025706;60%;1027207;40% | R1.2
Proc | 43 | [6 empty] | 40% | 20% | 20% | 10% | 10% |  |  |  | 10% | 10%
Sum | 44 |  |  |  |  | 1104 | 2208 | 898 | 457 | 457 | 235 | 235 | 0 | 0 | 0 | 235 | 235 | 2752
Sys Eng | 45 | eCS Algo\Sys Eng |  |  |  | 168 | 336 | 142 | 74 | 74 | 39 | 39 | 0 | 0 | 0 | 39 | 39 | 446
SW Dev | 46 | eCS Algo\SW Dev |  |  |  | 528 | 1056 | 426 | 217 | 217 | 112 | 112 | 0 | 0 | 0 | 112 | 112 | 1308
Testing | 47 | eCS Algo\Testing |  |  |  | 408 | 816 | 330 | 166 | 166 | 84 | 84 | 0 | 0 | 0 | 84 | 84 | 998
1 | 48 |  | Customer Req Analysis | 100 | 2 | 8 | 16 | 7 | 4 | 4 | 2 | 2 |  |  |  | 2 | 2
2 | 49 |  | Sys Requirements Creation | 100 | 2 | 16 | 32 | 13 | 7 | 7 | 4 | 4 |  |  |  | 4 | 4
3 | 50 |  | Sys Requirements Verification Criteria | 100 | 2 | 4 | 8 | 4 | 2 | 2 | 1 | 1 |  |  |  | 1 | 1
4 | 51 |  | Sys Requirements Review | 100 | 2 | 8 | 16 | 7 | 4 | 4 | 2 | 2 |  |  |  | 2 | 2
5 | 52 |  | Sys Requirements Update after Review | 100 | 2 | 4 | 8 | 4 | 2 | 2 | 1 | 1 |  |  |  | 1 | 1
6 | 53 |  | Sys Architecture Creation/Update | 100 | 2 | 12 | 24 | 10 | 5 | 5 | 3 | 3 |  |  |  | 3 | 3
7 | 54 |  | Sys Arch Traceability | 100 | 2 | 8 | 16 | 7 | 4 | 4 | 2 | 2 |  |  |  | 2 | 2
8 | 55 |  | Sys Architecture Review | 100 | 2 | 8 | 16 | 7 | 4 | 4 | 2 | 2 |  |  |  | 2 | 2
9 | 56 |  | Sys Architecture Update after Review | 100 | 2 | 4 | 8 | 4 | 2 | 2 | 1 | 1 |  |  |  | 1 | 1
10 | 57 |  | SW Requirements Creation | 100 | 2 | 48 | 96 | 39 | 20 | 20 | 10 | 10 |  |  |  | 10 | 10
11 | 58 |  | SW Requirements Verification Criteria | 100 | 2 | 12 | 24 | 10 | 5 | 5 | 3 | 3 |  |  |  | 3 | 3
12 | 59 |  | SW Requirements Review | 100 | 2 | 24 | 48 | 20 | 10 | 10 | 5 | 5 |  |  |  | 5 | 5
13 | 60 |  | SW Requirements Update after Review | 100 | 2 | 12 | 24 | 10 | 5 | 5 | 3 | 3 |  |  |  | 3 | 3
14 | 61 |  | SW Architecture Specification | 100 | 2 | 48 | 96 | 39 | 20 | 20 | 10 | 10 |  |  |  | 10 | 10
15 | 62 |  | SW Architecture Specification Review | 100 | 2 | 16 | 32 | 13 | 7 | 7 | 4 | 4 |  |  |  | 4 | 4
16 | 63 |  | Design Specification | 100 | 2 | 48 | 96 | 39 | 20 | 20 | 10 | 10 |  |  |  | 10 | 10
17 | 64 |  | Design Specification Review | 100 | 2 | 16 | 32 | 13 | 7 | 7 | 4 | 4 |  |  |  | 4 | 4
18 | 65 |  | Code Implementation | 100 | 2 | 80 | 160 | 64 | 32 | 32 | 16 | 16 |  |  |  | 16 | 16
19 | 66 |  | QAC/Code Metrics Verification | 100 | 2 | 16 | 32 | 13 | 7 | 7 | 4 | 4 |  |  |  | 4 | 4
20 | 67 |  | Code Review | 100 | 2 | 32 | 64 | 26 | 13 | 13 | 7 | 7 |  |  |  | 7 | 7
21 | 68 |  | Unit Test Specification | 100 | 2 | 80 | 160 | 64 | 32 | 32 | 16 | 16 |  |  |  | 16 | 16
22 | 69 |  | Unit Test Specification Review | 100 | 2 | 16 | 32 | 13 | 7 | 7 | 4 | 4 |  |  |  | 4 | 4
23 | 70 |  | Unit Test Execution | 100 | 2 | 16 | 32 | 13 | 7 | 7 | 4 | 4 |  |  |  | 4 | 4
24 | 71 |  | SW Integration Test Specification | 100 | 2 | 80 | 160 | 64 | 32 | 32 | 16 | 16 |  |  |  | 16 | 16
25 | 72 |  | SW Integration Test Specification Review | 100 | 2 | 32 | 64 | 26 | 13 | 13 | 7 | 7 |  |  |  | 7 | 7
26 | 73 |  | SW Integration Test Execution | 100 | 2 | 48 | 96 | 39 | 20 | 20 | 10 | 10 |  |  |  | 10 | 10
27 | 74 |  | SW Qualification Test Specification | 100 | 2 | 80 | 160 | 64 | 32 | 32 | 16 | 16 |  |  |  | 16 | 16
28 | 75 |  | SW Qualification Test Specification Review | 100 | 2 | 20 | 40 | 16 | 8 | 8 | 4 | 4 |  |  |  | 4 | 4
29 | 76 |  | SW Qualification Test Execution | 100 | 2 | 48 | 96 | 39 | 20 | 20 | 10 | 10 |  |  |  | 10 | 10
30 | 77 |  | Sys Integration Test Specification | 100 | 2 | 80 | 160 | 64 | 32 | 32 | 16 | 16 |  |  |  | 16 | 16
31 | 78 |  | Sys Integration Test Specification Review | 100 | 2 | 32 | 64 | 26 | 13 | 13 | 7 | 7 |  |  |  | 7 | 7
32 | 79 |  | Sys Integration Test Execution | 100 | 2 | 64 | 128 | 52 | 26 | 26 | 13 | 13 |  |  |  | 13 | 13
33 | 80 |  | Sys Qualification Test Specification | 100 | 2 | 48 | 96 | 39 | 20 | 20 | 10 | 10 |  |  |  | 10 | 10
34 | 81 |  | Sys Qualification Test Specification Review | 100 | 2 | 12 | 24 | 10 | 5 | 5 | 3 | 3 |  |  |  | 3 | 3
35 | 82 |  | Sys Qualification Test Execution | 100 | 2 | 24 | 48 | 20 | 10 | 10 | 5 | 5 |  |  |  | 5 | 5
Feature | 83 | Solenoid control |  | 90 | 1.5 |  |  | 40% | 60% | 80% | 90% | 100% |  |  |  | 110% | 120% |  |  | 929733;40%;930407;30%;930408;30% | R1.1 |  | 929733;40%;930407;30%;930407;30% | R1.1 |  | 1027208 | R1.2
Proc | 84 | [6 empty] | 40% | 20% | 20% | 10% | 10% |  |  |  | 10% | 10%
Sum | 85 |  |  |  |  | 993.6 | 1490.4 | 613 | 317 | 317 | 169 | 169 | 0 | 0 | 0 | 169 | 169 | 1923
Sys Eng | 86 | Solenoid control\Sys Eng |  |  |  | 151.2 | 226.8 | 98 | 55 | 55 | 31 | 31 | 0 | 0 | 0 | 31 | 31 | 332
SW Dev | 87 | Solenoid control\SW Dev |  |  |  | 475.2 | 712.8 | 291 | 148 | 148 | 79 | 79 | 0 | 0 | 0 | 79 | 79 | 903
Testing | 88 | Solenoid control\Testing |  |  |  | 367.2 | 550.8 | 224 | 114 | 114 | 59 | 59 | 0 | 0 | 0 | 59 | 59 | 688
1 | 89 |  | Customer Req Analysis | 90 | 1.5 | 7.2 | 10.8 | 5 | 3 | 3 | 2 | 2 |  |  |  | 2 | 2
2 | 90 |  | Sys Requirements Creation | 90 | 1.5 | 14.4 | 21.6 | 9 | 5 | 5 | 3 | 3 |  |  |  | 3 | 3
3 | 91 |  | Sys Requirements Verification Criteria | 90 | 1.5 | 3.6 | 5.4 | 3 | 2 | 2 | 1 | 1 |  |  |  | 1 | 1
4 | 92 |  | Sys Requirements Review | 90 | 1.5 | 7.2 | 10.8 | 5 | 3 | 3 | 2 | 2 |  |  |  | 2 | 2
5 | 93 |  | Sys Requirements Update after Review | 90 | 1.5 | 3.6 | 5.4 | 3 | 2 | 2 | 1 | 1 |  |  |  | 1 | 1
6 | 94 |  | Sys Architecture Creation/Update | 90 | 1.5 | 10.8 | 16.2 | 7 | 4 | 4 | 2 | 2 |  |  |  | 2 | 2
7 | 95 |  | Sys Arch Traceability | 90 | 1.5 | 7.2 | 10.8 | 5 | 3 | 3 | 2 | 2 |  |  |  | 2 | 2
8 | 96 |  | Sys Architecture Review | 90 | 1.5 | 7.2 | 10.8 | 5 | 3 | 3 | 2 | 2 |  |  |  | 2 | 2
9 | 97 |  | Sys Architecture Update after Review | 90 | 1.5 | 3.6 | 5.4 | 3 | 2 | 2 | 1 | 1 |  |  |  | 1 | 1
10 | 98 |  | SW Requirements Creation | 90 | 1.5 | 43.2 | 64.8 | 26 | 13 | 13 | 7 | 7 |  |  |  | 7 | 7
11 | 99 |  | SW Requirements Verification Criteria | 90 | 1.5 | 10.8 | 16.2 | 7 | 4 | 4 | 2 | 2 |  |  |  | 2 | 2
12 | 100 |  | SW Requirements Review | 90 | 1.5 | 21.6 | 32.4 | 13 | 7 | 7 | 4 | 4 |  |  |  | 4 | 4
13 | 101 |  | SW Requirements Update after Review | 90 | 1.5 | 10.8 | 16.2 | 7 | 4 | 4 | 2 | 2 |  |  |  | 2 | 2
14 | 102 |  | SW Architecture Specification | 90 | 1.5 | 43.2 | 64.8 | 26 | 13 | 13 | 7 | 7 |  |  |  | 7 | 7
15 | 103 |  | SW Architecture Specification Review | 90 | 1.5 | 14.4 | 21.6 | 9 | 5 | 5 | 3 | 3 |  |  |  | 3 | 3
16 | 104 |  | Design Specification | 90 | 1.5 | 43.2 | 64.8 | 26 | 13 | 13 | 7 | 7 |  |  |  | 7 | 7
17 | 105 |  | Design Specification Review | 90 | 1.5 | 14.4 | 21.6 | 9 | 5 | 5 | 3 | 3 |  |  |  | 3 | 3
18 | 106 |  | Code Implementation | 90 | 1.5 | 72 | 108 | 44 | 22 | 22 | 11 | 11 |  |  |  | 11 | 11
19 | 107 |  | QAC/Code Metrics Verification | 90 | 1.5 | 14.4 | 21.6 | 9 | 5 | 5 | 3 | 3 |  |  |  | 3 | 3
20 | 108 |  | Code Review | 90 | 1.5 | 28.8 | 43.2 | 18 | 9 | 9 | 5 | 5 |  |  |  | 5 | 5
21 | 109 |  | Unit Test Specification | 90 | 1.5 | 72 | 108 | 44 | 22 | 22 | 11 | 11 |  |  |  | 11 | 11
22 | 110 |  | Unit Test Specification Review | 90 | 1.5 | 14.4 | 21.6 | 9 | 5 | 5 | 3 | 3 |  |  |  | 3 | 3
23 | 111 |  | Unit Test Execution | 90 | 1.5 | 14.4 | 21.6 | 9 | 5 | 5 | 3 | 3 |  |  |  | 3 | 3
24 | 112 |  | SW Integration Test Specification | 90 | 1.5 | 72 | 108 | 44 | 22 | 22 | 11 | 11 |  |  |  | 11 | 11
25 | 113 |  | SW Integration Test Specification Review | 90 | 1.5 | 28.8 | 43.2 | 18 | 9 | 9 | 5 | 5 |  |  |  | 5 | 5
26 | 114 |  | SW Integration Test Execution | 90 | 1.5 | 43.2 | 64.8 | 26 | 13 | 13 | 7 | 7 |  |  |  | 7 | 7
27 | 115 |  | SW Qualification Test Specification | 90 | 1.5 | 72 | 108 | 44 | 22 | 22 | 11 | 11 |  |  |  | 11 | 11
28 | 116 |  | SW Qualification Test Specification Review | 90 | 1.5 | 18 | 27 | 11 | 6 | 6 | 3 | 3 |  |  |  | 3 | 3
29 | 117 |  | SW Qualification Test Execution | 90 | 1.5 | 43.2 | 64.8 | 26 | 13 | 13 | 7 | 7 |  |  |  | 7 | 7
30 | 118 |  | Sys Integration Test Specification | 90 | 1.5 | 72 | 108 | 44 | 22 | 22 | 11 | 11 |  |  |  | 11 | 11
31 | 119 |  | Sys Integration Test Specification Review | 90 | 1.5 | 28.8 | 43.2 | 18 | 9 | 9 | 5 | 5 |  |  |  | 5 | 5
32 | 120 |  | Sys Integration Test Execution | 90 | 1.5 | 57.6 | 86.4 | 35 | 18 | 18 | 9 | 9 |  |  |  | 9 | 9
33 | 121 |  | Sys Qualification Test Specification | 90 | 1.5 | 43.2 | 64.8 | 26 | 13 | 13 | 7 | 7 |  |  |  | 7 | 7
34 | 122 |  | Sys Qualification Test Specification Review | 90 | 1.5 | 10.8 | 16.2 | 7 | 4 | 4 | 2 | 2 |  |  |  | 2 | 2
35 | 123 |  | Sys Qualification Test Execution | 90 | 1.5 | 21.6 | 32.4 | 13 | 7 | 7 | 4 | 4 |  |  |  | 4 | 4
Feature | 124 | Solenoid Diagnostic |  | 50 | 1 |  |  |  | 70% | 80% |  | 100% |  |  |  | 110% | 120% |  |  | 929735 | R1.1 |  | 929735 | R1.1
Proc | 125 | [7 empty] | 70% | 10% |  | 20% |  |  |  | 10% | 10%
Sum | 126 |  |  |  |  | 552 | 552 | 0 | 400 | 70 | 0 | 124 | 0 | 0 | 0 | 70 | 70 | 734
Sys Eng | 127 | Solenoid Diagnostic\Sys Eng |  |  |  | 84 | 84 | 0 | 65 | 16 | 0 | 23 | 0 | 0 | 0 | 16 | 16 | 136
SW Dev | 128 | Solenoid Diagnostic\SW Dev |  |  |  | 264 | 264 | 0 | 189 | 30 | 0 | 57 | 0 | 0 | 0 | 30 | 30 | 336
Testing | 129 | Solenoid Diagnostic\Testing |  |  |  | 204 | 204 | 0 | 146 | 24 | 0 | 44 | 0 | 0 | 0 | 24 | 24 | 262
1 | 130 |  | Customer Req Analysis | 50 | 1 | 4 | 4 |  | 3 | 1 |  | 1 |  |  |  | 1 | 1
2 | 131 |  | Sys Requirements Creation | 50 | 1 | 8 | 8 |  | 6 | 1 |  | 2 |  |  |  | 1 | 1
3 | 132 |  | Sys Requirements Verification Criteria | 50 | 1 | 2 | 2 |  | 2 | 1 |  | 1 |  |  |  | 1 | 1
4 | 133 |  | Sys Requirements Review | 50 | 1 | 4 | 4 |  | 3 | 1 |  | 1 |  |  |  | 1 | 1
5 | 134 |  | Sys Requirements Update after Review | 50 | 1 | 2 | 2 |  | 2 | 1 |  | 1 |  |  |  | 1 | 1
6 | 135 |  | Sys Architecture Creation/Update | 50 | 1 | 6 | 6 |  | 5 | 1 |  | 2 |  |  |  | 1 | 1
7 | 136 |  | Sys Arch Traceability | 50 | 1 | 4 | 4 |  | 3 | 1 |  | 1 |  |  |  | 1 | 1
8 | 137 |  | Sys Architecture Review | 50 | 1 | 4 | 4 |  | 3 | 1 |  | 1 |  |  |  | 1 | 1
9 | 138 |  | Sys Architecture Update after Review | 50 | 1 | 2 | 2 |  | 2 | 1 |  | 1 |  |  |  | 1 | 1
10 | 139 |  | SW Requirements Creation | 50 | 1 | 24 | 24 |  | 17 | 3 |  | 5 |  |  |  | 3 | 3
11 | 140 |  | SW Requirements Verification Criteria | 50 | 1 | 6 | 6 |  | 5 | 1 |  | 2 |  |  |  | 1 | 1
12 | 141 |  | SW Requirements Review | 50 | 1 | 12 | 12 |  | 9 | 2 |  | 3 |  |  |  | 2 | 2
13 | 142 |  | SW Requirements Update after Review | 50 | 1 | 6 | 6 |  | 5 | 1 |  | 2 |  |  |  | 1 | 1
14 | 143 |  | SW Architecture Specification | 50 | 1 | 24 | 24 |  | 17 | 3 |  | 5 |  |  |  | 3 | 3
15 | 144 |  | SW Architecture Specification Review | 50 | 1 | 8 | 8 |  | 6 | 1 |  | 2 |  |  |  | 1 | 1
16 | 145 |  | Design Specification | 50 | 1 | 24 | 24 |  | 17 | 3 |  | 5 |  |  |  | 3 | 3
17 | 146 |  | Design Specification Review | 50 | 1 | 8 | 8 |  | 6 | 1 |  | 2 |  |  |  | 1 | 1
18 | 147 |  | Code Implementation | 50 | 1 | 40 | 40 |  | 28 | 4 |  | 8 |  |  |  | 4 | 4
19 | 148 |  | QAC/Code Metrics Verification | 50 | 1 | 8 | 8 |  | 6 | 1 |  | 2 |  |  |  | 1 | 1
20 | 149 |  | Code Review | 50 | 1 | 16 | 16 |  | 12 | 2 |  | 4 |  |  |  | 2 | 2
21 | 150 |  | Unit Test Specification | 50 | 1 | 40 | 40 |  | 28 | 4 |  | 8 |  |  |  | 4 | 4
22 | 151 |  | Unit Test Specification Review | 50 | 1 | 8 | 8 |  | 6 | 1 |  | 2 |  |  |  | 1 | 1
23 | 152 |  | Unit Test Execution | 50 | 1 | 8 | 8 |  | 6 | 1 |  | 2 |  |  |  | 1 | 1
24 | 153 |  | SW Integration Test Specification | 50 | 1 | 40 | 40 |  | 28 | 4 |  | 8 |  |  |  | 4 | 4
25 | 154 |  | SW Integration Test Specification Review | 50 | 1 | 16 | 16 |  | 12 | 2 |  | 4 |  |  |  | 2 | 2
26 | 155 |  | SW Integration Test Execution | 50 | 1 | 24 | 24 |  | 17 | 3 |  | 5 |  |  |  | 3 | 3
27 | 156 |  | SW Qualification Test Specification | 50 | 1 | 40 | 40 |  | 28 | 4 |  | 8 |  |  |  | 4 | 4
28 | 157 |  | SW Qualification Test Specification Review | 50 | 1 | 10 | 10 |  | 7 | 1 |  | 2 |  |  |  | 1 | 1
29 | 158 |  | SW Qualification Test Execution | 50 | 1 | 24 | 24 |  | 17 | 3 |  | 5 |  |  |  | 3 | 3
30 | 159 |  | Sys Integration Test Specification | 50 | 1 | 40 | 40 |  | 28 | 4 |  | 8 |  |  |  | 4 | 4
31 | 160 |  | Sys Integration Test Specification Review | 50 | 1 | 16 | 16 |  | 12 | 2 |  | 4 |  |  |  | 2 | 2
32 | 161 |  | Sys Integration Test Execution | 50 | 1 | 32 | 32 |  | 23 | 4 |  | 7 |  |  |  | 4 | 4
33 | 162 |  | Sys Qualification Test Specification | 50 | 1 | 24 | 24 |  | 17 | 3 |  | 5 |  |  |  | 3 | 3
34 | 163 |  | Sys Qualification Test Specification Review | 50 | 1 | 6 | 6 |  | 5 | 1 |  | 2 |  |  |  | 1 | 1
35 | 164 |  | Sys Qualification Test Execution | 50 | 1 | 12 | 12 |  | 9 | 2 |  | 3 |  |  |  | 2 | 2
Feature | 165 | Wake-up by wire |  | 150 | 1.5 |  |  | 20% | 40% | 70% | 80% |  | 100% |  |  | 110% | 120% |  |  | 929737 | R1.1 |  | 929737 | R1.1 |  | 1027209 | R1.2
Proc | 166 | [6 empty] | 20% | 20% | 30% | 10% |  | 20% |  |  | 10% | 10%
Sum | 167 |  |  |  |  | 1656 | 2484 | 511 | 511 | 761 | 259 | 0 | 511 | 0 | 0 | 259 | 259 | 3071
Sys Eng | 168 | Wake-up by wire\Sys Eng |  |  |  | 252 | 378 | 81 | 81 | 121 | 41 | 0 | 81 | 0 | 0 | 41 | 41 | 487
SW Dev | 169 | Wake-up by wire\SW Dev |  |  |  | 792 | 1188 | 244 | 244 | 360 | 123 | 0 | 244 | 0 | 0 | 123 | 123 | 1461
Testing | 170 | Wake-up by wire\Testing |  |  |  | 612 | 918 | 186 | 186 | 280 | 95 | 0 | 186 | 0 | 0 | 95 | 95 | 1123
1 | 171 |  | Customer Req Analysis | 150 | 1.5 | 12 | 18 | 4 | 4 | 6 | 2 |  | 4 |  |  | 2 | 2
2 | 172 |  | Sys Requirements Creation | 150 | 1.5 | 24 | 36 | 8 | 8 | 11 | 4 |  | 8 |  |  | 4 | 4
3 | 173 |  | Sys Requirements Verification Criteria | 150 | 1.5 | 6 | 9 | 2 | 2 | 3 | 1 |  | 2 |  |  | 1 | 1
4 | 174 |  | Sys Requirements Review | 150 | 1.5 | 12 | 18 | 4 | 4 | 6 | 2 |  | 4 |  |  | 2 | 2
5 | 175 |  | Sys Requirements Update after Review | 150 | 1.5 | 6 | 9 | 2 | 2 | 3 | 1 |  | 2 |  |  | 1 | 1
6 | 176 |  | Sys Architecture Creation/Update | 150 | 1.5 | 18 | 27 | 6 | 6 | 9 | 3 |  | 6 |  |  | 3 | 3
7 | 177 |  | Sys Arch Traceability | 150 | 1.5 | 12 | 18 | 4 | 4 | 6 | 2 |  | 4 |  |  | 2 | 2
8 | 178 |  | Sys Architecture Review | 150 | 1.5 | 12 | 18 | 4 | 4 | 6 | 2 |  | 4 |  |  | 2 | 2
9 | 179 |  | Sys Architecture Update after Review | 150 | 1.5 | 6 | 9 | 2 | 2 | 3 | 1 |  | 2 |  |  | 1 | 1
10 | 180 |  | SW Requirements Creation | 150 | 1.5 | 72 | 108 | 22 | 22 | 33 | 11 |  | 22 |  |  | 11 | 11
11 | 181 |  | SW Requirements Verification Criteria | 150 | 1.5 | 18 | 27 | 6 | 6 | 9 | 3 |  | 6 |  |  | 3 | 3
12 | 182 |  | SW Requirements Review | 150 | 1.5 | 36 | 54 | 11 | 11 | 17 | 6 |  | 11 |  |  | 6 | 6
13 | 183 |  | SW Requirements Update after Review | 150 | 1.5 | 18 | 27 | 6 | 6 | 9 | 3 |  | 6 |  |  | 3 | 3
14 | 184 |  | SW Architecture Specification | 150 | 1.5 | 72 | 108 | 22 | 22 | 33 | 11 |  | 22 |  |  | 11 | 11
15 | 185 |  | SW Architecture Specification Review | 150 | 1.5 | 24 | 36 | 8 | 8 | 11 | 4 |  | 8 |  |  | 4 | 4
16 | 186 |  | Design Specification | 150 | 1.5 | 72 | 108 | 22 | 22 | 33 | 11 |  | 22 |  |  | 11 | 11
17 | 187 |  | Design Specification Review | 150 | 1.5 | 24 | 36 | 8 | 8 | 11 | 4 |  | 8 |  |  | 4 | 4
18 | 188 |  | Code Implementation | 150 | 1.5 | 120 | 180 | 36 | 36 | 54 | 18 |  | 36 |  |  | 18 | 18
19 | 189 |  | QAC/Code Metrics Verification | 150 | 1.5 | 24 | 36 | 8 | 8 | 11 | 4 |  | 8 |  |  | 4 | 4
20 | 190 |  | Code Review | 150 | 1.5 | 48 | 72 | 15 | 15 | 22 | 8 |  | 15 |  |  | 8 | 8
21 | 191 |  | Unit Test Specification | 150 | 1.5 | 120 | 180 | 36 | 36 | 54 | 18 |  | 36 |  |  | 18 | 18
22 | 192 |  | Unit Test Specification Review | 150 | 1.5 | 24 | 36 | 8 | 8 | 11 | 4 |  | 8 |  |  | 4 | 4
23 | 193 |  | Unit Test Execution | 150 | 1.5 | 24 | 36 | 8 | 8 | 11 | 4 |  | 8 |  |  | 4 | 4
24 | 194 |  | SW Integration Test Specification | 150 | 1.5 | 120 | 180 | 36 | 36 | 54 | 18 |  | 36 |  |  | 18 | 18
25 | 195 |  | SW Integration Test Specification Review | 150 | 1.5 | 48 | 72 | 15 | 15 | 22 | 8 |  | 15 |  |  | 8 | 8
26 | 196 |  | SW Integration Test Execution | 150 | 1.5 | 72 | 108 | 22 | 22 | 33 | 11 |  | 22 |  |  | 11 | 11
27 | 197 |  | SW Qualification Test Specification | 150 | 1.5 | 120 | 180 | 36 | 36 | 54 | 18 |  | 36 |  |  | 18 | 18
28 | 198 |  | SW Qualification Test Specification Review | 150 | 1.5 | 30 | 45 | 9 | 9 | 14 | 5 |  | 9 |  |  | 5 | 5
29 | 199 |  | SW Qualification Test Execution | 150 | 1.5 | 72 | 108 | 22 | 22 | 33 | 11 |  | 22 |  |  | 11 | 11
30 | 200 |  | Sys Integration Test Specification | 150 | 1.5 | 120 | 180 | 36 | 36 | 54 | 18 |  | 36 |  |  | 18 | 18
31 | 201 |  | Sys Integration Test Specification Review | 150 | 1.5 | 48 | 72 | 15 | 15 | 22 | 8 |  | 15 |  |  | 8 | 8
32 | 202 |  | Sys Integration Test Execution | 150 | 1.5 | 96 | 144 | 29 | 29 | 44 | 15 |  | 29 |  |  | 15 | 15
33 | 203 |  | Sys Qualification Test Specification | 150 | 1.5 | 72 | 108 | 22 | 22 | 33 | 11 |  | 22 |  |  | 11 | 11
34 | 204 |  | Sys Qualification Test Specification Review | 150 | 1.5 | 18 | 27 | 6 | 6 | 9 | 3 |  | 6 |  |  | 3 | 3
35 | 205 |  | Sys Qualification Test Execution | 150 | 1.5 | 36 | 54 | 11 | 11 | 17 | 6 |  | 11 |  |  | 6 | 6
Feature | 206 | Bootloader |  | 300 | 1 |  |  | 20% |  | 35% |  |  | 50% | 80% | 100% | 110% | 120% |  |  | 930399;70%;930405;30% | R1.1 |  | 930399;70%; 930405;30% | R1.1
Proc | 207 | [6 empty] | 20% |  | 15% |  |  | 15% | 30% | 20% | 10% | 10%
Sum | 208 |  |  |  |  | 3312 | 3312 | 676 | 0 | 511 | 0 | 0 | 511 | 1009 | 676 | 347 | 346 | 4076
Sys Eng | 209 | Bootloader\Sys Eng |  |  |  | 504 | 504 | 107 | 0 | 81 | 0 | 0 | 81 | 158 | 107 | 58 | 58 | 650
SW Dev | 210 | Bootloader\SW Dev |  |  |  | 1584 | 1584 | 321 | 0 | 244 | 0 | 0 | 244 | 481 | 321 | 162 | 162 | 1935
Testing | 211 | Bootloader\Testing |  |  |  | 1224 | 1224 | 248 | 0 | 186 | 0 | 0 | 186 | 370 | 248 | 127 | 126 | 1491
1 | 212 |  | Customer Req Analysis | 300 | 1 | 24 | 24 | 5 |  | 4 |  |  | 4 | 8 | 5 | 3 | 3
2 | 213 |  | Sys Requirements Creation | 300 | 1 | 48 | 48 | 10 |  | 8 |  |  | 8 | 15 | 10 | 5 | 5
3 | 214 |  | Sys Requirements Verification Criteria | 300 | 1 | 12 | 12 | 3 |  | 2 |  |  | 2 | 4 | 3 | 2 | 2
4 | 215 |  | Sys Requirements Review | 300 | 1 | 24 | 24 | 5 |  | 4 |  |  | 4 | 8 | 5 | 3 | 3
5 | 216 |  | Sys Requirements Update after Review | 300 | 1 | 12 | 12 | 3 |  | 2 |  |  | 2 | 4 | 3 | 2 | 2
6 | 217 |  | Sys Architecture Creation/Update | 300 | 1 | 36 | 36 | 8 |  | 6 |  |  | 6 | 11 | 8 | 4 | 4
7 | 218 |  | Sys Arch Traceability | 300 | 1 | 24 | 24 | 5 |  | 4 |  |  | 4 | 8 | 5 | 3 | 3
8 | 219 |  | Sys Architecture Review | 300 | 1 | 24 | 24 | 5 |  | 4 |  |  | 4 | 8 | 5 | 3 | 3
9 | 220 |  | Sys Architecture Update after Review | 300 | 1 | 12 | 12 | 3 |  | 2 |  |  | 2 | 4 | 3 | 2 | 2
10 | 221 |  | SW Requirements Creation | 300 | 1 | 144 | 144 | 29 |  | 22 |  |  | 22 | 44 | 29 | 15 | 15
11 | 222 |  | SW Requirements Verification Criteria | 300 | 1 | 36 | 36 | 8 |  | 6 |  |  | 6 | 11 | 8 | 4 | 4
12 | 223 |  | SW Requirements Review | 300 | 1 | 72 | 72 | 15 |  | 11 |  |  | 11 | 22 | 15 | 8 | 8
13 | 224 |  | SW Requirements Update after Review | 300 | 1 | 36 | 36 | 8 |  | 6 |  |  | 6 | 11 | 8 | 4 | 4
14 | 225 |  | SW Architecture Specification | 300 | 1 | 144 | 144 | 29 |  | 22 |  |  | 22 | 44 | 29 | 15 | 15
15 | 226 |  | SW Architecture Specification Review | 300 | 1 | 48 | 48 | 10 |  | 8 |  |  | 8 | 15 | 10 | 5 | 5
16 | 227 |  | Design Specification | 300 | 1 | 144 | 144 | 29 |  | 22 |  |  | 22 | 44 | 29 | 15 | 15
17 | 228 |  | Design Specification Review | 300 | 1 | 48 | 48 | 10 |  | 8 |  |  | 8 | 15 | 10 | 5 | 5
18 | 229 |  | Code Implementation | 300 | 1 | 240 | 240 | 48 |  | 36 |  |  | 36 | 72 | 48 | 24 | 24
19 | 230 |  | QAC/Code Metrics Verification | 300 | 1 | 48 | 48 | 10 |  | 8 |  |  | 8 | 15 | 10 | 5 | 5
20 | 231 |  | Code Review | 300 | 1 | 96 | 96 | 20 |  | 15 |  |  | 15 | 29 | 20 | 10 | 10
21 | 232 |  | Unit Test Specification | 300 | 1 | 240 | 240 | 48 |  | 36 |  |  | 36 | 72 | 48 | 24 | 24
22 | 233 |  | Unit Test Specification Review | 300 | 1 | 48 | 48 | 10 |  | 8 |  |  | 8 | 15 | 10 | 5 | 5
23 | 234 |  | Unit Test Execution | 300 | 1 | 48 | 48 | 10 |  | 8 |  |  | 8 | 15 | 10 | 5 | 5
24 | 235 |  | SW Integration Test Specification | 300 | 1 | 240 | 240 | 48 |  | 36 |  |  | 36 | 72 | 48 | 24 | 24
25 | 236 |  | SW Integration Test Specification Review | 300 | 1 | 96 | 96 | 20 |  | 15 |  |  | 15 | 29 | 20 | 10 | 10
26 | 237 |  | SW Integration Test Execution | 300 | 1 | 144 | 144 | 29 |  | 22 |  |  | 22 | 44 | 29 | 15 | 15
27 | 238 |  | SW Qualification Test Specification | 300 | 1 | 240 | 240 | 48 |  | 36 |  |  | 36 | 72 | 48 | 24 | 24
28 | 239 |  | SW Qualification Test Specification Review | 300 | 1 | 60 | 60 | 12 |  | 9 |  |  | 9 | 18 | 12 | 7 | 6
29 | 240 |  | SW Qualification Test Execution | 300 | 1 | 144 | 144 | 29 |  | 22 |  |  | 22 | 44 | 29 | 15 | 15
30 | 241 |  | Sys Integration Test Specification | 300 | 1 | 240 | 240 | 48 |  | 36 |  |  | 36 | 72 | 48 | 24 | 24
31 | 242 |  | Sys Integration Test Specification Review | 300 | 1 | 96 | 96 | 20 |  | 15 |  |  | 15 | 29 | 20 | 10 | 10
32 | 243 |  | Sys Integration Test Execution | 300 | 1 | 192 | 192 | 39 |  | 29 |  |  | 29 | 58 | 39 | 20 | 20
33 | 244 |  | Sys Qualification Test Specification | 300 | 1 | 144 | 144 | 29 |  | 22 |  |  | 22 | 44 | 29 | 15 | 15
34 | 245 |  | Sys Qualification Test Specification Review | 300 | 1 | 36 | 36 | 8 |  | 6 |  |  | 6 | 11 | 8 | 4 | 4
35 | 246 |  | Sys Qualification Test Execution | 300 | 1 | 72 | 72 | 15 |  | 11 |  |  | 11 | 22 | 15 | 8 | 8
Feature | 247 | COM Matrix integration |  | 700 | 0.75 |  |  |  | 15% | 25% |  |  | 30% | 60% | 80% | 100% | 120% |  |  | 929738 | R1.1 |  | 929738 | R1.1
Proc | 248 | [7 empty] | 15% | 10% |  |  | 5% | 30% | 20% | 20% | 20%
Sum | 249 |  |  |  |  | 7728 | 5796 | 0 | 884 | 599 | 0 | 0 | 311 | 1753 | 1174 | 1174 | 1174 | 7069
Sys Eng | 250 | COM Matrix integration\Sys Eng |  |  |  | 1176 | 882 | 0 | 140 | 98 | 0 | 0 | 55 | 270 | 184 | 184 | 184 | 1115
SW Dev | 251 | COM Matrix integration\SW Dev |  |  |  | 3696 | 2772 | 0 | 420 | 283 | 0 | 0 | 145 | 838 | 558 | 558 | 558 | 3360
Testing | 252 | COM Matrix integration\Testing |  |  |  | 2856 | 2142 | 0 | 324 | 218 | 0 | 0 | 111 | 645 | 432 | 432 | 432 | 2594
1 | 253 |  | Customer Req Analysis | 700 | 0.75 | 56 | 42 |  | 7 | 5 |  |  | 3 | 13 | 9 | 9 | 9
2 | 254 |  | Sys Requirements Creation | 700 | 0.75 | 112 | 84 |  | 13 | 9 |  |  | 5 | 26 | 17 | 17 | 17
3 | 255 |  | Sys Requirements Verification Criteria | 700 | 0.75 | 28 | 21 |  | 4 | 3 |  |  | 2 | 7 | 5 | 5 | 5
4 | 256 |  | Sys Requirements Review | 700 | 0.75 | 56 | 42 |  | 7 | 5 |  |  | 3 | 13 | 9 | 9 | 9
5 | 257 |  | Sys Requirements Update after Review | 700 | 0.75 | 28 | 21 |  | 4 | 3 |  |  | 2 | 7 | 5 | 5 | 5
6 | 258 |  | Sys Architecture Creation/Update | 700 | 0.75 | 84 | 63 |  | 10 | 7 |  |  | 4 | 19 | 13 | 13 | 13
7 | 259 |  | Sys Arch Traceability | 700 | 0.75 | 56 | 42 |  | 7 | 5 |  |  | 3 | 13 | 9 | 9 | 9
8 | 260 |  | Sys Architecture Review | 700 | 0.75 | 56 | 42 |  | 7 | 5 |  |  | 3 | 13 | 9 | 9 | 9
9 | 261 |  | Sys Architecture Update after Review | 700 | 0.75 | 28 | 21 |  | 4 | 3 |  |  | 2 | 7 | 5 | 5 | 5
10 | 262 |  | SW Requirements Creation | 700 | 0.75 | 336 | 252 |  | 38 | 26 |  |  | 13 | 76 | 51 | 51 | 51
11 | 263 |  | SW Requirements Verification Criteria | 700 | 0.75 | 84 | 63 |  | 10 | 7 |  |  | 4 | 19 | 13 | 13 | 13
12 | 264 |  | SW Requirements Review | 700 | 0.75 | 168 | 126 |  | 19 | 13 |  |  | 7 | 38 | 26 | 26 | 26
13 | 265 |  | SW Requirements Update after Review | 700 | 0.75 | 84 | 63 |  | 10 | 7 |  |  | 4 | 19 | 13 | 13 | 13
14 | 266 |  | SW Architecture Specification | 700 | 0.75 | 336 | 252 |  | 38 | 26 |  |  | 13 | 76 | 51 | 51 | 51
15 | 267 |  | SW Architecture Specification Review | 700 | 0.75 | 112 | 84 |  | 13 | 9 |  |  | 5 | 26 | 17 | 17 | 17
16 | 268 |  | Design Specification | 700 | 0.75 | 336 | 252 |  | 38 | 26 |  |  | 13 | 76 | 51 | 51 | 51
17 | 269 |  | Design Specification Review | 700 | 0.75 | 112 | 84 |  | 13 | 9 |  |  | 5 | 26 | 17 | 17 | 17
18 | 270 |  | Code Implementation | 700 | 0.75 | 560 | 420 |  | 63 | 42 |  |  | 21 | 126 | 84 | 84 | 84
19 | 271 |  | QAC/Code Metrics Verification | 700 | 0.75 | 112 | 84 |  | 13 | 9 |  |  | 5 | 26 | 17 | 17 | 17
20 | 272 |  | Code Review | 700 | 0.75 | 224 | 168 |  | 26 | 17 |  |  | 9 | 51 | 34 | 34 | 34
21 | 273 |  | Unit Test Specification | 700 | 0.75 | 560 | 420 |  | 63 | 42 |  |  | 21 | 126 | 84 | 84 | 84
22 | 274 |  | Unit Test Specification Review | 700 | 0.75 | 112 | 84 |  | 13 | 9 |  |  | 5 | 26 | 17 | 17 | 17
23 | 275 |  | Unit Test Execution | 700 | 0.75 | 112 | 84 |  | 13 | 9 |  |  | 5 | 26 | 17 | 17 | 17
24 | 276 |  | SW Integration Test Specification | 700 | 0.75 | 560 | 420 |  | 63 | 42 |  |  | 21 | 126 | 84 | 84 | 84
25 | 277 |  | SW Integration Test Specification Review | 700 | 0.75 | 224 | 168 |  | 26 | 17 |  |  | 9 | 51 | 34 | 34 | 34
26 | 278 |  | SW Integration Test Execution | 700 | 0.75 | 336 | 252 |  | 38 | 26 |  |  | 13 | 76 | 51 | 51 | 51
27 | 279 |  | SW Qualification Test Specification | 700 | 0.75 | 560 | 420 |  | 63 | 42 |  |  | 21 | 126 | 84 | 84 | 84
28 | 280 |  | SW Qualification Test Specification Review | 700 | 0.75 | 140 | 105 |  | 16 | 11 |  |  | 6 | 32 | 21 | 21 | 21
29 | 281 |  | SW Qualification Test Execution | 700 | 0.75 | 336 | 252 |  | 38 | 26 |  |  | 13 | 76 | 51 | 51 | 51
30 | 282 |  | Sys Integration Test Specification | 700 | 0.75 | 560 | 420 |  | 63 | 42 |  |  | 21 | 126 | 84 | 84 | 84
31 | 283 |  | Sys Integration Test Specification Review | 700 | 0.75 | 224 | 168 |  | 26 | 17 |  |  | 9 | 51 | 34 | 34 | 34
32 | 284 |  | Sys Integration Test Execution | 700 | 0.75 | 448 | 336 |  | 51 | 34 |  |  | 17 | 101 | 68 | 68 | 68
33 | 285 |  | Sys Qualification Test Specification | 700 | 0.75 | 336 | 252 |  | 38 | 26 |  |  | 13 | 76 | 51 | 51 | 51
34 | 286 |  | Sys Qualification Test Specification Review | 700 | 0.75 | 84 | 63 |  | 10 | 7 |  |  | 4 | 19 | 13 | 13 | 13
35 | 287 |  | Sys Qualification Test Execution | 700 | 0.75 | 168 | 126 |  | 19 | 13 |  |  | 7 | 38 | 26 | 26 | 26
Feature | 288 | CAN Stack |  | 80 | 0.75 |  |  |  | 50% |  | 80% |  | 100% |  |  | 110% | [9 empty] | 1027288 | R1.2
Proc | 289 | [7 empty] | 50% |  | 30% |  | 20% |  |  | 10%
Sum | 290 |  |  |  |  | 883.2 | 662.4 | 0 | 346 | 0 | 214 | 0 | 142 | 0 | 0 | 76 | 0 | 778
Sys Eng | 291 | CAN Stack\Sys Eng |  |  |  | 134.4 | 100.8 | 0 | 58 | 0 | 37 | 0 | 24 | 0 | 0 | 16 | 0 | 135
SW Dev | 292 | CAN Stack\SW Dev |  |  |  | 422.4 | 316.8 | 0 | 162 | 0 | 99 | 0 | 66 | 0 | 0 | 33 | 0 | 360
Testing | 293 | CAN Stack\Testing |  |  |  | 326.4 | 244.8 | 0 | 126 | 0 | 78 | 0 | 52 | 0 | 0 | 27 | 0 | 283
1 | 294 |  | Customer Req Analysis | 80 | 0.75 | 6.4 | 4.8 |  | 3 |  | 2 |  | 1 |  |  | 1
2 | 295 |  | Sys Requirements Creation | 80 | 0.75 | 12.8 | 9.6 |  | 5 |  | 3 |  | 2 |  |  | 1
3 | 296 |  | Sys Requirements Verification Criteria | 80 | 0.75 | 3.2 | 2.4 |  | 2 |  | 1 |  | 1 |  |  | 1
4 | 297 |  | Sys Requirements Review | 80 | 0.75 | 6.4 | 4.8 |  | 3 |  | 2 |  | 1 |  |  | 1
5 | 298 |  | Sys Requirements Update after Review | 80 | 0.75 | 3.2 | 2.4 |  | 2 |  | 1 |  | 1 |  |  | 1
6 | 299 |  | Sys Architecture Creation/Update | 80 | 0.75 | 9.6 | 7.2 |  | 4 |  | 3 |  | 2 |  |  | 1
7 | 300 |  | Sys Arch Traceability | 80 | 0.75 | 6.4 | 4.8 |  | 3 |  | 2 |  | 1 |  |  | 1
8 | 301 |  | Sys Architecture Review | 80 | 0.75 | 6.4 | 4.8 |  | 3 |  | 2 |  | 1 |  |  | 1
9 | 302 |  | Sys Architecture Update after Review | 80 | 0.75 | 3.2 | 2.4 |  | 2 |  | 1 |  | 1 |  |  | 1
10 | 303 |  | SW Requirements Creation | 80 | 0.75 | 38.4 | 28.8 |  | 15 |  | 9 |  | 6 |  |  | 3
11 | 304 |  | SW Requirements Verification Criteria | 80 | 0.75 | 9.6 | 7.2 |  | 4 |  | 3 |  | 2 |  |  | 1
12 | 305 |  | SW Requirements Review | 80 | 0.75 | 19.2 | 14.4 |  | 8 |  | 5 |  | 3 |  |  | 2
13 | 306 |  | SW Requirements Update after Review | 80 | 0.75 | 9.6 | 7.2 |  | 4 |  | 3 |  | 2 |  |  | 1
14 | 307 |  | SW Architecture Specification | 80 | 0.75 | 38.4 | 28.8 |  | 15 |  | 9 |  | 6 |  |  | 3
15 | 308 |  | SW Architecture Specification Review | 80 | 0.75 | 12.8 | 9.6 |  | 5 |  | 3 |  | 2 |  |  | 1
16 | 309 |  | Design Specification | 80 | 0.75 | 38.4 | 28.8 |  | 15 |  | 9 |  | 6 |  |  | 3
17 | 310 |  | Design Specification Review | 80 | 0.75 | 12.8 | 9.6 |  | 5 |  | 3 |  | 2 |  |  | 1
18 | 311 |  | Code Implementation | 80 | 0.75 | 64 | 48 |  | 24 |  | 15 |  | 10 |  |  | 5
19 | 312 |  | QAC/Code Metrics Verification | 80 | 0.75 | 12.8 | 9.6 |  | 5 |  | 3 |  | 2 |  |  | 1
20 | 313 |  | Code Review | 80 | 0.75 | 25.6 | 19.2 |  | 10 |  | 6 |  | 4 |  |  | 2
21 | 314 |  | Unit Test Specification | 80 | 0.75 | 64 | 48 |  | 24 |  | 15 |  | 10 |  |  | 5
22 | 315 |  | Unit Test Specification Review | 80 | 0.75 | 12.8 | 9.6 |  | 5 |  | 3 |  | 2 |  |  | 1
23 | 316 |  | Unit Test Execution | 80 | 0.75 | 12.8 | 9.6 |  | 5 |  | 3 |  | 2 |  |  | 1
24 | 317 |  | SW Integration Test Specification | 80 | 0.75 | 64 | 48 |  | 24 |  | 15 |  | 10 |  |  | 5
25 | 318 |  | SW Integration Test Specification Review | 80 | 0.75 | 25.6 | 19.2 |  | 10 |  | 6 |  | 4 |  |  | 2
26 | 319 |  | SW Integration Test Execution | 80 | 0.75 | 38.4 | 28.8 |  | 15 |  | 9 |  | 6 |  |  | 3
27 | 320 |  | SW Qualification Test Specification | 80 | 0.75 | 64 | 48 |  | 24 |  | 15 |  | 10 |  |  | 5
28 | 321 |  | SW Qualification Test Specification Review | 80 | 0.75 | 16 | 12 |  | 6 |  | 4 |  | 3 |  |  | 2
29 | 322 |  | SW Qualification Test Execution | 80 | 0.75 | 38.4 | 28.8 |  | 15 |  | 9 |  | 6 |  |  | 3
30 | 323 |  | Sys Integration Test Specification | 80 | 0.75 | 64 | 48 |  | 24 |  | 15 |  | 10 |  |  | 5
31 | 324 |  | Sys Integration Test Specification Review | 80 | 0.75 | 25.6 | 19.2 |  | 10 |  | 6 |  | 4 |  |  | 2
32 | 325 |  | Sys Integration Test Execution | 80 | 0.75 | 51.2 | 38.4 |  | 20 |  | 12 |  | 8 |  |  | 4
33 | 326 |  | Sys Qualification Test Specification | 80 | 0.75 | 38.4 | 28.8 |  | 15 |  | 9 |  | 6 |  |  | 3
34 | 327 |  | Sys Qualification Test Specification Review | 80 | 0.75 | 9.6 | 7.2 |  | 4 |  | 3 |  | 2 |  |  | 1
35 | 328 |  | Sys Qualification Test Execution | 80 | 0.75 | 19.2 | 14.4 |  | 8 |  | 5 |  | 3 |  |  | 2
Feature | 329 | Network Management |  | 250 | 0.75 |  |  |  | 30% | 100% |  |  |  |  | 110% |  | 120%
Proc | 330 | [7 empty] | 30% | 70% |  |  |  |  | 10% |  | 10%
Sum | 331 |  |  |  |  | 2760 | 2070 | 0 | 628 | 1456 | 0 | 0 | 0 | 0 | 223 | 0 | 214 | 2521
Sys Eng | 332 | Network Management\Sys Eng |  |  |  | 420 | 315 | 0 | 100 | 226 | 0 | 0 | 0 | 0 | 38 | 0 | 37 | 401
SW Dev | 333 | Network Management\SW Dev |  |  |  | 1320 | 990 | 0 | 297 | 693 | 0 | 0 | 0 | 0 | 104 | 0 | 99 | 1193
Testing | 334 | Network Management\Testing |  |  |  | 1020 | 765 | 0 | 231 | 537 | 0 | 0 | 0 | 0 | 81 | 0 | 78 | 927
1 | 335 |  | Customer Req Analysis | 250 | 0.75 | 20 | 15 |  | 5 | 11 |  |  |  |  | 2 |  | 2
2 | 336 |  | Sys Requirements Creation | 250 | 0.75 | 40 | 30 |  | 9 | 21 |  |  |  |  | 3 |  | 3
3 | 337 |  | Sys Requirements Verification Criteria | 250 | 0.75 | 10 | 7.5 |  | 3 | 6 |  |  |  |  | 1 |  | 1
4 | 338 |  | Sys Requirements Review | 250 | 0.75 | 20 | 15 |  | 5 | 11 |  |  |  |  | 2 |  | 2
5 | 339 |  | Sys Requirements Update after Review | 250 | 0.75 | 10 | 7.5 |  | 3 | 6 |  |  |  |  | 1 |  | 1
6 | 340 |  | Sys Architecture Creation/Update | 250 | 0.75 | 30 | 22.5 |  | 7 | 16 |  |  |  |  | 3 |  | 3
7 | 341 |  | Sys Arch Traceability | 250 | 0.75 | 20 | 15 |  | 5 | 11 |  |  |  |  | 2 |  | 2
8 | 342 |  | Sys Architecture Review | 250 | 0.75 | 20 | 15 |  | 5 | 11 |  |  |  |  | 2 |  | 2
9 | 343 |  | Sys Architecture Update after Review | 250 | 0.75 | 10 | 7.5 |  | 3 | 6 |  |  |  |  | 1 |  | 1
10 | 344 |  | SW Requirements Creation | 250 | 0.75 | 120 | 90 |  | 27 | 63 |  |  |  |  | 10 |  | 9
11 | 345 |  | SW Requirements Verification Criteria | 250 | 0.75 | 30 | 22.5 |  | 7 | 16 |  |  |  |  | 3 |  | 3
12 | 346 |  | SW Requirements Review | 250 | 0.75 | 60 | 45 |  | 14 | 32 |  |  |  |  | 5 |  | 5
13 | 347 |  | SW Requirements Update after Review | 250 | 0.75 | 30 | 22.5 |  | 7 | 16 |  |  |  |  | 3 |  | 3
14 | 348 |  | SW Architecture Specification | 250 | 0.75 | 120 | 90 |  | 27 | 63 |  |  |  |  | 10 |  | 9
15 | 349 |  | SW Architecture Specification Review | 250 | 0.75 | 40 | 30 |  | 9 | 21 |  |  |  |  | 3 |  | 3
16 | 350 |  | Design Specification | 250 | 0.75 | 120 | 90 |  | 27 | 63 |  |  |  |  | 10 |  | 9
17 | 351 |  | Design Specification Review | 250 | 0.75 | 40 | 30 |  | 9 | 21 |  |  |  |  | 3 |  | 3
18 | 352 |  | Code Implementation | 250 | 0.75 | 200 | 150 |  | 45 | 105 |  |  |  |  | 15 |  | 15
19 | 353 |  | QAC/Code Metrics Verification | 250 | 0.75 | 40 | 30 |  | 9 | 21 |  |  |  |  | 3 |  | 3
20 | 354 |  | Code Review | 250 | 0.75 | 80 | 60 |  | 18 | 42 |  |  |  |  | 7 |  | 6
21 | 355 |  | Unit Test Specification | 250 | 0.75 | 200 | 150 |  | 45 | 105 |  |  |  |  | 15 |  | 15
22 | 356 |  | Unit Test Specification Review | 250 | 0.75 | 40 | 30 |  | 9 | 21 |  |  |  |  | 3 |  | 3
23 | 357 |  | Unit Test Execution | 250 | 0.75 | 40 | 30 |  | 9 | 21 |  |  |  |  | 3 |  | 3
24 | 358 |  | SW Integration Test Specification | 250 | 0.75 | 200 | 150 |  | 45 | 105 |  |  |  |  | 15 |  | 15
25 | 359 |  | SW Integration Test Specification Review | 250 | 0.75 | 80 | 60 |  | 18 | 42 |  |  |  |  | 7 |  | 6
26 | 360 |  | SW Integration Test Execution | 250 | 0.75 | 120 | 90 |  | 27 | 63 |  |  |  |  | 10 |  | 9
27 | 361 |  | SW Qualification Test Specification | 250 | 0.75 | 200 | 150 |  | 45 | 105 |  |  |  |  | 15 |  | 15
28 | 362 |  | SW Qualification Test Specification Review | 250 | 0.75 | 50 | 37.5 |  | 12 | 27 |  |  |  |  | 4 |  | 4
29 | 363 |  | SW Qualification Test Execution | 250 | 0.75 | 120 | 90 |  | 27 | 63 |  |  |  |  | 10 |  | 9
30 | 364 |  | Sys Integration Test Specification | 250 | 0.75 | 200 | 150 |  | 45 | 105 |  |  |  |  | 15 |  | 15
31 | 365 |  | Sys Integration Test Specification Review | 250 | 0.75 | 80 | 60 |  | 18 | 42 |  |  |  |  | 7 |  | 6
32 | 366 |  | Sys Integration Test Execution | 250 | 0.75 | 160 | 120 |  | 36 | 84 |  |  |  |  | 12 |  | 12
33 | 367 |  | Sys Qualification Test Specification | 250 | 0.75 | 120 | 90 |  | 27 | 63 |  |  |  |  | 10 |  | 9
34 | 368 |  | Sys Qualification Test Specification Review | 250 | 0.75 | 30 | 22.5 |  | 7 | 16 |  |  |  |  | 3 |  | 3
35 | 369 |  | Sys Qualification Test Execution | 250 | 0.75 | 60 | 45 |  | 14 | 32 |  |  |  |  | 5 |  | 5
Feature | 370 | AUTOSAR & OS |  | 250 | 1 |  |  |  | 50% | 60% |  | 70% | 100% |  |  | 110% |  |  |  | 1026901;40%;930396;20%;930814;20%;986100;20% | R1.1 |  | 930396;40%;930814;30%;986100;30% | R1.1
Proc | 371 | [7 empty] | 50% | 10% |  | 10% | 30% |  |  | 10%
Sum | 372 |  |  |  |  | 2760 | 2760 | 0 | 1380 | 276 | 0 | 276 | 828 | 0 | 0 | 281 | 0 | 3041
Sys Eng | 373 | AUTOSAR & OS\Sys Eng |  |  |  | 420 | 420 | 0 | 210 | 42 | 0 | 42 | 126 | 0 | 0 | 43 | 0 | 463
SW Dev | 374 | AUTOSAR & OS\SW Dev |  |  |  | 1320 | 1320 | 0 | 660 | 132 | 0 | 132 | 396 | 0 | 0 | 134 | 0 | 1454
Testing | 375 | AUTOSAR & OS\Testing |  |  |  | 1020 | 1020 | 0 | 510 | 102 | 0 | 102 | 306 | 0 | 0 | 104 | 0 | 1124
1 | 376 |  | Customer Req Analysis | 250 | 1 | 20 | 20 |  | 10 | 2 |  | 2 | 6 |  |  | 2
2 | 377 |  | Sys Requirements Creation | 250 | 1 | 40 | 40 |  | 20 | 4 |  | 4 | 12 |  |  | 4
3 | 378 |  | Sys Requirements Verification Criteria | 250 | 1 | 10 | 10 |  | 5 | 1 |  | 1 | 3 |  |  | 1
4 | 379 |  | Sys Requirements Review | 250 | 1 | 20 | 20 |  | 10 | 2 |  | 2 | 6 |  |  | 2
5 | 380 |  | Sys Requirements Update after Review | 250 | 1 | 10 | 10 |  | 5 | 1 |  | 1 | 3 |  |  | 1
6 | 381 |  | Sys Architecture Creation/Update | 250 | 1 | 30 | 30 |  | 15 | 3 |  | 3 | 9 |  |  | 3
7 | 382 |  | Sys Arch Traceability | 250 | 1 | 20 | 20 |  | 10 | 2 |  | 2 | 6 |  |  | 2
8 | 383 |  | Sys Architecture Review | 250 | 1 | 20 | 20 |  | 10 | 2 |  | 2 | 6 |  |  | 2
9 | 384 |  | Sys Architecture Update after Review | 250 | 1 | 10 | 10 |  | 5 | 1 |  | 1 | 3 |  |  | 1
10 | 385 |  | SW Requirements Creation | 250 | 1 | 120 | 120 |  | 60 | 12 |  | 12 | 36 |  |  | 12
11 | 386 |  | SW Requirements Verification Criteria | 250 | 1 | 30 | 30 |  | 15 | 3 |  | 3 | 9 |  |  | 3
12 | 387 |  | SW Requirements Review | 250 | 1 | 60 | 60 |  | 30 | 6 |  | 6 | 18 |  |  | 7
13 | 388 |  | SW Requirements Update after Review | 250 | 1 | 30 | 30 |  | 15 | 3 |  | 3 | 9 |  |  | 3
14 | 389 |  | SW Architecture Specification | 250 | 1 | 120 | 120 |  | 60 | 12 |  | 12 | 36 |  |  | 12
15 | 390 |  | SW Architecture Specification Review | 250 | 1 | 40 | 40 |  | 20 | 4 |  | 4 | 12 |  |  | 4
16 | 391 |  | Design Specification | 250 | 1 | 120 | 120 |  | 60 | 12 |  | 12 | 36 |  |  | 12
17 | 392 |  | Design Specification Review | 250 | 1 | 40 | 40 |  | 20 | 4 |  | 4 | 12 |  |  | 4
18 | 393 |  | Code Implementation | 250 | 1 | 200 | 200 |  | 100 | 20 |  | 20 | 60 |  |  | 20
19 | 394 |  | QAC/Code Metrics Verification | 250 | 1 | 40 | 40 |  | 20 | 4 |  | 4 | 12 |  |  | 4
20 | 395 |  | Code Review | 250 | 1 | 80 | 80 |  | 40 | 8 |  | 8 | 24 |  |  | 9
21 | 396 |  | Unit Test Specification | 250 | 1 | 200 | 200 |  | 100 | 20 |  | 20 | 60 |  |  | 20
22 | 397 |  | Unit Test Specification Review | 250 | 1 | 40 | 40 |  | 20 | 4 |  | 4 | 12 |  |  | 4
23 | 398 |  | Unit Test Execution | 250 | 1 | 40 | 40 |  | 20 | 4 |  | 4 | 12 |  |  | 4
24 | 399 |  | SW Integration Test Specification | 250 | 1 | 200 | 200 |  | 100 | 20 |  | 20 | 60 |  |  | 20
25 | 400 |  | SW Integration Test Specification Review | 250 | 1 | 80 | 80 |  | 40 | 8 |  | 8 | 24 |  |  | 9
26 | 401 |  | SW Integration Test Execution | 250 | 1 | 120 | 120 |  | 60 | 12 |  | 12 | 36 |  |  | 12
27 | 402 |  | SW Qualification Test Specification | 250 | 1 | 200 | 200 |  | 100 | 20 |  | 20 | 60 |  |  | 20
28 | 403 |  | SW Qualification Test Specification Review | 250 | 1 | 50 | 50 |  | 25 | 5 |  | 5 | 15 |  |  | 5
29 | 404 |  | SW Qualification Test Execution | 250 | 1 | 120 | 120 |  | 60 | 12 |  | 12 | 36 |  |  | 12
30 | 405 |  | Sys Integration Test Specification | 250 | 1 | 200 | 200 |  | 100 | 20 |  | 20 | 60 |  |  | 20
31 | 406 |  | Sys Integration Test Specification Review | 250 | 1 | 80 | 80 |  | 40 | 8 |  | 8 | 24 |  |  | 9
32 | 407 |  | Sys Integration Test Execution | 250 | 1 | 160 | 160 |  | 80 | 16 |  | 16 | 48 |  |  | 16
33 | 408 |  | Sys Qualification Test Specification | 250 | 1 | 120 | 120 |  | 60 | 12 |  | 12 | 36 |  |  | 12
34 | 409 |  | Sys Qualification Test Specification Review | 250 | 1 | 30 | 30 |  | 15 | 3 |  | 3 | 9 |  |  | 3
35 | 410 |  | Sys Qualification Test Execution | 250 | 1 | 60 | 60 |  | 30 | 6 |  | 6 | 18 |  |  | 7
Feature | 411 | Self-Tests |  | 300 | 1.25 |  |  |  | 30% | 50% | 55% | 60% |  | 80% | 100% | 110% | 120% |  |  | 929740 | R1.1 |  | 929740 | R1.1 |  | 1027308;50%;1027307;50% | R1.2
Proc | 412 | [7 empty] | 30% | 20% | 5% | 5% |  | 20% | 20% | 10% | 10%
Sum | 413 |  |  |  |  | 3312 | 4140 | 0 | 1246 | 828 | 223 | 214 | 0 | 828 | 828 | 426 | 418 | 5011
Sys Eng | 414 | Self-Tests\Sys Eng |  |  |  | 504 | 630 | 0 | 192 | 126 | 38 | 37 | 0 | 126 | 126 | 68 | 66 | 779
SW Dev | 415 | Self-Tests\SW Dev |  |  |  | 1584 | 1980 | 0 | 594 | 396 | 104 | 99 | 0 | 396 | 396 | 203 | 198 | 2386
Testing | 416 | Self-Tests\Testing |  |  |  | 1224 | 1530 | 0 | 460 | 306 | 81 | 78 | 0 | 306 | 306 | 155 | 154 | 1846
1 | 417 |  | Customer Req Analysis | 300 | 1.25 | 24 | 30 |  | 9 | 6 | 2 | 2 |  | 6 | 6 | 3 | 3
2 | 418 |  | Sys Requirements Creation | 300 | 1.25 | 48 | 60 |  | 18 | 12 | 3 | 3 |  | 12 | 12 | 7 | 6
3 | 419 |  | Sys Requirements Verification Criteria | 300 | 1.25 | 12 | 15 |  | 5 | 3 | 1 | 1 |  | 3 | 3 | 2 | 2
4 | 420 |  | Sys Requirements Review | 300 | 1.25 | 24 | 30 |  | 9 | 6 | 2 | 2 |  | 6 | 6 | 3 | 3
5 | 421 |  | Sys Requirements Update after Review | 300 | 1.25 | 12 | 15 |  | 5 | 3 | 1 | 1 |  | 3 | 3 | 2 | 2
6 | 422 |  | Sys Architecture Creation/Update | 300 | 1.25 | 36 | 45 |  | 14 | 9 | 3 | 3 |  | 9 | 9 | 5 | 5
7 | 423 |  | Sys Arch Traceability | 300 | 1.25 | 24 | 30 |  | 9 | 6 | 2 | 2 |  | 6 | 6 | 3 | 3
8 | 424 |  | Sys Architecture Review | 300 | 1.25 | 24 | 30 |  | 9 | 6 | 2 | 2 |  | 6 | 6 | 3 | 3
9 | 425 |  | Sys Architecture Update after Review | 300 | 1.25 | 12 | 15 |  | 5 | 3 | 1 | 1 |  | 3 | 3 | 2 | 2
10 | 426 |  | SW Requirements Creation | 300 | 1.25 | 144 | 180 |  | 54 | 36 | 10 | 9 |  | 36 | 36 | 18 | 18
11 | 427 |  | SW Requirements Verification Criteria | 300 | 1.25 | 36 | 45 |  | 14 | 9 | 3 | 3 |  | 9 | 9 | 5 | 5
12 | 428 |  | SW Requirements Review | 300 | 1.25 | 72 | 90 |  | 27 | 18 | 5 | 5 |  | 18 | 18 | 10 | 9
13 | 429 |  | SW Requirements Update after Review | 300 | 1.25 | 36 | 45 |  | 14 | 9 | 3 | 3 |  | 9 | 9 | 5 | 5
14 | 430 |  | SW Architecture Specification | 300 | 1.25 | 144 | 180 |  | 54 | 36 | 10 | 9 |  | 36 | 36 | 18 | 18
15 | 431 |  | SW Architecture Specification Review | 300 | 1.25 | 48 | 60 |  | 18 | 12 | 3 | 3 |  | 12 | 12 | 7 | 6
16 | 432 |  | Design Specification | 300 | 1.25 | 144 | 180 |  | 54 | 36 | 10 | 9 |  | 36 | 36 | 18 | 18
17 | 433 |  | Design Specification Review | 300 | 1.25 | 48 | 60 |  | 18 | 12 | 3 | 3 |  | 12 | 12 | 7 | 6
18 | 434 |  | Code Implementation | 300 | 1.25 | 240 | 300 |  | 90 | 60 | 15 | 15 |  | 60 | 60 | 30 | 30
19 | 435 |  | QAC/Code Metrics Verification | 300 | 1.25 | 48 | 60 |  | 18 | 12 | 3 | 3 |  | 12 | 12 | 7 | 6
20 | 436 |  | Code Review | 300 | 1.25 | 96 | 120 |  | 36 | 24 | 7 | 6 |  | 24 | 24 | 12 | 12
21 | 437 |  | Unit Test Specification | 300 | 1.25 | 240 | 300 |  | 90 | 60 | 15 | 15 |  | 60 | 60 | 30 | 30
22 | 438 |  | Unit Test Specification Review | 300 | 1.25 | 48 | 60 |  | 18 | 12 | 3 | 3 |  | 12 | 12 | 7 | 6
23 | 439 |  | Unit Test Execution | 300 | 1.25 | 48 | 60 |  | 18 | 12 | 3 | 3 |  | 12 | 12 | 7 | 6
24 | 440 |  | SW Integration Test Specification | 300 | 1.25 | 240 | 300 |  | 90 | 60 | 15 | 15 |  | 60 | 60 | 30 | 30
25 | 441 |  | SW Integration Test Specification Review | 300 | 1.25 | 96 | 120 |  | 36 | 24 | 7 | 6 |  | 24 | 24 | 12 | 12
26 | 442 |  | SW Integration Test Execution | 300 | 1.25 | 144 | 180 |  | 54 | 36 | 10 | 9 |  | 36 | 36 | 18 | 18
27 | 443 |  | SW Qualification Test Specification | 300 | 1.25 | 240 | 300 |  | 90 | 60 | 15 | 15 |  | 60 | 60 | 30 | 30
28 | 444 |  | SW Qualification Test Specification Review | 300 | 1.25 | 60 | 75 |  | 23 | 15 | 4 | 4 |  | 15 | 15 | 8 | 8
29 | 445 |  | SW Qualification Test Execution | 300 | 1.25 | 144 | 180 |  | 54 | 36 | 10 | 9 |  | 36 | 36 | 18 | 18
30 | 446 |  | Sys Integration Test Specification | 300 | 1.25 | 240 | 300 |  | 90 | 60 | 15 | 15 |  | 60 | 60 | 30 | 30
31 | 447 |  | Sys Integration Test Specification Review | 300 | 1.25 | 96 | 120 |  | 36 | 24 | 7 | 6 |  | 24 | 24 | 12 | 12
32 | 448 |  | Sys Integration Test Execution | 300 | 1.25 | 192 | 240 |  | 72 | 48 | 12 | 12 |  | 48 | 48 | 24 | 24
33 | 449 |  | Sys Qualification Test Specification | 300 | 1.25 | 144 | 180 |  | 54 | 36 | 10 | 9 |  | 36 | 36 | 18 | 18
34 | 450 |  | Sys Qualification Test Specification Review | 300 | 1.25 | 36 | 45 |  | 14 | 9 | 3 | 3 |  | 9 | 9 | 5 | 5
35 | 451 |  | Sys Qualification Test Execution | 300 | 1.25 | 72 | 90 |  | 27 | 18 | 5 | 5 |  | 18 | 18 | 10 | 9
Feature | 452 | ECU Fault Detection |  | 250 | 1 |  |  |  | 30% | 50% | 55% | 60% |  | 80% | 100% | 110% | 120% |  |  | 930397 | R1.1 |  | 930397 | R1.1 |  | 1027309 | R1.2
Proc | 453 | [7 empty] | 30% | 20% | 5% | 5% |  | 20% | 20% | 10% | 10%
Sum | 454 |  |  |  |  | 2760 | 2760 | 0 | 828 | 552 | 149 | 142 | 0 | 552 | 552 | 281 | 276 | 3332
Sys Eng | 455 | ECU Fault Detection\Sys Eng |  |  |  | 420 | 420 | 0 | 126 | 84 | 25 | 24 | 0 | 84 | 84 | 43 | 42 | 512
SW Dev | 456 | ECU Fault Detection\SW Dev |  |  |  | 1320 | 1320 | 0 | 396 | 264 | 69 | 66 | 0 | 264 | 264 | 134 | 132 | 1589
Testing | 457 | ECU Fault Detection\Testing |  |  |  | 1020 | 1020 | 0 | 306 | 204 | 55 | 52 | 0 | 204 | 204 | 104 | 102 | 1231
1 | 458 |  | Customer Req Analysis | 250 | 1 | 20 | 20 |  | 6 | 4 | 1 | 1 |  | 4 | 4 | 2 | 2
2 | 459 |  | Sys Requirements Creation | 250 | 1 | 40 | 40 |  | 12 | 8 | 2 | 2 |  | 8 | 8 | 4 | 4
3 | 460 |  | Sys Requirements Verification Criteria | 250 | 1 | 10 | 10 |  | 3 | 2 | 1 | 1 |  | 2 | 2 | 1 | 1
4 | 461 |  | Sys Requirements Review | 250 | 1 | 20 | 20 |  | 6 | 4 | 1 | 1 |  | 4 | 4 | 2 | 2
5 | 462 |  | Sys Requirements Update after Review | 250 | 1 | 10 | 10 |  | 3 | 2 | 1 | 1 |  | 2 | 2 | 1 | 1
6 | 463 |  | Sys Architecture Creation/Update | 250 | 1 | 30 | 30 |  | 9 | 6 | 2 | 2 |  | 6 | 6 | 3 | 3
7 | 464 |  | Sys Arch Traceability | 250 | 1 | 20 | 20 |  | 6 | 4 | 1 | 1 |  | 4 | 4 | 2 | 2
8 | 465 |  | Sys Architecture Review | 250 | 1 | 20 | 20 |  | 6 | 4 | 1 | 1 |  | 4 | 4 | 2 | 2
9 | 466 |  | Sys Architecture Update after Review | 250 | 1 | 10 | 10 |  | 3 | 2 | 1 | 1 |  | 2 | 2 | 1 | 1
10 | 467 |  | SW Requirements Creation | 250 | 1 | 120 | 120 |  | 36 | 24 | 7 | 6 |  | 24 | 24 | 12 | 12
11 | 468 |  | SW Requirements Verification Criteria | 250 | 1 | 30 | 30 |  | 9 | 6 | 2 | 2 |  | 6 | 6 | 3 | 3
12 | 469 |  | SW Requirements Review | 250 | 1 | 60 | 60 |  | 18 | 12 | 3 | 3 |  | 12 | 12 | 7 | 6
13 | 470 |  | SW Requirements Update after Review | 250 | 1 | 30 | 30 |  | 9 | 6 | 2 | 2 |  | 6 | 6 | 3 | 3
14 | 471 |  | SW Architecture Specification | 250 | 1 | 120 | 120 |  | 36 | 24 | 7 | 6 |  | 24 | 24 | 12 | 12
15 | 472 |  | SW Architecture Specification Review | 250 | 1 | 40 | 40 |  | 12 | 8 | 2 | 2 |  | 8 | 8 | 4 | 4
16 | 473 |  | Design Specification | 250 | 1 | 120 | 120 |  | 36 | 24 | 7 | 6 |  | 24 | 24 | 12 | 12
17 | 474 |  | Design Specification Review | 250 | 1 | 40 | 40 |  | 12 | 8 | 2 | 2 |  | 8 | 8 | 4 | 4
18 | 475 |  | Code Implementation | 250 | 1 | 200 | 200 |  | 60 | 40 | 10 | 10 |  | 40 | 40 | 20 | 20
19 | 476 |  | QAC/Code Metrics Verification | 250 | 1 | 40 | 40 |  | 12 | 8 | 2 | 2 |  | 8 | 8 | 4 | 4
20 | 477 |  | Code Review | 250 | 1 | 80 | 80 |  | 24 | 16 | 4 | 4 |  | 16 | 16 | 9 | 8
21 | 478 |  | Unit Test Specification | 250 | 1 | 200 | 200 |  | 60 | 40 | 10 | 10 |  | 40 | 40 | 20 | 20
22 | 479 |  | Unit Test Specification Review | 250 | 1 | 40 | 40 |  | 12 | 8 | 2 | 2 |  | 8 | 8 | 4 | 4
23 | 480 |  | Unit Test Execution | 250 | 1 | 40 | 40 |  | 12 | 8 | 2 | 2 |  | 8 | 8 | 4 | 4
24 | 481 |  | SW Integration Test Specification | 250 | 1 | 200 | 200 |  | 60 | 40 | 10 | 10 |  | 40 | 40 | 20 | 20
25 | 482 |  | SW Integration Test Specification Review | 250 | 1 | 80 | 80 |  | 24 | 16 | 4 | 4 |  | 16 | 16 | 9 | 8
26 | 483 |  | SW Integration Test Execution | 250 | 1 | 120 | 120 |  | 36 | 24 | 7 | 6 |  | 24 | 24 | 12 | 12
27 | 484 |  | SW Qualification Test Specification | 250 | 1 | 200 | 200 |  | 60 | 40 | 10 | 10 |  | 40 | 40 | 20 | 20
28 | 485 |  | SW Qualification Test Specification Review | 250 | 1 | 50 | 50 |  | 15 | 10 | 3 | 3 |  | 10 | 10 | 5 | 5
29 | 486 |  | SW Qualification Test Execution | 250 | 1 | 120 | 120 |  | 36 | 24 | 7 | 6 |  | 24 | 24 | 12 | 12
30 | 487 |  | Sys Integration Test Specification | 250 | 1 | 200 | 200 |  | 60 | 40 | 10 | 10 |  | 40 | 40 | 20 | 20
31 | 488 |  | Sys Integration Test Specification Review | 250 | 1 | 80 | 80 |  | 24 | 16 | 4 | 4 |  | 16 | 16 | 9 | 8
32 | 489 |  | Sys Integration Test Execution | 250 | 1 | 160 | 160 |  | 48 | 32 | 9 | 8 |  | 32 | 32 | 16 | 16
33 | 490 |  | Sys Qualification Test Specification | 250 | 1 | 120 | 120 |  | 36 | 24 | 7 | 6 |  | 24 | 24 | 12 | 12
34 | 491 |  | Sys Qualification Test Specification Review | 250 | 1 | 30 | 30 |  | 9 | 6 | 2 | 2 |  | 6 | 6 | 3 | 3
35 | 492 |  | Sys Qualification Test Execution | 250 | 1 | 60 | 60 |  | 18 | 12 | 3 | 3 |  | 12 | 12 | 7 | 6
Feature | 493 | ECU-External Specific Diag |  | 400 | 1 | [6 empty] | 30% | 40% |  | 60% | 100% | 120%
Proc | 494 | [10 empty] | 30% | 10% |  | 20% | 40% | 20%
Sum | 495 |  |  |  |  | 4416 | 4416 | 0 | 0 | 0 | 0 | 1339 | 457 | 0 | 898 | 1780 | 898 | 5372
Sys Eng | 496 | ECU-External Specific Diag\Sys Eng |  |  |  | 672 | 672 | 0 | 0 | 0 | 0 | 207 | 74 | 0 | 142 | 275 | 142 | 840
SW Dev | 497 | ECU-External Specific Diag\SW Dev |  |  |  | 2112 | 2112 | 0 | 0 | 0 | 0 | 640 | 217 | 0 | 426 | 849 | 426 | 2558
Testing | 498 | ECU-External Specific Diag\Testing |  |  |  | 1632 | 1632 | 0 | 0 | 0 | 0 | 492 | 166 | 0 | 330 | 656 | 330 | 1974
1 | 499 |  | Customer Req Analysis | 400 | 1 | 32 | 32 |  |  |  |  | 10 | 4 |  | 7 | 13 | 7
2 | 500 |  | Sys Requirements Creation | 400 | 1 | 64 | 64 |  |  |  |  | 20 | 7 |  | 13 | 26 | 13
3 | 501 |  | Sys Requirements Verification Criteria | 400 | 1 | 16 | 16 |  |  |  |  | 5 | 2 |  | 4 | 7 | 4
4 | 502 |  | Sys Requirements Review | 400 | 1 | 32 | 32 |  |  |  |  | 10 | 4 |  | 7 | 13 | 7
5 | 503 |  | Sys Requirements Update after Review | 400 | 1 | 16 | 16 |  |  |  |  | 5 | 2 |  | 4 | 7 | 4
6 | 504 |  | Sys Architecture Creation/Update | 400 | 1 | 48 | 48 |  |  |  |  | 15 | 5 |  | 10 | 20 | 10
7 | 505 |  | Sys Arch Traceability | 400 | 1 | 32 | 32 |  |  |  |  | 10 | 4 |  | 7 | 13 | 7
8 | 506 |  | Sys Architecture Review | 400 | 1 | 32 | 32 |  |  |  |  | 10 | 4 |  | 7 | 13 | 7
9 | 507 |  | Sys Architecture Update after Review | 400 | 1 | 16 | 16 |  |  |  |  | 5 | 2 |  | 4 | 7 | 4
10 | 508 |  | SW Requirements Creation | 400 | 1 | 192 | 192 |  |  |  |  | 58 | 20 |  | 39 | 77 | 39
11 | 509 |  | SW Requirements Verification Criteria | 400 | 1 | 48 | 48 |  |  |  |  | 15 | 5 |  | 10 | 20 | 10
12 | 510 |  | SW Requirements Review | 400 | 1 | 96 | 96 |  |  |  |  | 29 | 10 |  | 20 | 39 | 20
13 | 511 |  | SW Requirements Update after Review | 400 | 1 | 48 | 48 |  |  |  |  | 15 | 5 |  | 10 | 20 | 10
14 | 512 |  | SW Architecture Specification | 400 | 1 | 192 | 192 |  |  |  |  | 58 | 20 |  | 39 | 77 | 39
15 | 513 |  | SW Architecture Specification Review | 400 | 1 | 64 | 64 |  |  |  |  | 20 | 7 |  | 13 | 26 | 13
16 | 514 |  | Design Specification | 400 | 1 | 192 | 192 |  |  |  |  | 58 | 20 |  | 39 | 77 | 39
17 | 515 |  | Design Specification Review | 400 | 1 | 64 | 64 |  |  |  |  | 20 | 7 |  | 13 | 26 | 13
18 | 516 |  | Code Implementation | 400 | 1 | 320 | 320 |  |  |  |  | 96 | 32 |  | 64 | 128 | 64
19 | 517 |  | QAC/Code Metrics Verification | 400 | 1 | 64 | 64 |  |  |  |  | 20 | 7 |  | 13 | 26 | 13
20 | 518 |  | Code Review | 400 | 1 | 128 | 128 |  |  |  |  | 39 | 13 |  | 26 | 52 | 26
21 | 519 |  | Unit Test Specification | 400 | 1 | 320 | 320 |  |  |  |  | 96 | 32 |  | 64 | 128 | 64
22 | 520 |  | Unit Test Specification Review | 400 | 1 | 64 | 64 |  |  |  |  | 20 | 7 |  | 13 | 26 | 13
23 | 521 |  | Unit Test Execution | 400 | 1 | 64 | 64 |  |  |  |  | 20 | 7 |  | 13 | 26 | 13
24 | 522 |  | SW Integration Test Specification | 400 | 1 | 320 | 320 |  |  |  |  | 96 | 32 |  | 64 | 128 | 64
25 | 523 |  | SW Integration Test Specification Review | 400 | 1 | 128 | 128 |  |  |  |  | 39 | 13 |  | 26 | 52 | 26
26 | 524 |  | SW Integration Test Execution | 400 | 1 | 192 | 192 |  |  |  |  | 58 | 20 |  | 39 | 77 | 39
27 | 525 |  | SW Qualification Test Specification | 400 | 1 | 320 | 320 |  |  |  |  | 96 | 32 |  | 64 | 128 | 64
28 | 526 |  | SW Qualification Test Specification Review | 400 | 1 | 80 | 80 |  |  |  |  | 24 | 8 |  | 16 | 32 | 16
29 | 527 |  | SW Qualification Test Execution | 400 | 1 | 192 | 192 |  |  |  |  | 58 | 20 |  | 39 | 77 | 39
30 | 528 |  | Sys Integration Test Specification | 400 | 1 | 320 | 320 |  |  |  |  | 96 | 32 |  | 64 | 128 | 64
31 | 529 |  | Sys Integration Test Specification Review | 400 | 1 | 128 | 128 |  |  |  |  | 39 | 13 |  | 26 | 52 | 26
32 | 530 |  | Sys Integration Test Execution | 400 | 1 | 256 | 256 |  |  |  |  | 77 | 26 |  | 52 | 103 | 52
33 | 531 |  | Sys Qualification Test Specification | 400 | 1 | 192 | 192 |  |  |  |  | 58 | 20 |  | 39 | 77 | 39
34 | 532 |  | Sys Qualification Test Specification Review | 400 | 1 | 48 | 48 |  |  |  |  | 15 | 5 |  | 10 | 20 | 10
35 | 533 |  | Sys Qualification Test Execution | 400 | 1 | 96 | 96 |  |  |  |  | 29 | 10 |  | 20 | 39 | 20
Feature | 534 | ECU-Internal Specific Diag |  | 300 | 0.8 | [6 empty] | 30% |  |  | 80% | 100% | 120%
Proc | 535 | [10 empty] | 30% |  |  | 50% | 20% | 20%
Sum | 536 |  |  |  |  | 3312 | 2649.6 | 0 | 0 | 0 | 0 | 811 | 0 | 0 | 1339 | 546 | 546 | 3242
Sys Eng | 537 | ECU-Internal Specific Diag\Sys Eng |  |  |  | 504 | 403.2 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 207 | 84 | 84 | 500
SW Dev | 538 | ECU-Internal Specific Diag\SW Dev |  |  |  | 1584 | 1267.2 | 0 | 0 | 0 | 0 | 387 | 0 | 0 | 640 | 261 | 261 | 1549
Testing | 539 | ECU-Internal Specific Diag\Testing |  |  |  | 1224 | 979.2 | 0 | 0 | 0 | 0 | 299 | 0 | 0 | 492 | 201 | 201 | 1193
1 | 540 |  | Customer Req Analysis | 300 | 0.8 | 24 | 19.2 |  |  |  |  | 6 |  |  | 10 | 4 | 4
2 | 541 |  | Sys Requirements Creation | 300 | 0.8 | 48 | 38.4 |  |  |  |  | 12 |  |  | 20 | 8 | 8
3 | 542 |  | Sys Requirements Verification Criteria | 300 | 0.8 | 12 | 9.6 |  |  |  |  | 3 |  |  | 5 | 2 | 2
4 | 543 |  | Sys Requirements Review | 300 | 0.8 | 24 | 19.2 |  |  |  |  | 6 |  |  | 10 | 4 | 4
5 | 544 |  | Sys Requirements Update after Review | 300 | 0.8 | 12 | 9.6 |  |  |  |  | 3 |  |  | 5 | 2 | 2
6 | 545 |  | Sys Architecture Creation/Update | 300 | 0.8 | 36 | 28.8 |  |  |  |  | 9 |  |  | 15 | 6 | 6
7 | 546 |  | Sys Arch Traceability | 300 | 0.8 | 24 | 19.2 |  |  |  |  | 6 |  |  | 10 | 4 | 4
8 | 547 |  | Sys Architecture Review | 300 | 0.8 | 24 | 19.2 |  |  |  |  | 6 |  |  | 10 | 4 | 4
9 | 548 |  | Sys Architecture Update after Review | 300 | 0.8 | 12 | 9.6 |  |  |  |  | 3 |  |  | 5 | 2 | 2
10 | 549 |  | SW Requirements Creation | 300 | 0.8 | 144 | 115.2 |  |  |  |  | 35 |  |  | 58 | 24 | 24
11 | 550 |  | SW Requirements Verification Criteria | 300 | 0.8 | 36 | 28.8 |  |  |  |  | 9 |  |  | 15 | 6 | 6
12 | 551 |  | SW Requirements Review | 300 | 0.8 | 72 | 57.6 |  |  |  |  | 18 |  |  | 29 | 12 | 12
13 | 552 |  | SW Requirements Update after Review | 300 | 0.8 | 36 | 28.8 |  |  |  |  | 9 |  |  | 15 | 6 | 6
14 | 553 |  | SW Architecture Specification | 300 | 0.8 | 144 | 115.2 |  |  |  |  | 35 |  |  | 58 | 24 | 24
15 | 554 |  | SW Architecture Specification Review | 300 | 0.8 | 48 | 38.4 |  |  |  |  | 12 |  |  | 20 | 8 | 8
16 | 555 |  | Design Specification | 300 | 0.8 | 144 | 115.2 |  |  |  |  | 35 |  |  | 58 | 24 | 24
17 | 556 |  | Design Specification Review | 300 | 0.8 | 48 | 38.4 |  |  |  |  | 12 |  |  | 20 | 8 | 8
18 | 557 |  | Code Implementation | 300 | 0.8 | 240 | 192 |  |  |  |  | 58 |  |  | 96 | 39 | 39
19 | 558 |  | QAC/Code Metrics Verification | 300 | 0.8 | 48 | 38.4 |  |  |  |  | 12 |  |  | 20 | 8 | 8
20 | 559 |  | Code Review | 300 | 0.8 | 96 | 76.8 |  |  |  |  | 24 |  |  | 39 | 16 | 16
21 | 560 |  | Unit Test Specification | 300 | 0.8 | 240 | 192 |  |  |  |  | 58 |  |  | 96 | 39 | 39
22 | 561 |  | Unit Test Specification Review | 300 | 0.8 | 48 | 38.4 |  |  |  |  | 12 |  |  | 20 | 8 | 8
23 | 562 |  | Unit Test Execution | 300 | 0.8 | 48 | 38.4 |  |  |  |  | 12 |  |  | 20 | 8 | 8
24 | 563 |  | SW Integration Test Specification | 300 | 0.8 | 240 | 192 |  |  |  |  | 58 |  |  | 96 | 39 | 39
25 | 564 |  | SW Integration Test Specification Review | 300 | 0.8 | 96 | 76.8 |  |  |  |  | 24 |  |  | 39 | 16 | 16
26 | 565 |  | SW Integration Test Execution | 300 | 0.8 | 144 | 115.2 |  |  |  |  | 35 |  |  | 58 | 24 | 24
27 | 566 |  | SW Qualification Test Specification | 300 | 0.8 | 240 | 192 |  |  |  |  | 58 |  |  | 96 | 39 | 39
28 | 567 |  | SW Qualification Test Specification Review | 300 | 0.8 | 60 | 48 |  |  |  |  | 15 |  |  | 24 | 10 | 10
29 | 568 |  | SW Qualification Test Execution | 300 | 0.8 | 144 | 115.2 |  |  |  |  | 35 |  |  | 58 | 24 | 24
30 | 569 |  | Sys Integration Test Specification | 300 | 0.8 | 240 | 192 |  |  |  |  | 58 |  |  | 96 | 39 | 39
31 | 570 |  | Sys Integration Test Specification Review | 300 | 0.8 | 96 | 76.8 |  |  |  |  | 24 |  |  | 39 | 16 | 16
32 | 571 |  | Sys Integration Test Execution | 300 | 0.8 | 192 | 153.6 |  |  |  |  | 47 |  |  | 77 | 31 | 31
33 | 572 |  | Sys Qualification Test Specification | 300 | 0.8 | 144 | 115.2 |  |  |  |  | 35 |  |  | 58 | 24 | 24
34 | 573 |  | Sys Qualification Test Specification Review | 300 | 0.8 | 36 | 28.8 |  |  |  |  | 9 |  |  | 15 | 6 | 6
35 | 574 |  | Sys Qualification Test Execution | 300 | 0.8 | 72 | 57.6 |  |  |  |  | 18 |  |  | 29 | 12 | 12
Feature | 575 | Error mapping strategy |  | 80 | 0.75 |  |  |  |  | 70% | 90% |  | 100% |  |  | 110% |  |  |  | 930398 | R1.1 |  | 930398 | R1.1 |  | 1027310 | R1.2
Proc | 576 | [8 empty] | 70% | 20% |  | 10% |  |  | 10%
Sum | 577 |  |  |  |  | 883.2 | 662.4 | 0 | 0 | 484 | 142 | 0 | 76 | 0 | 0 | 76 | 0 | 778
Sys Eng | 578 | Error mapping strategy\Sys Eng |  |  |  | 134.4 | 100.8 | 0 | 0 | 79 | 24 | 0 | 16 | 0 | 0 | 16 | 0 | 135
SW Dev | 579 | Error mapping strategy\SW Dev |  |  |  | 422.4 | 316.8 | 0 | 0 | 228 | 66 | 0 | 33 | 0 | 0 | 33 | 0 | 360
Testing | 580 | Error mapping strategy\Testing |  |  |  | 326.4 | 244.8 | 0 | 0 | 177 | 52 | 0 | 27 | 0 | 0 | 27 | 0 | 283
1 | 581 |  | Customer Req Analysis | 80 | 0.75 | 6.4 | 4.8 |  |  | 4 | 1 |  | 1 |  |  | 1
2 | 582 |  | Sys Requirements Creation | 80 | 0.75 | 12.8 | 9.6 |  |  | 7 | 2 |  | 1 |  |  | 1
3 | 583 |  | Sys Requirements Verification Criteria | 80 | 0.75 | 3.2 | 2.4 |  |  | 2 | 1 |  | 1 |  |  | 1
4 | 584 |  | Sys Requirements Review | 80 | 0.75 | 6.4 | 4.8 |  |  | 4 | 1 |  | 1 |  |  | 1
5 | 585 |  | Sys Requirements Update after Review | 80 | 0.75 | 3.2 | 2.4 |  |  | 2 | 1 |  | 1 |  |  | 1
6 | 586 |  | Sys Architecture Creation/Update | 80 | 0.75 | 9.6 | 7.2 |  |  | 6 | 2 |  | 1 |  |  | 1
7 | 587 |  | Sys Arch Traceability | 80 | 0.75 | 6.4 | 4.8 |  |  | 4 | 1 |  | 1 |  |  | 1
8 | 588 |  | Sys Architecture Review | 80 | 0.75 | 6.4 | 4.8 |  |  | 4 | 1 |  | 1 |  |  | 1
9 | 589 |  | Sys Architecture Update after Review | 80 | 0.75 | 3.2 | 2.4 |  |  | 2 | 1 |  | 1 |  |  | 1
10 | 590 |  | SW Requirements Creation | 80 | 0.75 | 38.4 | 28.8 |  |  | 21 | 6 |  | 3 |  |  | 3
11 | 591 |  | SW Requirements Verification Criteria | 80 | 0.75 | 9.6 | 7.2 |  |  | 6 | 2 |  | 1 |  |  | 1
12 | 592 |  | SW Requirements Review | 80 | 0.75 | 19.2 | 14.4 |  |  | 11 | 3 |  | 2 |  |  | 2
13 | 593 |  | SW Requirements Update after Review | 80 | 0.75 | 9.6 | 7.2 |  |  | 6 | 2 |  | 1 |  |  | 1
14 | 594 |  | SW Architecture Specification | 80 | 0.75 | 38.4 | 28.8 |  |  | 21 | 6 |  | 3 |  |  | 3
15 | 595 |  | SW Architecture Specification Review | 80 | 0.75 | 12.8 | 9.6 |  |  | 7 | 2 |  | 1 |  |  | 1
16 | 596 |  | Design Specification | 80 | 0.75 | 38.4 | 28.8 |  |  | 21 | 6 |  | 3 |  |  | 3
17 | 597 |  | Design Specification Review | 80 | 0.75 | 12.8 | 9.6 |  |  | 7 | 2 |  | 1 |  |  | 1
18 | 598 |  | Code Implementation | 80 | 0.75 | 64 | 48 |  |  | 34 | 10 |  | 5 |  |  | 5
19 | 599 |  | QAC/Code Metrics Verification | 80 | 0.75 | 12.8 | 9.6 |  |  | 7 | 2 |  | 1 |  |  | 1
20 | 600 |  | Code Review | 80 | 0.75 | 25.6 | 19.2 |  |  | 14 | 4 |  | 2 |  |  | 2
21 | 601 |  | Unit Test Specification | 80 | 0.75 | 64 | 48 |  |  | 34 | 10 |  | 5 |  |  | 5
22 | 602 |  | Unit Test Specification Review | 80 | 0.75 | 12.8 | 9.6 |  |  | 7 | 2 |  | 1 |  |  | 1
23 | 603 |  | Unit Test Execution | 80 | 0.75 | 12.8 | 9.6 |  |  | 7 | 2 |  | 1 |  |  | 1
24 | 604 |  | SW Integration Test Specification | 80 | 0.75 | 64 | 48 |  |  | 34 | 10 |  | 5 |  |  | 5
25 | 605 |  | SW Integration Test Specification Review | 80 | 0.75 | 25.6 | 19.2 |  |  | 14 | 4 |  | 2 |  |  | 2
26 | 606 |  | SW Integration Test Execution | 80 | 0.75 | 38.4 | 28.8 |  |  | 21 | 6 |  | 3 |  |  | 3
27 | 607 |  | SW Qualification Test Specification | 80 | 0.75 | 64 | 48 |  |  | 34 | 10 |  | 5 |  |  | 5
28 | 608 |  | SW Qualification Test Specification Review | 80 | 0.75 | 16 | 12 |  |  | 9 | 3 |  | 2 |  |  | 2
29 | 609 |  | SW Qualification Test Execution | 80 | 0.75 | 38.4 | 28.8 |  |  | 21 | 6 |  | 3 |  |  | 3
30 | 610 |  | Sys Integration Test Specification | 80 | 0.75 | 64 | 48 |  |  | 34 | 10 |  | 5 |  |  | 5
31 | 611 |  | Sys Integration Test Specification Review | 80 | 0.75 | 25.6 | 19.2 |  |  | 14 | 4 |  | 2 |  |  | 2
32 | 612 |  | Sys Integration Test Execution | 80 | 0.75 | 51.2 | 38.4 |  |  | 27 | 8 |  | 4 |  |  | 4
33 | 613 |  | Sys Qualification Test Specification | 80 | 0.75 | 38.4 | 28.8 |  |  | 21 | 6 |  | 3 |  |  | 3
34 | 614 |  | Sys Qualification Test Specification Review | 80 | 0.75 | 9.6 | 7.2 |  |  | 6 | 2 |  | 1 |  |  | 1
35 | 615 |  | Sys Qualification Test Execution | 80 | 0.75 | 19.2 | 14.4 |  |  | 11 | 3 |  | 2 |  |  | 2
Feature | 616 | Temperature Sensor |  | 30 | 1 |  |  |  | 20% |  |  | 50% |  | 80% | 100% | 110%
Proc | 617 | [7 empty] | 20% |  |  | 30% |  | 30% | 20% | 10%
Sum | 618 |  |  |  |  | 331.2 | 331.2 | 0 | 76 | 0 | 0 | 120 | 0 | 120 | 76 | 52 | 0 | 444
Sys Eng | 619 | Temperature Sensor\Sys Eng |  |  |  | 50.4 | 50.4 | 0 | 16 | 0 | 0 | 23 | 0 | 23 | 16 | 14 | 0 | 92
SW Dev | 620 | Temperature Sensor\SW Dev |  |  |  | 158.4 | 158.4 | 0 | 33 | 0 | 0 | 55 | 0 | 55 | 33 | 22 | 0 | 198
Testing | 621 | Temperature Sensor\Testing |  |  |  | 122.4 | 122.4 | 0 | 27 | 0 | 0 | 42 | 0 | 42 | 27 | 16 | 0 | 154
1 | 622 |  | Customer Req Analysis | 30 | 1 | 2.4 | 2.4 |  | 1 |  |  | 1 |  | 1 | 1 | 1
2 | 623 |  | Sys Requirements Creation | 30 | 1 | 4.8 | 4.8 |  | 1 |  |  | 2 |  | 2 | 1 | 1
3 | 624 |  | Sys Requirements Verification Criteria | 30 | 1 | 1.2 | 1.2 |  | 1 |  |  | 1 |  | 1 | 1 | 1
4 | 625 |  | Sys Requirements Review | 30 | 1 | 2.4 | 2.4 |  | 1 |  |  | 1 |  | 1 | 1 | 1
5 | 626 |  | Sys Requirements Update after Review | 30 | 1 | 1.2 | 1.2 |  | 1 |  |  | 1 |  | 1 | 1 | 1
6 | 627 |  | Sys Architecture Creation/Update | 30 | 1 | 3.6 | 3.6 |  | 1 |  |  | 2 |  | 2 | 1 | 1
7 | 628 |  | Sys Arch Traceability | 30 | 1 | 2.4 | 2.4 |  | 1 |  |  | 1 |  | 1 | 1 | 1
8 | 629 |  | Sys Architecture Review | 30 | 1 | 2.4 | 2.4 |  | 1 |  |  | 1 |  | 1 | 1 | 1
9 | 630 |  | Sys Architecture Update after Review | 30 | 1 | 1.2 | 1.2 |  | 1 |  |  | 1 |  | 1 | 1 | 1
10 | 631 |  | SW Requirements Creation | 30 | 1 | 14.4 | 14.4 |  | 3 |  |  | 5 |  | 5 | 3 | 2
11 | 632 |  | SW Requirements Verification Criteria | 30 | 1 | 3.6 | 3.6 |  | 1 |  |  | 2 |  | 2 | 1 | 1
12 | 633 |  | SW Requirements Review | 30 | 1 | 7.2 | 7.2 |  | 2 |  |  | 3 |  | 3 | 2 | 1
13 | 634 |  | SW Requirements Update after Review | 30 | 1 | 3.6 | 3.6 |  | 1 |  |  | 2 |  | 2 | 1 | 1
14 | 635 |  | SW Architecture Specification | 30 | 1 | 14.4 | 14.4 |  | 3 |  |  | 5 |  | 5 | 3 | 2
15 | 636 |  | SW Architecture Specification Review | 30 | 1 | 4.8 | 4.8 |  | 1 |  |  | 2 |  | 2 | 1 | 1
16 | 637 |  | Design Specification | 30 | 1 | 14.4 | 14.4 |  | 3 |  |  | 5 |  | 5 | 3 | 2
17 | 638 |  | Design Specification Review | 30 | 1 | 4.8 | 4.8 |  | 1 |  |  | 2 |  | 2 | 1 | 1
18 | 639 |  | Code Implementation | 30 | 1 | 24 | 24 |  | 5 |  |  | 8 |  | 8 | 5 | 3
19 | 640 |  | QAC/Code Metrics Verification | 30 | 1 | 4.8 | 4.8 |  | 1 |  |  | 2 |  | 2 | 1 | 1
20 | 641 |  | Code Review | 30 | 1 | 9.6 | 9.6 |  | 2 |  |  | 3 |  | 3 | 2 | 1
21 | 642 |  | Unit Test Specification | 30 | 1 | 24 | 24 |  | 5 |  |  | 8 |  | 8 | 5 | 3
22 | 643 |  | Unit Test Specification Review | 30 | 1 | 4.8 | 4.8 |  | 1 |  |  | 2 |  | 2 | 1 | 1
23 | 644 |  | Unit Test Execution | 30 | 1 | 4.8 | 4.8 |  | 1 |  |  | 2 |  | 2 | 1 | 1
24 | 645 |  | SW Integration Test Specification | 30 | 1 | 24 | 24 |  | 5 |  |  | 8 |  | 8 | 5 | 3
25 | 646 |  | SW Integration Test Specification Review | 30 | 1 | 9.6 | 9.6 |  | 2 |  |  | 3 |  | 3 | 2 | 1
26 | 647 |  | SW Integration Test Execution | 30 | 1 | 14.4 | 14.4 |  | 3 |  |  | 5 |  | 5 | 3 | 2
27 | 648 |  | SW Qualification Test Specification | 30 | 1 | 24 | 24 |  | 5 |  |  | 8 |  | 8 | 5 | 3
28 | 649 |  | SW Qualification Test Specification Review | 30 | 1 | 6 | 6 |  | 2 |  |  | 2 |  | 2 | 2 | 1
29 | 650 |  | SW Qualification Test Execution | 30 | 1 | 14.4 | 14.4 |  | 3 |  |  | 5 |  | 5 | 3 | 2
30 | 651 |  | Sys Integration Test Specification | 30 | 1 | 24 | 24 |  | 5 |  |  | 8 |  | 8 | 5 | 3
31 | 652 |  | Sys Integration Test Specification Review | 30 | 1 | 9.6 | 9.6 |  | 2 |  |  | 3 |  | 3 | 2 | 1
32 | 653 |  | Sys Integration Test Execution | 30 | 1 | 19.2 | 19.2 |  | 4 |  |  | 6 |  | 6 | 4 | 2
33 | 654 |  | Sys Qualification Test Specification | 30 | 1 | 14.4 | 14.4 |  | 3 |  |  | 5 |  | 5 | 3 | 2
34 | 655 |  | Sys Qualification Test Specification Review | 30 | 1 | 3.6 | 3.6 |  | 1 |  |  | 2 |  | 2 | 1 | 1
35 | 656 |  | Sys Qualification Test Execution | 30 | 1 | 7.2 | 7.2 |  | 2 |  |  | 3 |  | 3 | 2 | 1
Feature | 657 | Temperature adaptation |  | 30 | 1.25 |  |  |  | 20% |  |  | 50% |  | 80% | 100% | 110% | 120%
Proc | 658 | [7 empty] | 20% |  |  | 30% |  | 30% | 20% | 10% | 10%
Sum | 659 |  |  |  |  | 331.2 | 414 | 0 | 97 | 0 | 0 | 137 | 0 | 137 | 97 | 56 | 56 | 580
Sys Eng | 660 | Temperature adaptation\Sys Eng |  |  |  | 50.4 | 63 | 0 | 18 | 0 | 0 | 24 | 0 | 24 | 18 | 14 | 14 | 112
SW Dev | 661 | Temperature adaptation\SW Dev |  |  |  | 158.4 | 198 | 0 | 46 | 0 | 0 | 63 | 0 | 63 | 46 | 24 | 24 | 266
Testing | 662 | Temperature adaptation\Testing |  |  |  | 122.4 | 153 | 0 | 33 | 0 | 0 | 50 | 0 | 50 | 33 | 18 | 18 | 202
1 | 663 |  | Customer Req Analysis | 30 | 1.25 | 2.4 | 3 |  | 1 |  |  | 1 |  | 1 | 1 | 1 | 1
2 | 664 |  | Sys Requirements Creation | 30 | 1.25 | 4.8 | 6 |  | 2 |  |  | 2 |  | 2 | 2 | 1 | 1
3 | 665 |  | Sys Requirements Verification Criteria | 30 | 1.25 | 1.2 | 1.5 |  | 1 |  |  | 1 |  | 1 | 1 | 1 | 1
4 | 666 |  | Sys Requirements Review | 30 | 1.25 | 2.4 | 3 |  | 1 |  |  | 1 |  | 1 | 1 | 1 | 1
5 | 667 |  | Sys Requirements Update after Review | 30 | 1.25 | 1.2 | 1.5 |  | 1 |  |  | 1 |  | 1 | 1 | 1 | 1
6 | 668 |  | Sys Architecture Creation/Update | 30 | 1.25 | 3.6 | 4.5 |  | 1 |  |  | 2 |  | 2 | 1 | 1 | 1
7 | 669 |  | Sys Arch Traceability | 30 | 1.25 | 2.4 | 3 |  | 1 |  |  | 1 |  | 1 | 1 | 1 | 1
8 | 670 |  | Sys Architecture Review | 30 | 1.25 | 2.4 | 3 |  | 1 |  |  | 1 |  | 1 | 1 | 1 | 1
9 | 671 |  | Sys Architecture Update after Review | 30 | 1.25 | 1.2 | 1.5 |  | 1 |  |  | 1 |  | 1 | 1 | 1 | 1
10 | 672 |  | SW Requirements Creation | 30 | 1.25 | 14.4 | 18 |  | 4 |  |  | 6 |  | 6 | 4 | 2 | 2
11 | 673 |  | SW Requirements Verification Criteria | 30 | 1.25 | 3.6 | 4.5 |  | 1 |  |  | 2 |  | 2 | 1 | 1 | 1
12 | 674 |  | SW Requirements Review | 30 | 1.25 | 7.2 | 9 |  | 2 |  |  | 3 |  | 3 | 2 | 1 | 1
13 | 675 |  | SW Requirements Update after Review | 30 | 1.25 | 3.6 | 4.5 |  | 1 |  |  | 2 |  | 2 | 1 | 1 | 1
14 | 676 |  | SW Architecture Specification | 30 | 1.25 | 14.4 | 18 |  | 4 |  |  | 6 |  | 6 | 4 | 2 | 2
15 | 677 |  | SW Architecture Specification Review | 30 | 1.25 | 4.8 | 6 |  | 2 |  |  | 2 |  | 2 | 2 | 1 | 1
16 | 678 |  | Design Specification | 30 | 1.25 | 14.4 | 18 |  | 4 |  |  | 6 |  | 6 | 4 | 2 | 2
17 | 679 |  | Design Specification Review | 30 | 1.25 | 4.8 | 6 |  | 2 |  |  | 2 |  | 2 | 2 | 1 | 1
18 | 680 |  | Code Implementation | 30 | 1.25 | 24 | 30 |  | 6 |  |  | 9 |  | 9 | 6 | 3 | 3
19 | 681 |  | QAC/Code Metrics Verification | 30 | 1.25 | 4.8 | 6 |  | 2 |  |  | 2 |  | 2 | 2 | 1 | 1
20 | 682 |  | Code Review | 30 | 1.25 | 9.6 | 12 |  | 3 |  |  | 4 |  | 4 | 3 | 2 | 2
21 | 683 |  | Unit Test Specification | 30 | 1.25 | 24 | 30 |  | 6 |  |  | 9 |  | 9 | 6 | 3 | 3
22 | 684 |  | Unit Test Specification Review | 30 | 1.25 | 4.8 | 6 |  | 2 |  |  | 2 |  | 2 | 2 | 1 | 1
23 | 685 |  | Unit Test Execution | 30 | 1.25 | 4.8 | 6 |  | 2 |  |  | 2 |  | 2 | 2 | 1 | 1
24 | 686 |  | SW Integration Test Specification | 30 | 1.25 | 24 | 30 |  | 6 |  |  | 9 |  | 9 | 6 | 3 | 3
25 | 687 |  | SW Integration Test Specification Review | 30 | 1.25 | 9.6 | 12 |  | 3 |  |  | 4 |  | 4 | 3 | 2 | 2
26 | 688 |  | SW Integration Test Execution | 30 | 1.25 | 14.4 | 18 |  | 4 |  |  | 6 |  | 6 | 4 | 2 | 2
27 | 689 |  | SW Qualification Test Specification | 30 | 1.25 | 24 | 30 |  | 6 |  |  | 9 |  | 9 | 6 | 3 | 3
28 | 690 |  | SW Qualification Test Specification Review | 30 | 1.25 | 6 | 7.5 |  | 2 |  |  | 3 |  | 3 | 2 | 1 | 1
29 | 691 |  | SW Qualification Test Execution | 30 | 1.25 | 14.4 | 18 |  | 4 |  |  | 6 |  | 6 | 4 | 2 | 2
30 | 692 |  | Sys Integration Test Specification | 30 | 1.25 | 24 | 30 |  | 6 |  |  | 9 |  | 9 | 6 | 3 | 3
31 | 693 |  | Sys Integration Test Specification Review | 30 | 1.25 | 9.6 | 12 |  | 3 |  |  | 4 |  | 4 | 3 | 2 | 2
32 | 694 |  | Sys Integration Test Execution | 30 | 1.25 | 19.2 | 24 |  | 5 |  |  | 8 |  | 8 | 5 | 3 | 3
33 | 695 |  | Sys Qualification Test Specification | 30 | 1.25 | 14.4 | 18 |  | 4 |  |  | 6 |  | 6 | 4 | 2 | 2
34 | 696 |  | Sys Qualification Test Specification Review | 30 | 1.25 | 3.6 | 4.5 |  | 1 |  |  | 2 |  | 2 | 1 | 1 | 1
35 | 697 |  | Sys Qualification Test Execution | 30 | 1.25 | 7.2 | 9 |  | 2 |  |  | 3 |  | 3 | 2 | 1 | 1
Feature | 698 | Ageing compensation |  | 30 | 1.5 | [6 empty] | 50% |  | 80% | 100% | 110% | 120%
Proc | 699 | [10 empty] | 50% |  | 30% | 20% | 10% | 10%
Sum | 700 |  |  |  |  | 331.2 | 496.8 | 0 | 0 | 0 | 0 | 259 | 0 | 169 | 120 | 69 | 69 | 686
Sys Eng | 701 | Ageing compensation\Sys Eng |  |  |  | 50.4 | 75.6 | 0 | 0 | 0 | 0 | 41 | 0 | 31 | 23 | 16 | 16 | 127
SW Dev | 702 | Ageing compensation\SW Dev |  |  |  | 158.4 | 237.6 | 0 | 0 | 0 | 0 | 123 | 0 | 79 | 55 | 30 | 30 | 317
Testing | 703 | Ageing compensation\Testing |  |  |  | 122.4 | 183.6 | 0 | 0 | 0 | 0 | 95 | 0 | 59 | 42 | 23 | 23 | 242
1 | 704 |  | Customer Req Analysis | 30 | 1.5 | 2.4 | 3.6 |  |  |  |  | 2 |  | 2 | 1 | 1 | 1
2 | 705 |  | Sys Requirements Creation | 30 | 1.5 | 4.8 | 7.2 |  |  |  |  | 4 |  | 3 | 2 | 1 | 1
3 | 706 |  | Sys Requirements Verification Criteria | 30 | 1.5 | 1.2 | 1.8 |  |  |  |  | 1 |  | 1 | 1 | 1 | 1
4 | 707 |  | Sys Requirements Review | 30 | 1.5 | 2.4 | 3.6 |  |  |  |  | 2 |  | 2 | 1 | 1 | 1
5 | 708 |  | Sys Requirements Update after Review | 30 | 1.5 | 1.2 | 1.8 |  |  |  |  | 1 |  | 1 | 1 | 1 | 1
6 | 709 |  | Sys Architecture Creation/Update | 30 | 1.5 | 3.6 | 5.4 |  |  |  |  | 3 |  | 2 | 2 | 1 | 1
7 | 710 |  | Sys Arch Traceability | 30 | 1.5 | 2.4 | 3.6 |  |  |  |  | 2 |  | 2 | 1 | 1 | 1
8 | 711 |  | Sys Architecture Review | 30 | 1.5 | 2.4 | 3.6 |  |  |  |  | 2 |  | 2 | 1 | 1 | 1
9 | 712 |  | Sys Architecture Update after Review | 30 | 1.5 | 1.2 | 1.8 |  |  |  |  | 1 |  | 1 | 1 | 1 | 1
10 | 713 |  | SW Requirements Creation | 30 | 1.5 | 14.4 | 21.6 |  |  |  |  | 11 |  | 7 | 5 | 3 | 3
11 | 714 |  | SW Requirements Verification Criteria | 30 | 1.5 | 3.6 | 5.4 |  |  |  |  | 3 |  | 2 | 2 | 1 | 1
12 | 715 |  | SW Requirements Review | 30 | 1.5 | 7.2 | 10.8 |  |  |  |  | 6 |  | 4 | 3 | 2 | 2
13 | 716 |  | SW Requirements Update after Review | 30 | 1.5 | 3.6 | 5.4 |  |  |  |  | 3 |  | 2 | 2 | 1 | 1
14 | 717 |  | SW Architecture Specification | 30 | 1.5 | 14.4 | 21.6 |  |  |  |  | 11 |  | 7 | 5 | 3 | 3
15 | 718 |  | SW Architecture Specification Review | 30 | 1.5 | 4.8 | 7.2 |  |  |  |  | 4 |  | 3 | 2 | 1 | 1
16 | 719 |  | Design Specification | 30 | 1.5 | 14.4 | 21.6 |  |  |  |  | 11 |  | 7 | 5 | 3 | 3
17 | 720 |  | Design Specification Review | 30 | 1.5 | 4.8 | 7.2 |  |  |  |  | 4 |  | 3 | 2 | 1 | 1
18 | 721 |  | Code Implementation | 30 | 1.5 | 24 | 36 |  |  |  |  | 18 |  | 11 | 8 | 4 | 4
19 | 722 |  | QAC/Code Metrics Verification | 30 | 1.5 | 4.8 | 7.2 |  |  |  |  | 4 |  | 3 | 2 | 1 | 1
20 | 723 |  | Code Review | 30 | 1.5 | 9.6 | 14.4 |  |  |  |  | 8 |  | 5 | 3 | 2 | 2
21 | 724 |  | Unit Test Specification | 30 | 1.5 | 24 | 36 |  |  |  |  | 18 |  | 11 | 8 | 4 | 4
22 | 725 |  | Unit Test Specification Review | 30 | 1.5 | 4.8 | 7.2 |  |  |  |  | 4 |  | 3 | 2 | 1 | 1
23 | 726 |  | Unit Test Execution | 30 | 1.5 | 4.8 | 7.2 |  |  |  |  | 4 |  | 3 | 2 | 1 | 1
24 | 727 |  | SW Integration Test Specification | 30 | 1.5 | 24 | 36 |  |  |  |  | 18 |  | 11 | 8 | 4 | 4
25 | 728 |  | SW Integration Test Specification Review | 30 | 1.5 | 9.6 | 14.4 |  |  |  |  | 8 |  | 5 | 3 | 2 | 2
26 | 729 |  | SW Integration Test Execution | 30 | 1.5 | 14.4 | 21.6 |  |  |  |  | 11 |  | 7 | 5 | 3 | 3
27 | 730 |  | SW Qualification Test Specification | 30 | 1.5 | 24 | 36 |  |  |  |  | 18 |  | 11 | 8 | 4 | 4
28 | 731 |  | SW Qualification Test Specification Review | 30 | 1.5 | 6 | 9 |  |  |  |  | 5 |  | 3 | 2 | 1 | 1
29 | 732 |  | SW Qualification Test Execution | 30 | 1.5 | 14.4 | 21.6 |  |  |  |  | 11 |  | 7 | 5 | 3 | 3
30 | 733 |  | Sys Integration Test Specification | 30 | 1.5 | 24 | 36 |  |  |  |  | 18 |  | 11 | 8 | 4 | 4
31 | 734 |  | Sys Integration Test Specification Review | 30 | 1.5 | 9.6 | 14.4 |  |  |  |  | 8 |  | 5 | 3 | 2 | 2
32 | 735 |  | Sys Integration Test Execution | 30 | 1.5 | 19.2 | 28.8 |  |  |  |  | 15 |  | 9 | 6 | 3 | 3
33 | 736 |  | Sys Qualification Test Specification | 30 | 1.5 | 14.4 | 21.6 |  |  |  |  | 11 |  | 7 | 5 | 3 | 3
34 | 737 |  | Sys Qualification Test Specification Review | 30 | 1.5 | 3.6 | 5.4 |  |  |  |  | 3 |  | 2 | 2 | 1 | 1
35 | 738 |  | Sys Qualification Test Execution | 30 | 1.5 | 7.2 | 10.8 |  |  |  |  | 6 |  | 4 | 3 | 2 | 2
Feature | 739 | Nachlauf |  | 20 | 1 |  |  |  | 20% |  |  | 100% |  |  |  | 110% | 120%
Proc | 740 | [7 empty] | 20% |  |  | 80% |  |  |  | 10% | 10%
Sum | 741 |  |  |  |  | 220.8 | 220.8 | 0 | 61 | 0 | 0 | 191 | 0 | 0 | 0 | 41 | 41 | 334
Sys Eng | 742 | Nachlauf\Sys Eng |  |  |  | 33.6 | 33.6 | 0 | 14 | 0 | 0 | 32 | 0 | 0 | 0 | 13 | 13 | 72
SW Dev | 743 | Nachlauf\SW Dev |  |  |  | 105.6 | 105.6 | 0 | 27 | 0 | 0 | 90 | 0 | 0 | 0 | 16 | 16 | 149
Testing | 744 | Nachlauf\Testing |  |  |  | 81.6 | 81.6 | 0 | 20 | 0 | 0 | 69 | 0 | 0 | 0 | 12 | 12 | 113
1 | 745 |  | Customer Req Analysis | 20 | 1 | 1.6 | 1.6 |  | 1 |  |  | 2 |  |  |  | 1 | 1
2 | 746 |  | Sys Requirements Creation | 20 | 1 | 3.2 | 3.2 |  | 1 |  |  | 3 |  |  |  | 1 | 1
3 | 747 |  | Sys Requirements Verification Criteria | 20 | 1 | 0.8 | 0.8 |  | 1 |  |  | 1 |  |  |  | 1 | 1
4 | 748 |  | Sys Requirements Review | 20 | 1 | 1.6 | 1.6 |  | 1 |  |  | 2 |  |  |  | 1 | 1
5 | 749 |  | Sys Requirements Update after Review | 20 | 1 | 0.8 | 0.8 |  | 1 |  |  | 1 |  |  |  | 1 | 1
6 | 750 |  | Sys Architecture Creation/Update | 20 | 1 | 2.4 | 2.4 |  | 1 |  |  | 2 |  |  |  | 1 | 1
7 | 751 |  | Sys Arch Traceability | 20 | 1 | 1.6 | 1.6 |  | 1 |  |  | 2 |  |  |  | 1 | 1
8 | 752 |  | Sys Architecture Review | 20 | 1 | 1.6 | 1.6 |  | 1 |  |  | 2 |  |  |  | 1 | 1
9 | 753 |  | Sys Architecture Update after Review | 20 | 1 | 0.8 | 0.8 |  | 1 |  |  | 1 |  |  |  | 1 | 1
10 | 754 |  | SW Requirements Creation | 20 | 1 | 9.6 | 9.6 |  | 2 |  |  | 8 |  |  |  | 1 | 1
11 | 755 |  | SW Requirements Verification Criteria | 20 | 1 | 2.4 | 2.4 |  | 1 |  |  | 2 |  |  |  | 1 | 1
12 | 756 |  | SW Requirements Review | 20 | 1 | 4.8 | 4.8 |  | 1 |  |  | 4 |  |  |  | 1 | 1
13 | 757 |  | SW Requirements Update after Review | 20 | 1 | 2.4 | 2.4 |  | 1 |  |  | 2 |  |  |  | 1 | 1
14 | 758 |  | SW Architecture Specification | 20 | 1 | 9.6 | 9.6 |  | 2 |  |  | 8 |  |  |  | 1 | 1
15 | 759 |  | SW Architecture Specification Review | 20 | 1 | 3.2 | 3.2 |  | 1 |  |  | 3 |  |  |  | 1 | 1
16 | 760 |  | Design Specification | 20 | 1 | 9.6 | 9.6 |  | 2 |  |  | 8 |  |  |  | 1 | 1
17 | 761 |  | Design Specification Review | 20 | 1 | 3.2 | 3.2 |  | 1 |  |  | 3 |  |  |  | 1 | 1
18 | 762 |  | Code Implementation | 20 | 1 | 16 | 16 |  | 4 |  |  | 13 |  |  |  | 2 | 2
19 | 763 |  | QAC/Code Metrics Verification | 20 | 1 | 3.2 | 3.2 |  | 1 |  |  | 3 |  |  |  | 1 | 1
20 | 764 |  | Code Review | 20 | 1 | 6.4 | 6.4 |  | 2 |  |  | 6 |  |  |  | 1 | 1
21 | 765 |  | Unit Test Specification | 20 | 1 | 16 | 16 |  | 4 |  |  | 13 |  |  |  | 2 | 2
22 | 766 |  | Unit Test Specification Review | 20 | 1 | 3.2 | 3.2 |  | 1 |  |  | 3 |  |  |  | 1 | 1
23 | 767 |  | Unit Test Execution | 20 | 1 | 3.2 | 3.2 |  | 1 |  |  | 3 |  |  |  | 1 | 1
24 | 768 |  | SW Integration Test Specification | 20 | 1 | 16 | 16 |  | 4 |  |  | 13 |  |  |  | 2 | 2
25 | 769 |  | SW Integration Test Specification Review | 20 | 1 | 6.4 | 6.4 |  | 2 |  |  | 6 |  |  |  | 1 | 1
26 | 770 |  | SW Integration Test Execution | 20 | 1 | 9.6 | 9.6 |  | 2 |  |  | 8 |  |  |  | 1 | 1
27 | 771 |  | SW Qualification Test Specification | 20 | 1 | 16 | 16 |  | 4 |  |  | 13 |  |  |  | 2 | 2
28 | 772 |  | SW Qualification Test Specification Review | 20 | 1 | 4 | 4 |  | 1 |  |  | 4 |  |  |  | 1 | 1
29 | 773 |  | SW Qualification Test Execution | 20 | 1 | 9.6 | 9.6 |  | 2 |  |  | 8 |  |  |  | 1 | 1
30 | 774 |  | Sys Integration Test Specification | 20 | 1 | 16 | 16 |  | 4 |  |  | 13 |  |  |  | 2 | 2
31 | 775 |  | Sys Integration Test Specification Review | 20 | 1 | 6.4 | 6.4 |  | 2 |  |  | 6 |  |  |  | 1 | 1
32 | 776 |  | Sys Integration Test Execution | 20 | 1 | 12.8 | 12.8 |  | 3 |  |  | 11 |  |  |  | 2 | 2
33 | 777 |  | Sys Qualification Test Specification | 20 | 1 | 9.6 | 9.6 |  | 2 |  |  | 8 |  |  |  | 1 | 1
34 | 778 |  | Sys Qualification Test Specification Review | 20 | 1 | 2.4 | 2.4 |  | 1 |  |  | 2 |  |  |  | 1 | 1
35 | 779 |  | Sys Qualification Test Execution | 20 | 1 | 4.8 | 4.8 |  | 1 |  |  | 4 |  |  |  | 1 | 1
Feature | 780 | Coding parameters |  | 100 | 1 | [7 empty] | 50% | 100% |  | 110%
Proc | 781 | [11 empty] | 50% | 50% |  | 10%
Sum | 782 |  |  |  |  | 1104 | 1104 | 0 | 0 | 0 | 0 | 0 | 552 | 552 | 0 | 129 | 0 | 1233
Sys Eng | 783 | Coding parameters\Sys Eng |  |  |  | 168 | 168 | 0 | 0 | 0 | 0 | 0 | 84 | 84 | 0 | 23 | 0 | 191
SW Dev | 784 | Coding parameters\SW Dev |  |  |  | 528 | 528 | 0 | 0 | 0 | 0 | 0 | 264 | 264 | 0 | 60 | 0 | 588
Testing | 785 | Coding parameters\Testing |  |  |  | 408 | 408 | 0 | 0 | 0 | 0 | 0 | 204 | 204 | 0 | 46 | 0 | 454
1 | 786 |  | Customer Req Analysis | 100 | 1 | 8 | 8 | [5 empty] | 4 | 4 |  | 1
2 | 787 |  | Sys Requirements Creation | 100 | 1 | 16 | 16 | [5 empty] | 8 | 8 |  | 2
3 | 788 |  | Sys Requirements Verification Criteria | 100 | 1 | 4 | 4 | [5 empty] | 2 | 2 |  | 1
4 | 789 |  | Sys Requirements Review | 100 | 1 | 8 | 8 | [5 empty] | 4 | 4 |  | 1
5 | 790 |  | Sys Requirements Update after Review | 100 | 1 | 4 | 4 | [5 empty] | 2 | 2 |  | 1
6 | 791 |  | Sys Architecture Creation/Update | 100 | 1 | 12 | 12 | [5 empty] | 6 | 6 |  | 2
7 | 792 |  | Sys Arch Traceability | 100 | 1 | 8 | 8 | [5 empty] | 4 | 4 |  | 1
8 | 793 |  | Sys Architecture Review | 100 | 1 | 8 | 8 | [5 empty] | 4 | 4 |  | 1
9 | 794 |  | Sys Architecture Update after Review | 100 | 1 | 4 | 4 | [5 empty] | 2 | 2 |  | 1
10 | 795 |  | SW Requirements Creation | 100 | 1 | 48 | 48 | [5 empty] | 24 | 24 |  | 5
11 | 796 |  | SW Requirements Verification Criteria | 100 | 1 | 12 | 12 | [5 empty] | 6 | 6 |  | 2
12 | 797 |  | SW Requirements Review | 100 | 1 | 24 | 24 | [5 empty] | 12 | 12 |  | 3
13 | 798 |  | SW Requirements Update after Review | 100 | 1 | 12 | 12 | [5 empty] | 6 | 6 |  | 2
14 | 799 |  | SW Architecture Specification | 100 | 1 | 48 | 48 | [5 empty] | 24 | 24 |  | 5
15 | 800 |  | SW Architecture Specification Review | 100 | 1 | 16 | 16 | [5 empty] | 8 | 8 |  | 2
16 | 801 |  | Design Specification | 100 | 1 | 48 | 48 | [5 empty] | 24 | 24 |  | 5
17 | 802 |  | Design Specification Review | 100 | 1 | 16 | 16 | [5 empty] | 8 | 8 |  | 2
18 | 803 |  | Code Implementation | 100 | 1 | 80 | 80 | [5 empty] | 40 | 40 |  | 9
19 | 804 |  | QAC/Code Metrics Verification | 100 | 1 | 16 | 16 | [5 empty] | 8 | 8 |  | 2
20 | 805 |  | Code Review | 100 | 1 | 32 | 32 | [5 empty] | 16 | 16 |  | 4
21 | 806 |  | Unit Test Specification | 100 | 1 | 80 | 80 | [5 empty] | 40 | 40 |  | 9
22 | 807 |  | Unit Test Specification Review | 100 | 1 | 16 | 16 | [5 empty] | 8 | 8 |  | 2
23 | 808 |  | Unit Test Execution | 100 | 1 | 16 | 16 | [5 empty] | 8 | 8 |  | 2
24 | 809 |  | SW Integration Test Specification | 100 | 1 | 80 | 80 | [5 empty] | 40 | 40 |  | 9
25 | 810 |  | SW Integration Test Specification Review | 100 | 1 | 32 | 32 | [5 empty] | 16 | 16 |  | 4
26 | 811 |  | SW Integration Test Execution | 100 | 1 | 48 | 48 | [5 empty] | 24 | 24 |  | 5
27 | 812 |  | SW Qualification Test Specification | 100 | 1 | 80 | 80 | [5 empty] | 40 | 40 |  | 9
28 | 813 |  | SW Qualification Test Specification Review | 100 | 1 | 20 | 20 | [5 empty] | 10 | 10 |  | 2
29 | 814 |  | SW Qualification Test Execution | 100 | 1 | 48 | 48 | [5 empty] | 24 | 24 |  | 5
30 | 815 |  | Sys Integration Test Specification | 100 | 1 | 80 | 80 | [5 empty] | 40 | 40 |  | 9
31 | 816 |  | Sys Integration Test Specification Review | 100 | 1 | 32 | 32 | [5 empty] | 16 | 16 |  | 4
32 | 817 |  | Sys Integration Test Execution | 100 | 1 | 64 | 64 | [5 empty] | 32 | 32 |  | 7
33 | 818 |  | Sys Qualification Test Specification | 100 | 1 | 48 | 48 | [5 empty] | 24 | 24 |  | 5
34 | 819 |  | Sys Qualification Test Specification Review | 100 | 1 | 12 | 12 | [5 empty] | 6 | 6 |  | 2
35 | 820 |  | Sys Qualification Test Execution | 100 | 1 | 24 | 24 | [5 empty] | 12 | 12 |  | 3
Feature | 821 | Calibrateable ECU |  | 70 | 1.25 | [7 empty] | 50% |  | 100% | 110%
Proc | 822 | [11 empty] | 50% |  | 50% | 10%
Sum | 823 |  |  |  |  | 772.8 | 966 | 0 | 0 | 0 | 0 | 0 | 490 | 0 | 490 | 120 | 0 | 1100
Sys Eng | 824 | Calibrateable ECU\Sys Eng |  |  |  | 117.6 | 147 | 0 | 0 | 0 | 0 | 0 | 79 | 0 | 79 | 23 | 0 | 181
SW Dev | 825 | Calibrateable ECU\SW Dev |  |  |  | 369.6 | 462 | 0 | 0 | 0 | 0 | 0 | 231 | 0 | 231 | 55 | 0 | 517
Testing | 826 | Calibrateable ECU\Testing |  |  |  | 285.6 | 357 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 180 | 42 | 0 | 402
1 | 827 |  | Customer Req Analysis | 70 | 1.25 | 5.6 | 7 | [5 empty] | 4 |  | 4 | 1
2 | 828 |  | Sys Requirements Creation | 70 | 1.25 | 11.2 | 14 | [5 empty] | 7 |  | 7 | 2
3 | 829 |  | Sys Requirements Verification Criteria | 70 | 1.25 | 2.8 | 3.5 | [5 empty] | 2 |  | 2 | 1
4 | 830 |  | Sys Requirements Review | 70 | 1.25 | 5.6 | 7 | [5 empty] | 4 |  | 4 | 1
5 | 831 |  | Sys Requirements Update after Review | 70 | 1.25 | 2.8 | 3.5 | [5 empty] | 2 |  | 2 | 1
6 | 832 |  | Sys Architecture Creation/Update | 70 | 1.25 | 8.4 | 10.5 | [5 empty] | 6 |  | 6 | 2
7 | 833 |  | Sys Arch Traceability | 70 | 1.25 | 5.6 | 7 | [5 empty] | 4 |  | 4 | 1
8 | 834 |  | Sys Architecture Review | 70 | 1.25 | 5.6 | 7 | [5 empty] | 4 |  | 4 | 1
9 | 835 |  | Sys Architecture Update after Review | 70 | 1.25 | 2.8 | 3.5 | [5 empty] | 2 |  | 2 | 1
10 | 836 |  | SW Requirements Creation | 70 | 1.25 | 33.6 | 42 | [5 empty] | 21 |  | 21 | 5
11 | 837 |  | SW Requirements Verification Criteria | 70 | 1.25 | 8.4 | 10.5 | [5 empty] | 6 |  | 6 | 2
12 | 838 |  | SW Requirements Review | 70 | 1.25 | 16.8 | 21 | [5 empty] | 11 |  | 11 | 3
13 | 839 |  | SW Requirements Update after Review | 70 | 1.25 | 8.4 | 10.5 | [5 empty] | 6 |  | 6 | 2
14 | 840 |  | SW Architecture Specification | 70 | 1.25 | 33.6 | 42 | [5 empty] | 21 |  | 21 | 5
15 | 841 |  | SW Architecture Specification Review | 70 | 1.25 | 11.2 | 14 | [5 empty] | 7 |  | 7 | 2
16 | 842 |  | Design Specification | 70 | 1.25 | 33.6 | 42 | [5 empty] | 21 |  | 21 | 5
17 | 843 |  | Design Specification Review | 70 | 1.25 | 11.2 | 14 | [5 empty] | 7 |  | 7 | 2
18 | 844 |  | Code Implementation | 70 | 1.25 | 56 | 70 | [5 empty] | 35 |  | 35 | 8
19 | 845 |  | QAC/Code Metrics Verification | 70 | 1.25 | 11.2 | 14 | [5 empty] | 7 |  | 7 | 2
20 | 846 |  | Code Review | 70 | 1.25 | 22.4 | 28 | [5 empty] | 14 |  | 14 | 3
21 | 847 |  | Unit Test Specification | 70 | 1.25 | 56 | 70 | [5 empty] | 35 |  | 35 | 8
22 | 848 |  | Unit Test Specification Review | 70 | 1.25 | 11.2 | 14 | [5 empty] | 7 |  | 7 | 2
23 | 849 |  | Unit Test Execution | 70 | 1.25 | 11.2 | 14 | [5 empty] | 7 |  | 7 | 2
24 | 850 |  | SW Integration Test Specification | 70 | 1.25 | 56 | 70 | [5 empty] | 35 |  | 35 | 8
25 | 851 |  | SW Integration Test Specification Review | 70 | 1.25 | 22.4 | 28 | [5 empty] | 14 |  | 14 | 3
26 | 852 |  | SW Integration Test Execution | 70 | 1.25 | 33.6 | 42 | [5 empty] | 21 |  | 21 | 5
27 | 853 |  | SW Qualification Test Specification | 70 | 1.25 | 56 | 70 | [5 empty] | 35 |  | 35 | 8
28 | 854 |  | SW Qualification Test Specification Review | 70 | 1.25 | 14 | 17.5 | [5 empty] | 9 |  | 9 | 2
29 | 855 |  | SW Qualification Test Execution | 70 | 1.25 | 33.6 | 42 | [5 empty] | 21 |  | 21 | 5
30 | 856 |  | Sys Integration Test Specification | 70 | 1.25 | 56 | 70 | [5 empty] | 35 |  | 35 | 8
31 | 857 |  | Sys Integration Test Specification Review | 70 | 1.25 | 22.4 | 28 | [5 empty] | 14 |  | 14 | 3
32 | 858 |  | Sys Integration Test Execution | 70 | 1.25 | 44.8 | 56 | [5 empty] | 28 |  | 28 | 6
33 | 859 |  | Sys Qualification Test Specification | 70 | 1.25 | 33.6 | 42 | [5 empty] | 21 |  | 21 | 5
34 | 860 |  | Sys Qualification Test Specification Review | 70 | 1.25 | 8.4 | 10.5 | [5 empty] | 6 |  | 6 | 2
35 | 861 |  | Sys Qualification Test Execution | 70 | 1.25 | 16.8 | 21 | [5 empty] | 11 |  | 11 | 3
Feature | 862 | Variant handling |  | 40 | 1.5 | [7 empty] | 50% |  | 100% | 110%
Proc | 863 | [11 empty] | 50% |  | 50% | 10%
Sum | 864 |  |  |  |  | 441.6 | 662.4 | 0 | 0 | 0 | 0 | 0 | 346 | 0 | 346 | 76 | 0 | 768
Sys Eng | 865 | Variant handling \Sys Eng |  |  |  | 67.2 | 100.8 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 58 | 16 | 0 | 132
SW Dev | 866 | Variant handling \SW Dev |  |  |  | 211.2 | 316.8 | 0 | 0 | 0 | 0 | 0 | 162 | 0 | 162 | 33 | 0 | 357
Testing | 867 | Variant handling \Testing |  |  |  | 163.2 | 244.8 | 0 | 0 | 0 | 0 | 0 | 126 | 0 | 126 | 27 | 0 | 279
1 | 868 |  | Customer Req Analysis | 40 | 1.5 | 3.2 | 4.8 | [5 empty] | 3 |  | 3 | 1
2 | 869 |  | Sys Requirements Creation | 40 | 1.5 | 6.4 | 9.6 | [5 empty] | 5 |  | 5 | 1
3 | 870 |  | Sys Requirements Verification Criteria | 40 | 1.5 | 1.6 | 2.4 | [5 empty] | 2 |  | 2 | 1
4 | 871 |  | Sys Requirements Review | 40 | 1.5 | 3.2 | 4.8 | [5 empty] | 3 |  | 3 | 1
5 | 872 |  | Sys Requirements Update after Review | 40 | 1.5 | 1.6 | 2.4 | [5 empty] | 2 |  | 2 | 1
6 | 873 |  | Sys Architecture Creation/Update | 40 | 1.5 | 4.8 | 7.2 | [5 empty] | 4 |  | 4 | 1
7 | 874 |  | Sys Arch Traceability | 40 | 1.5 | 3.2 | 4.8 | [5 empty] | 3 |  | 3 | 1
8 | 875 |  | Sys Architecture Review | 40 | 1.5 | 3.2 | 4.8 | [5 empty] | 3 |  | 3 | 1
9 | 876 |  | Sys Architecture Update after Review | 40 | 1.5 | 1.6 | 2.4 | [5 empty] | 2 |  | 2 | 1
10 | 877 |  | SW Requirements Creation | 40 | 1.5 | 19.2 | 28.8 | [5 empty] | 15 |  | 15 | 3
11 | 878 |  | SW Requirements Verification Criteria | 40 | 1.5 | 4.8 | 7.2 | [5 empty] | 4 |  | 4 | 1
12 | 879 |  | SW Requirements Review | 40 | 1.5 | 9.6 | 14.4 | [5 empty] | 8 |  | 8 | 2
13 | 880 |  | SW Requirements Update after Review | 40 | 1.5 | 4.8 | 7.2 | [5 empty] | 4 |  | 4 | 1
14 | 881 |  | SW Architecture Specification | 40 | 1.5 | 19.2 | 28.8 | [5 empty] | 15 |  | 15 | 3
15 | 882 |  | SW Architecture Specification Review | 40 | 1.5 | 6.4 | 9.6 | [5 empty] | 5 |  | 5 | 1
16 | 883 |  | Design Specification | 40 | 1.5 | 19.2 | 28.8 | [5 empty] | 15 |  | 15 | 3
17 | 884 |  | Design Specification Review | 40 | 1.5 | 6.4 | 9.6 | [5 empty] | 5 |  | 5 | 1
18 | 885 |  | Code Implementation | 40 | 1.5 | 32 | 48 | [5 empty] | 24 |  | 24 | 5
19 | 886 |  | QAC/Code Metrics Verification | 40 | 1.5 | 6.4 | 9.6 | [5 empty] | 5 |  | 5 | 1
20 | 887 |  | Code Review | 40 | 1.5 | 12.8 | 19.2 | [5 empty] | 10 |  | 10 | 2
21 | 888 |  | Unit Test Specification | 40 | 1.5 | 32 | 48 | [5 empty] | 24 |  | 24 | 5
22 | 889 |  | Unit Test Specification Review | 40 | 1.5 | 6.4 | 9.6 | [5 empty] | 5 |  | 5 | 1
23 | 890 |  | Unit Test Execution | 40 | 1.5 | 6.4 | 9.6 | [5 empty] | 5 |  | 5 | 1
24 | 891 |  | SW Integration Test Specification | 40 | 1.5 | 32 | 48 | [5 empty] | 24 |  | 24 | 5
25 | 892 |  | SW Integration Test Specification Review | 40 | 1.5 | 12.8 | 19.2 | [5 empty] | 10 |  | 10 | 2
26 | 893 |  | SW Integration Test Execution | 40 | 1.5 | 19.2 | 28.8 | [5 empty] | 15 |  | 15 | 3
27 | 894 |  | SW Qualification Test Specification | 40 | 1.5 | 32 | 48 | [5 empty] | 24 |  | 24 | 5
28 | 895 |  | SW Qualification Test Specification Review | 40 | 1.5 | 8 | 12 | [5 empty] | 6 |  | 6 | 2
29 | 896 |  | SW Qualification Test Execution | 40 | 1.5 | 19.2 | 28.8 | [5 empty] | 15 |  | 15 | 3
30 | 897 |  | Sys Integration Test Specification | 40 | 1.5 | 32 | 48 | [5 empty] | 24 |  | 24 | 5
31 | 898 |  | Sys Integration Test Specification Review | 40 | 1.5 | 12.8 | 19.2 | [5 empty] | 10 |  | 10 | 2
32 | 899 |  | Sys Integration Test Execution | 40 | 1.5 | 25.6 | 38.4 | [5 empty] | 20 |  | 20 | 4
33 | 900 |  | Sys Qualification Test Specification | 40 | 1.5 | 19.2 | 28.8 | [5 empty] | 15 |  | 15 | 3
34 | 901 |  | Sys Qualification Test Specification Review | 40 | 1.5 | 4.8 | 7.2 | [5 empty] | 4 |  | 4 | 1
35 | 902 |  | Sys Qualification Test Execution | 40 | 1.5 | 9.6 | 14.4 | [5 empty] | 8 |  | 8 | 2
Feature | 903 | UNECE |  | 150 | 1.5 | [6 empty] | 40% | 80% |  | 100% | 110%
Proc | 904 | [10 empty] | 40% | 40% |  | 20% | 10%
Sum | 905 |  |  |  |  | 1656 | 2484 | 0 | 0 | 0 | 0 | 1009 | 1009 | 0 | 511 | 259 | 0 | 2788
Sys Eng | 906 | UNECE\Sys Eng |  |  |  | 252 | 378 | 0 | 0 | 0 | 0 | 158 | 158 | 0 | 81 | 41 | 0 | 438
SW Dev | 907 | UNECE\SW Dev |  |  |  | 792 | 1188 | 0 | 0 | 0 | 0 | 481 | 481 | 0 | 244 | 123 | 0 | 1329
Testing | 908 | UNECE\Testing |  |  |  | 612 | 918 | 0 | 0 | 0 | 0 | 370 | 370 | 0 | 186 | 95 | 0 | 1021
1 | 909 |  | Customer Req Analysis | 150 | 1.5 | 12 | 18 |  |  |  |  | 8 | 8 |  | 4 | 2
2 | 910 |  | Sys Requirements Creation | 150 | 1.5 | 24 | 36 |  |  |  |  | 15 | 15 |  | 8 | 4
3 | 911 |  | Sys Requirements Verification Criteria | 150 | 1.5 | 6 | 9 |  |  |  |  | 4 | 4 |  | 2 | 1
4 | 912 |  | Sys Requirements Review | 150 | 1.5 | 12 | 18 |  |  |  |  | 8 | 8 |  | 4 | 2
5 | 913 |  | Sys Requirements Update after Review | 150 | 1.5 | 6 | 9 |  |  |  |  | 4 | 4 |  | 2 | 1
6 | 914 |  | Sys Architecture Creation/Update | 150 | 1.5 | 18 | 27 |  |  |  |  | 11 | 11 |  | 6 | 3
7 | 915 |  | Sys Arch Traceability | 150 | 1.5 | 12 | 18 |  |  |  |  | 8 | 8 |  | 4 | 2
8 | 916 |  | Sys Architecture Review | 150 | 1.5 | 12 | 18 |  |  |  |  | 8 | 8 |  | 4 | 2
9 | 917 |  | Sys Architecture Update after Review | 150 | 1.5 | 6 | 9 |  |  |  |  | 4 | 4 |  | 2 | 1
10 | 918 |  | SW Requirements Creation | 150 | 1.5 | 72 | 108 |  |  |  |  | 44 | 44 |  | 22 | 11
11 | 919 |  | SW Requirements Verification Criteria | 150 | 1.5 | 18 | 27 |  |  |  |  | 11 | 11 |  | 6 | 3
12 | 920 |  | SW Requirements Review | 150 | 1.5 | 36 | 54 |  |  |  |  | 22 | 22 |  | 11 | 6
13 | 921 |  | SW Requirements Update after Review | 150 | 1.5 | 18 | 27 |  |  |  |  | 11 | 11 |  | 6 | 3
14 | 922 |  | SW Architecture Specification | 150 | 1.5 | 72 | 108 |  |  |  |  | 44 | 44 |  | 22 | 11
15 | 923 |  | SW Architecture Specification Review | 150 | 1.5 | 24 | 36 |  |  |  |  | 15 | 15 |  | 8 | 4
16 | 924 |  | Design Specification | 150 | 1.5 | 72 | 108 |  |  |  |  | 44 | 44 |  | 22 | 11
17 | 925 |  | Design Specification Review | 150 | 1.5 | 24 | 36 |  |  |  |  | 15 | 15 |  | 8 | 4
18 | 926 |  | Code Implementation | 150 | 1.5 | 120 | 180 |  |  |  |  | 72 | 72 |  | 36 | 18
19 | 927 |  | QAC/Code Metrics Verification | 150 | 1.5 | 24 | 36 |  |  |  |  | 15 | 15 |  | 8 | 4
20 | 928 |  | Code Review | 150 | 1.5 | 48 | 72 |  |  |  |  | 29 | 29 |  | 15 | 8
21 | 929 |  | Unit Test Specification | 150 | 1.5 | 120 | 180 |  |  |  |  | 72 | 72 |  | 36 | 18
22 | 930 |  | Unit Test Specification Review | 150 | 1.5 | 24 | 36 |  |  |  |  | 15 | 15 |  | 8 | 4
23 | 931 |  | Unit Test Execution | 150 | 1.5 | 24 | 36 |  |  |  |  | 15 | 15 |  | 8 | 4
24 | 932 |  | SW Integration Test Specification | 150 | 1.5 | 120 | 180 |  |  |  |  | 72 | 72 |  | 36 | 18
25 | 933 |  | SW Integration Test Specification Review | 150 | 1.5 | 48 | 72 |  |  |  |  | 29 | 29 |  | 15 | 8
26 | 934 |  | SW Integration Test Execution | 150 | 1.5 | 72 | 108 |  |  |  |  | 44 | 44 |  | 22 | 11
27 | 935 |  | SW Qualification Test Specification | 150 | 1.5 | 120 | 180 |  |  |  |  | 72 | 72 |  | 36 | 18
28 | 936 |  | SW Qualification Test Specification Review | 150 | 1.5 | 30 | 45 |  |  |  |  | 18 | 18 |  | 9 | 5
29 | 937 |  | SW Qualification Test Execution | 150 | 1.5 | 72 | 108 |  |  |  |  | 44 | 44 |  | 22 | 11
30 | 938 |  | Sys Integration Test Specification | 150 | 1.5 | 120 | 180 |  |  |  |  | 72 | 72 |  | 36 | 18
31 | 939 |  | Sys Integration Test Specification Review | 150 | 1.5 | 48 | 72 |  |  |  |  | 29 | 29 |  | 15 | 8
32 | 940 |  | Sys Integration Test Execution | 150 | 1.5 | 96 | 144 |  |  |  |  | 58 | 58 |  | 29 | 15
33 | 941 |  | Sys Qualification Test Specification | 150 | 1.5 | 72 | 108 |  |  |  |  | 44 | 44 |  | 22 | 11
34 | 942 |  | Sys Qualification Test Specification Review | 150 | 1.5 | 18 | 27 |  |  |  |  | 11 | 11 |  | 6 | 3
35 | 943 |  | Sys Qualification Test Execution | 150 | 1.5 | 36 | 54 |  |  |  |  | 22 | 22 |  | 11 | 6
Feature | 944 | Knockout |  | 50 | 1 | [9 empty] | 100% | 110% | 120%
Proc | 945 | [13 empty] | 100% | 10% | 10%
Sum | 946 |  |  |  |  | 552 | 552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552 | 70 | 70 | 692
Sys Eng | 947 | Knockout\Sys Eng |  |  |  | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 16 | 16 | 116
SW Dev | 948 | Knockout\SW Dev |  |  |  | 264 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264 | 30 | 30 | 324
Testing | 949 | Knockout\Testing |  |  |  | 204 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204 | 24 | 24 | 252
1 | 950 |  | Customer Req Analysis | 50 | 1 | 4 | 4 | [7 empty] | 4 | 1 | 1
2 | 951 |  | Sys Requirements Creation | 50 | 1 | 8 | 8 | [7 empty] | 8 | 1 | 1
3 | 952 |  | Sys Requirements Verification Criteria | 50 | 1 | 2 | 2 | [7 empty] | 2 | 1 | 1
4 | 953 |  | Sys Requirements Review | 50 | 1 | 4 | 4 | [7 empty] | 4 | 1 | 1
5 | 954 |  | Sys Requirements Update after Review | 50 | 1 | 2 | 2 | [7 empty] | 2 | 1 | 1
6 | 955 |  | Sys Architecture Creation/Update | 50 | 1 | 6 | 6 | [7 empty] | 6 | 1 | 1
7 | 956 |  | Sys Arch Traceability | 50 | 1 | 4 | 4 | [7 empty] | 4 | 1 | 1
8 | 957 |  | Sys Architecture Review | 50 | 1 | 4 | 4 | [7 empty] | 4 | 1 | 1
9 | 958 |  | Sys Architecture Update after Review | 50 | 1 | 2 | 2 | [7 empty] | 2 | 1 | 1
10 | 959 |  | SW Requirements Creation | 50 | 1 | 24 | 24 | [7 empty] | 24 | 3 | 3
11 | 960 |  | SW Requirements Verification Criteria | 50 | 1 | 6 | 6 | [7 empty] | 6 | 1 | 1
12 | 961 |  | SW Requirements Review | 50 | 1 | 12 | 12 | [7 empty] | 12 | 2 | 2
13 | 962 |  | SW Requirements Update after Review | 50 | 1 | 6 | 6 | [7 empty] | 6 | 1 | 1
14 | 963 |  | SW Architecture Specification | 50 | 1 | 24 | 24 | [7 empty] | 24 | 3 | 3
15 | 964 |  | SW Architecture Specification Review | 50 | 1 | 8 | 8 | [7 empty] | 8 | 1 | 1
16 | 965 |  | Design Specification | 50 | 1 | 24 | 24 | [7 empty] | 24 | 3 | 3
17 | 966 |  | Design Specification Review | 50 | 1 | 8 | 8 | [7 empty] | 8 | 1 | 1
18 | 967 |  | Code Implementation | 50 | 1 | 40 | 40 | [7 empty] | 40 | 4 | 4
19 | 968 |  | QAC/Code Metrics Verification | 50 | 1 | 8 | 8 | [7 empty] | 8 | 1 | 1
20 | 969 |  | Code Review | 50 | 1 | 16 | 16 | [7 empty] | 16 | 2 | 2
21 | 970 |  | Unit Test Specification | 50 | 1 | 40 | 40 | [7 empty] | 40 | 4 | 4
22 | 971 |  | Unit Test Specification Review | 50 | 1 | 8 | 8 | [7 empty] | 8 | 1 | 1
23 | 972 |  | Unit Test Execution | 50 | 1 | 8 | 8 | [7 empty] | 8 | 1 | 1
24 | 973 |  | SW Integration Test Specification | 50 | 1 | 40 | 40 | [7 empty] | 40 | 4 | 4
25 | 974 |  | SW Integration Test Specification Review | 50 | 1 | 16 | 16 | [7 empty] | 16 | 2 | 2
26 | 975 |  | SW Integration Test Execution | 50 | 1 | 24 | 24 | [7 empty] | 24 | 3 | 3
27 | 976 |  | SW Qualification Test Specification | 50 | 1 | 40 | 40 | [7 empty] | 40 | 4 | 4
28 | 977 |  | SW Qualification Test Specification Review | 50 | 1 | 10 | 10 | [7 empty] | 10 | 1 | 1
29 | 978 |  | SW Qualification Test Execution | 50 | 1 | 24 | 24 | [7 empty] | 24 | 3 | 3
30 | 979 |  | Sys Integration Test Specification | 50 | 1 | 40 | 40 | [7 empty] | 40 | 4 | 4
31 | 980 |  | Sys Integration Test Specification Review | 50 | 1 | 16 | 16 | [7 empty] | 16 | 2 | 2
32 | 981 |  | Sys Integration Test Execution | 50 | 1 | 32 | 32 | [7 empty] | 32 | 4 | 4
33 | 982 |  | Sys Qualification Test Specification | 50 | 1 | 24 | 24 | [7 empty] | 24 | 3 | 3
34 | 983 |  | Sys Qualification Test Specification Review | 50 | 1 | 6 | 6 | [7 empty] | 6 | 1 | 1
35 | 984 |  | Sys Qualification Test Execution | 50 | 1 | 12 | 12 | [7 empty] | 12 | 2 | 2
Feature | 985 | System context |  | 40 | 1 | [7 empty] | 40% |  | 100% | 110%
Proc | 986 | [11 empty] | 40% |  | 60% | 10%
Sum | 987 |  |  |  |  | 441.6 | 441.6 | 0 | 0 | 0 | 0 | 0 | 191 | 0 | 276 | 61 | 0 | 528
Sys Eng | 988 | System context\Sys Eng |  |  |  | 67.2 | 67.2 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 42 | 14 | 0 | 88
SW Dev | 989 | System context\SW Dev |  |  |  | 211.2 | 211.2 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 132 | 27 | 0 | 249
Testing | 990 | System context\Testing |  |  |  | 163.2 | 163.2 | 0 | 0 | 0 | 0 | 0 | 69 | 0 | 102 | 20 | 0 | 191
1 | 991 |  | Customer Req Analysis | 40 | 1 | 3.2 | 3.2 | [5 empty] | 2 |  | 2 | 1
2 | 992 |  | Sys Requirements Creation | 40 | 1 | 6.4 | 6.4 | [5 empty] | 3 |  | 4 | 1
3 | 993 |  | Sys Requirements Verification Criteria | 40 | 1 | 1.6 | 1.6 | [5 empty] | 1 |  | 1 | 1
4 | 994 |  | Sys Requirements Review | 40 | 1 | 3.2 | 3.2 | [5 empty] | 2 |  | 2 | 1
5 | 995 |  | Sys Requirements Update after Review | 40 | 1 | 1.6 | 1.6 | [5 empty] | 1 |  | 1 | 1
6 | 996 |  | Sys Architecture Creation/Update | 40 | 1 | 4.8 | 4.8 | [5 empty] | 2 |  | 3 | 1
7 | 997 |  | Sys Arch Traceability | 40 | 1 | 3.2 | 3.2 | [5 empty] | 2 |  | 2 | 1
8 | 998 |  | Sys Architecture Review | 40 | 1 | 3.2 | 3.2 | [5 empty] | 2 |  | 2 | 1
9 | 999 |  | Sys Architecture Update after Review | 40 | 1 | 1.6 | 1.6 | [5 empty] | 1 |  | 1 | 1
10 | 1000 |  | SW Requirements Creation | 40 | 1 | 19.2 | 19.2 | [5 empty] | 8 |  | 12 | 2
11 | 1001 |  | SW Requirements Verification Criteria | 40 | 1 | 4.8 | 4.8 | [5 empty] | 2 |  | 3 | 1
12 | 1002 |  | SW Requirements Review | 40 | 1 | 9.6 | 9.6 | [5 empty] | 4 |  | 6 | 1
13 | 1003 |  | SW Requirements Update after Review | 40 | 1 | 4.8 | 4.8 | [5 empty] | 2 |  | 3 | 1
14 | 1004 |  | SW Architecture Specification | 40 | 1 | 19.2 | 19.2 | [5 empty] | 8 |  | 12 | 2
15 | 1005 |  | SW Architecture Specification Review | 40 | 1 | 6.4 | 6.4 | [5 empty] | 3 |  | 4 | 1
16 | 1006 |  | Design Specification | 40 | 1 | 19.2 | 19.2 | [5 empty] | 8 |  | 12 | 2
17 | 1007 |  | Design Specification Review | 40 | 1 | 6.4 | 6.4 | [5 empty] | 3 |  | 4 | 1
18 | 1008 |  | Code Implementation | 40 | 1 | 32 | 32 | [5 empty] | 13 |  | 20 | 4
19 | 1009 |  | QAC/Code Metrics Verification | 40 | 1 | 6.4 | 6.4 | [5 empty] | 3 |  | 4 | 1
20 | 1010 |  | Code Review | 40 | 1 | 12.8 | 12.8 | [5 empty] | 6 |  | 8 | 2
21 | 1011 |  | Unit Test Specification | 40 | 1 | 32 | 32 | [5 empty] | 13 |  | 20 | 4
22 | 1012 |  | Unit Test Specification Review | 40 | 1 | 6.4 | 6.4 | [5 empty] | 3 |  | 4 | 1
23 | 1013 |  | Unit Test Execution | 40 | 1 | 6.4 | 6.4 | [5 empty] | 3 |  | 4 | 1
24 | 1014 |  | SW Integration Test Specification | 40 | 1 | 32 | 32 | [5 empty] | 13 |  | 20 | 4
25 | 1015 |  | SW Integration Test Specification Review | 40 | 1 | 12.8 | 12.8 | [5 empty] | 6 |  | 8 | 2
26 | 1016 |  | SW Integration Test Execution | 40 | 1 | 19.2 | 19.2 | [5 empty] | 8 |  | 12 | 2
27 | 1017 |  | SW Qualification Test Specification | 40 | 1 | 32 | 32 | [5 empty] | 13 |  | 20 | 4
28 | 1018 |  | SW Qualification Test Specification Review | 40 | 1 | 8 | 8 | [5 empty] | 4 |  | 5 | 1
29 | 1019 |  | SW Qualification Test Execution | 40 | 1 | 19.2 | 19.2 | [5 empty] | 8 |  | 12 | 2
30 | 1020 |  | Sys Integration Test Specification | 40 | 1 | 32 | 32 | [5 empty] | 13 |  | 20 | 4
31 | 1021 |  | Sys Integration Test Specification Review | 40 | 1 | 12.8 | 12.8 | [5 empty] | 6 |  | 8 | 2
32 | 1022 |  | Sys Integration Test Execution | 40 | 1 | 25.6 | 25.6 | [5 empty] | 11 |  | 16 | 3
33 | 1023 |  | Sys Qualification Test Specification | 40 | 1 | 19.2 | 19.2 | [5 empty] | 8 |  | 12 | 2
34 | 1024 |  | Sys Qualification Test Specification Review | 40 | 1 | 4.8 | 4.8 | [5 empty] | 2 |  | 3 | 1
35 | 1025 |  | Sys Qualification Test Execution | 40 | 1 | 9.6 | 9.6 | [5 empty] | 4 |  | 6 | 1
Feature | 1026 | Flash lock |  | 30 | 1 | [9 empty] | 90% | 100% | 120%
Proc | 1027 | [13 empty] | 90% | 10% | 20%
Sum | 1028 |  |  |  |  | 331.2 | 331.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317 | 52 | 76 | 445
Sys Eng | 1029 | Flash lock\Sys Eng |  |  |  | 50.4 | 50.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 14 | 16 | 85
SW Dev | 1030 | Flash lock\SW Dev |  |  |  | 158.4 | 158.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 22 | 33 | 203
Testing | 1031 | Flash lock\Testing |  |  |  | 122.4 | 122.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 16 | 27 | 157
1 | 1032 |  | Customer Req Analysis | 30 | 1 | 2.4 | 2.4 | [7 empty] | 3 | 1 | 1
2 | 1033 |  | Sys Requirements Creation | 30 | 1 | 4.8 | 4.8 | [7 empty] | 5 | 1 | 1
3 | 1034 |  | Sys Requirements Verification Criteria | 30 | 1 | 1.2 | 1.2 | [7 empty] | 2 | 1 | 1
4 | 1035 |  | Sys Requirements Review | 30 | 1 | 2.4 | 2.4 | [7 empty] | 3 | 1 | 1
5 | 1036 |  | Sys Requirements Update after Review | 30 | 1 | 1.2 | 1.2 | [7 empty] | 2 | 1 | 1
6 | 1037 |  | Sys Architecture Creation/Update | 30 | 1 | 3.6 | 3.6 | [7 empty] | 4 | 1 | 1
7 | 1038 |  | Sys Arch Traceability | 30 | 1 | 2.4 | 2.4 | [7 empty] | 3 | 1 | 1
8 | 1039 |  | Sys Architecture Review | 30 | 1 | 2.4 | 2.4 | [7 empty] | 3 | 1 | 1
9 | 1040 |  | Sys Architecture Update after Review | 30 | 1 | 1.2 | 1.2 | [7 empty] | 2 | 1 | 1
10 | 1041 |  | SW Requirements Creation | 30 | 1 | 14.4 | 14.4 | [7 empty] | 13 | 2 | 3
11 | 1042 |  | SW Requirements Verification Criteria | 30 | 1 | 3.6 | 3.6 | [7 empty] | 4 | 1 | 1
12 | 1043 |  | SW Requirements Review | 30 | 1 | 7.2 | 7.2 | [7 empty] | 7 | 1 | 2
13 | 1044 |  | SW Requirements Update after Review | 30 | 1 | 3.6 | 3.6 | [7 empty] | 4 | 1 | 1
14 | 1045 |  | SW Architecture Specification | 30 | 1 | 14.4 | 14.4 | [7 empty] | 13 | 2 | 3
15 | 1046 |  | SW Architecture Specification Review | 30 | 1 | 4.8 | 4.8 | [7 empty] | 5 | 1 | 1
16 | 1047 |  | Design Specification | 30 | 1 | 14.4 | 14.4 | [7 empty] | 13 | 2 | 3
17 | 1048 |  | Design Specification Review | 30 | 1 | 4.8 | 4.8 | [7 empty] | 5 | 1 | 1
18 | 1049 |  | Code Implementation | 30 | 1 | 24 | 24 | [7 empty] | 22 | 3 | 5
19 | 1050 |  | QAC/Code Metrics Verification | 30 | 1 | 4.8 | 4.8 | [7 empty] | 5 | 1 | 1
20 | 1051 |  | Code Review | 30 | 1 | 9.6 | 9.6 | [7 empty] | 9 | 1 | 2
21 | 1052 |  | Unit Test Specification | 30 | 1 | 24 | 24 | [7 empty] | 22 | 3 | 5
22 | 1053 |  | Unit Test Specification Review | 30 | 1 | 4.8 | 4.8 | [7 empty] | 5 | 1 | 1
23 | 1054 |  | Unit Test Execution | 30 | 1 | 4.8 | 4.8 | [7 empty] | 5 | 1 | 1
24 | 1055 |  | SW Integration Test Specification | 30 | 1 | 24 | 24 | [7 empty] | 22 | 3 | 5
25 | 1056 |  | SW Integration Test Specification Review | 30 | 1 | 9.6 | 9.6 | [7 empty] | 9 | 1 | 2
26 | 1057 |  | SW Integration Test Execution | 30 | 1 | 14.4 | 14.4 | [7 empty] | 13 | 2 | 3
27 | 1058 |  | SW Qualification Test Specification | 30 | 1 | 24 | 24 | [7 empty] | 22 | 3 | 5
28 | 1059 |  | SW Qualification Test Specification Review | 30 | 1 | 6 | 6 | [7 empty] | 6 | 1 | 2
29 | 1060 |  | SW Qualification Test Execution | 30 | 1 | 14.4 | 14.4 | [7 empty] | 13 | 2 | 3
30 | 1061 |  | Sys Integration Test Specification | 30 | 1 | 24 | 24 | [7 empty] | 22 | 3 | 5
31 | 1062 |  | Sys Integration Test Specification Review | 30 | 1 | 9.6 | 9.6 | [7 empty] | 9 | 1 | 2
32 | 1063 |  | Sys Integration Test Execution | 30 | 1 | 19.2 | 19.2 | [7 empty] | 18 | 2 | 4
33 | 1064 |  | Sys Qualification Test Specification | 30 | 1 | 14.4 | 14.4 | [7 empty] | 13 | 2 | 3
34 | 1065 |  | Sys Qualification Test Specification Review | 30 | 1 | 3.6 | 3.6 | [7 empty] | 4 | 1 | 1
35 | 1066 |  | Sys Qualification Test Execution | 30 | 1 | 7.2 | 7.2 | [7 empty] | 7 | 1 | 2
Feature | 1067 | Safety mechanisms |  | 1 | 1.5 | [14 empty] | 930409 | R1.1 |  | 930409 | R1.1
Proc | 1068
Sum | 1069 |  |  |  |  | 11.04 | 16.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sys Eng | 1070 | Safety mechanisms\Sys Eng |  |  |  | 1.68 | 2.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SW Dev | 1071 | Safety mechanisms\SW Dev |  |  |  | 5.28 | 7.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 1072 | Safety mechanisms\Testing |  |  |  | 4.08 | 6.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 1073 |  | Customer Req Analysis | 1 | 1.5 | 0.08 | 0.12
2 | 1074 |  | Sys Requirements Creation | 1 | 1.5 | 0.16 | 0.24
3 | 1075 |  | Sys Requirements Verification Criteria | 1 | 1.5 | 0.04 | 0.06
4 | 1076 |  | Sys Requirements Review | 1 | 1.5 | 0.08 | 0.12
5 | 1077 |  | Sys Requirements Update after Review | 1 | 1.5 | 0.04 | 0.06
6 | 1078 |  | Sys Architecture Creation/Update | 1 | 1.5 | 0.12 | 0.18
7 | 1079 |  | Sys Arch Traceability | 1 | 1.5 | 0.08 | 0.12
8 | 1080 |  | Sys Architecture Review | 1 | 1.5 | 0.08 | 0.12
9 | 1081 |  | Sys Architecture Update after Review | 1 | 1.5 | 0.04 | 0.06
10 | 1082 |  | SW Requirements Creation | 1 | 1.5 | 0.48 | 0.72
11 | 1083 |  | SW Requirements Verification Criteria | 1 | 1.5 | 0.12 | 0.18
12 | 1084 |  | SW Requirements Review | 1 | 1.5 | 0.24 | 0.36
13 | 1085 |  | SW Requirements Update after Review | 1 | 1.5 | 0.12 | 0.18
14 | 1086 |  | SW Architecture Specification | 1 | 1.5 | 0.48 | 0.72
15 | 1087 |  | SW Architecture Specification Review | 1 | 1.5 | 0.16 | 0.24
16 | 1088 |  | Design Specification | 1 | 1.5 | 0.48 | 0.72
17 | 1089 |  | Design Specification Review | 1 | 1.5 | 0.16 | 0.24
18 | 1090 |  | Code Implementation | 1 | 1.5 | 0.8 | 1.2
19 | 1091 |  | QAC/Code Metrics Verification | 1 | 1.5 | 0.16 | 0.24
20 | 1092 |  | Code Review | 1 | 1.5 | 0.32 | 0.48
21 | 1093 |  | Unit Test Specification | 1 | 1.5 | 0.8 | 1.2
22 | 1094 |  | Unit Test Specification Review | 1 | 1.5 | 0.16 | 0.24
23 | 1095 |  | Unit Test Execution | 1 | 1.5 | 0.16 | 0.24
24 | 1096 |  | SW Integration Test Specification | 1 | 1.5 | 0.8 | 1.2
25 | 1097 |  | SW Integration Test Specification Review | 1 | 1.5 | 0.32 | 0.48
26 | 1098 |  | SW Integration Test Execution | 1 | 1.5 | 0.48 | 0.72
27 | 1099 |  | SW Qualification Test Specification | 1 | 1.5 | 0.8 | 1.2
28 | 1100 |  | SW Qualification Test Specification Review | 1 | 1.5 | 0.2 | 0.3
29 | 1101 |  | SW Qualification Test Execution | 1 | 1.5 | 0.48 | 0.72
30 | 1102 |  | Sys Integration Test Specification | 1 | 1.5 | 0.8 | 1.2
31 | 1103 |  | Sys Integration Test Specification Review | 1 | 1.5 | 0.32 | 0.48
32 | 1104 |  | Sys Integration Test Execution | 1 | 1.5 | 0.64 | 0.96
33 | 1105 |  | Sys Qualification Test Specification | 1 | 1.5 | 0.48 | 0.72
34 | 1106 |  | Sys Qualification Test Specification Review | 1 | 1.5 | 0.12 | 0.18
35 | 1107 |  | Sys Qualification Test Execution | 1 | 1.5 | 0.24 | 0.36
Feature | 1067 | SW Bug-Fix |  | 0 | 0 |  |  | 10% | 20% | 25% | 35% | 50% | 60% | 70% | 80% | 90% | 100% |  |  | 931787;931300;958166;958825;1001716;1002843;998640;999736;1002919;1002810;931383;995611;995617;1002902;961690;1007551;1017575;1018803;1018821;1026966;995596;1026956;931299;1026903 | R1.1 |  | 931787;931300;958166;958825;1001716;1002843;998640;999736;1002919;1002810;931383;995611;995617;1002902;961690;1007551;1017575;1018803;1018821;1026950;1026966;995596;1026956 | R1.1 |  | 931326;931349;931822;1001793;1024191;1024203;1024204;1017999;1011142;1007511;1017436;1018037;1018039;1025469;1024313;1024313;1027052;1027188;1018026;1025369 | R1.2
Proc | 1068 | [6 empty] | 10% | 10% | 5% | 10% | 15% | 10% | 10% | 10% | 10% | 10%
Sum | 1069 |  |  |  |  | 27827 | 7272.2 | 738 | 738 | 374 | 738 | 1100 | 738 | 738 | 738 | 738 | 738 | 7378
Sys Eng | 1070 | SW Bug-Fix\Sys Eng |  |  |  | 2254 | 676.2 | 69 | 69 | 35 | 69 | 103 | 69 | 69 | 69 | 69 | 69 | 690
SW Dev | 1071 | SW Bug-Fix\SW Dev |  |  |  | 25573 | 6596 | 669 | 669 | 339 | 669 | 997 | 669 | 669 | 669 | 669 | 669 | 6688
Testing | 1072 | SW Bug-Fix\Testing |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 1073 |  | Customer Req Analysis | 0 | 0.3 | 434 | 130.2 | 14 | 14 | 7 | 14 | 20 | 14 | 14 | 14 | 14 | 14
2 | 1074 |  | Sys Requirements Creation | 0 | 0 | 0 | 0
3 | 1075 |  | Sys Requirements Verification Criteria | 0 | 0 | 0 | 0
4 | 1076 |  | Sys Requirements Review | 0 | 0 | 0 | 0
5 | 1077 |  | Sys Requirements Update after Review | 0 | 0 | 0 | 0
6 | 1078 |  | Sys Architecture Creation/Update | 0 | 0 | 0 | 0
7 | 1079 |  | Sys Arch Traceability | 0 | 0 | 0 | 0
8 | 1080 |  | Sys Architecture Review | 0 | 0 | 0 | 0
9 | 1081 |  | Sys Architecture Update after Review | 0 | 0 | 0 | 0
10 | 1082 |  | SW Requirements Creation | 0 | 0 | 0 | 0
11 | 1083 |  | SW Requirements Verification Criteria | 0 | 0 | 0 | 0
12 | 1084 |  | SW Requirements Review | 0 | 0.3 | 1196 | 358.8 | 36 | 36 | 18 | 36 | 54 | 36 | 36 | 36 | 36 | 36
13 | 1085 |  | SW Requirements Update after Review | 0 | 0.3 | 624 | 187.2 | 19 | 19 | 10 | 19 | 29 | 19 | 19 | 19 | 19 | 19
14 | 1086 |  | SW Architecture Specification | 0 | 0.3 | 2324 | 697.2 | 70 | 70 | 35 | 70 | 105 | 70 | 70 | 70 | 70 | 70
15 | 1087 |  | SW Architecture Specification Review | 0 | 0.3 | 803 | 240.9 | 25 | 25 | 13 | 25 | 37 | 25 | 25 | 25 | 25 | 25
16 | 1088 |  | Design Specification | 0 | 0.3 | 2324 | 697.2 | 70 | 70 | 35 | 70 | 105 | 70 | 70 | 70 | 70 | 70
17 | 1089 |  | Design Specification Review | 0 | 0.3 | 803 | 240.9 | 25 | 25 | 13 | 25 | 37 | 25 | 25 | 25 | 25 | 25
18 | 1090 |  | Code Implementation | 0 | 0.3 | 3816 | 1144.8 | 115 | 115 | 58 | 115 | 172 | 115 | 115 | 115 | 115 | 115
19 | 1091 |  | QAC/Code Metrics Verification | 0 | 0.3 | 803 | 240.9 | 25 | 25 | 13 | 25 | 37 | 25 | 25 | 25 | 25 | 25
20 | 1092 |  | Code Review | 0 | 0.3 | 1569 | 470.7 | 48 | 48 | 24 | 48 | 71 | 48 | 48 | 48 | 48 | 48
21 | 1093 |  | Unit Test Specification | 0 | 0.2 | 3816 | 763.2 | 77 | 77 | 39 | 77 | 115 | 77 | 77 | 77 | 77 | 77
22 | 1094 |  | Unit Test Specification Review | 0 | 0.3 | 803 | 240.9 | 25 | 25 | 13 | 25 | 37 | 25 | 25 | 25 | 25 | 25
23 | 1095 |  | Unit Test Execution | 0 | 0.2 | 803 | 160.6 | 17 | 17 | 9 | 17 | 25 | 17 | 17 | 17 | 17 | 17
24 | 1096 |  | SW Integration Test Specification | 0 | 0.2 | 3816 | 763.2 | 77 | 77 | 39 | 77 | 115 | 77 | 77 | 77 | 77 | 77
25 | 1097 |  | SW Integration Test Specification Review | 0 | 0.3 | 1569 | 470.7 | 48 | 48 | 24 | 48 | 71 | 48 | 48 | 48 | 48 | 48
26 | 1098 |  | SW Integration Test Execution | 0 | 0.2 | 2324 | 464.8 | 47 | 47 | 24 | 47 | 70 | 47 | 47 | 47 | 47 | 47
27 | 1099 |  | SW Qualification Test Specification | 0 | 0 | 0 | 0
28 | 1100 |  | SW Qualification Test Specification Review | 0 | 0 | 0 | 0
29 | 1101 |  | SW Qualification Test Execution | 0 | 0 | 0 | 0
30 | 1102 |  | Sys Integration Test Specification | 0 | 0 | 0 | 0
31 | 1103 |  | Sys Integration Test Specification Review | 0 | 0 | 0 | 0
32 | 1104 |  | Sys Integration Test Execution | 0 | 0 | 0 | 0
33 | 1105 |  | Sys Qualification Test Specification | 0 | 0 | 0 | 0
34 | 1106 |  | Sys Qualification Test Specification Review | 0 | 0 | 0 | 0
35 | 1107 |  | Sys Qualification Test Execution | 0 | 0 | 0 | 0
Feature | 1108 | HW Development |  | 100 | 2 |  |  | 40% | 70% | 100% | 100% |  |  |  | 110% | 115%
Proc | 1109 | HW Development\Proc | [5 empty] | 40% | 30% | 30% | 0% |  |  |  | 10% | 5%
Sum HW | 1110 | HW Development\Sum HW |  |  |  | 1600 | 3200 | 1280 | 960 | 960 | 0 | 0 | 0 | 0 | 321 | 160 | 0 | 3681
1 | 1111 |  | HW Requirements Creation | 100 | 2 | 100 | 200 | 10%: 80; 20%: 60; 25%: 60; 80%: 20; 90%: 10
2 | 1112 |  | HW Requirements Review | 100 | 2 | 80 | 160 | 10%: 64; 20%: 48; 25%: 48; 80%: 16; 90%: 8
3 | 1113 |  | HW Architecture | 100 | 2 | 160 | 320 | 10%: 128; 20%: 96; 25%: 96; 80%: 32; 90%: 16
4 | 1114 |  | Proof of Design Documentation | 100 | 2 | 240 | 480 | 10%: 192; 20%: 144; 25%: 144; 80%: 48; 90%: 24
5 | 1115 |  | Schematics Definition | 100 | 2 | 240 | 480 | 10%: 192; 20%: 144; 25%: 144; 80%: 48; 90%: 24
6 | 1116 |  | Layout Definition | 100 | 2 | 200 | 400 | 10%: 160; 20%: 120; 25%: 120; 80%: 40; 90%: 20
7 | 1117 |  | BOM Creation | 100 | 2 | 100 | 200 | 10%: 80; 20%: 60; 25%: 60; 80%: 20; 90%: 10
8 | 1118 |  | HW Design Review | 100 | 2 | 100 | 200 | 10%: 80; 20%: 60; 25%: 60; 80%: 20; 90%: 10
9 | 1119 |  | HW Tests | 100 | 2 | 300 | 600 | 10%: 240; 20%: 180; 25%: 180; 80%: 61; 90%: 30
10 | 1120 |  | Custome HW Review | 100 | 2 | 80 | 160 | 10%: 64; 20%: 48; 25%: 48; 80%: 16; 90%: 8
Feature | 1121 | Mechanical |  | 40 | 1 |  |  | 10%: 40%; 20%: 70%; 25%: 100%; 35%: 100%; 80%: 110%
Proc | 1122 | Mechanical\Proc | [5 empty] | 10%: 40%; 20%: 30%; 25%: 30%; 35%: 0%; 80%: 10%
Sum Mech | 1123 | Mechanical\Sum Mech |  |  |  | 732 | 732 | 294 | 222 | 222 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 813
1 | 1124 |  | HW Requirements Creation | 40 | 1 | 40 | 40 | 10%: 16; 20%: 12; 25%: 12; 80%: 4
2 | 1125 |  | HW Requirements Review | 40 | 1 | 24 | 24 | 10%: 10; 20%: 8; 25%: 8; 80%: 3
3 | 1126 |  | HW Architecture | 40 | 1 | 100 | 100 | 10%: 40; 20%: 30; 25%: 30; 80%: 10
4 | 1127 |  | Proof of Design Documentation | 40 | 1 | 120 | 120 | 10%: 48; 20%: 36; 25%: 36; 80%: 12
5 | 1128 |  | Schematics Definition | 40 | 1 | 120 | 120 | 10%: 48; 20%: 36; 25%: 36; 80%: 12
6 | 1129 |  | Layout Definition | 40 | 1 | 40 | 40 | 10%: 16; 20%: 12; 25%: 12; 80%: 4
7 | 1130 |  | BOM Creation | 40 | 1 | 24 | 24 | 10%: 10; 20%: 8; 25%: 8; 80%: 3
8 | 1131 |  | HW Design Review | 40 | 1 | 24 | 24 | 10%: 10; 20%: 8; 25%: 8; 80%: 3
9 | 1132 |  | HW Tests | 40 | 1 | 240 | 240 | 10%: 96; 20%: 72; 25%: 72; 80%: 24
Feature | 1133 | Product Validation |  |  | 0.75 |  |  | 10%: 80%; 25%: 100%; 35%: 100%; 80%: 110%
Proc | 1134 | Product Validation\Proc | [5 empty] | 10%: 80%; 25%: 20%; 35%: 0%; 80%: 10%
Sum Valid | 1135 | Product Validation\Sum Valid |  |  |  | 264 | 198 | 165 | 0 | 48 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 240
1 | 1136 |  | EMC Test Plan Definition | 0 | 0.75 | 24 | 18 | 10%: 15; 25%: 4; 80%: 2
2 | 1137 |  | EMC Test Plan Review | 0 | 0.75 | 16 | 12 | 10%: 10; 25%: 3; 80%: 2
3 | 1138 |  | EMC Test Execution Support | 0 | 0.75 | 24 | 18 | 10%: 15; 25%: 4; 80%: 2
4 | 1139 |  | EMC Test Report Creation | 0 | 0.75 | 16 | 12 | 10%: 10; 25%: 3; 80%: 2
5 | 1140 |  | EMC Test Report Review | 0 | 0.75 | 8 | 6 | 10%: 5; 25%: 2; 80%: 1
6 | 1141 |  | Environmental Test Plan Definition | 0 | 0.75 | 24 | 18 | 10%: 15; 25%: 4; 80%: 2
7 | 1142 |  | Environmental Test Plan Review | 0 | 0.75 | 16 | 12 | 10%: 10; 25%: 3; 80%: 2
8 | 1143 |  | Environmental Test Execution Support | 0 | 0.75 | 24 | 18 | 10%: 15; 25%: 4; 80%: 2
9 | 1144 |  | Environmental Test Report Creation | 0 | 0.75 | 16 | 12 | 10%: 10; 25%: 3; 80%: 2
10 | 1145 |  | Environmental Test Report Review | 0 | 0.75 | 8 | 6 | 10%: 5; 25%: 2; 80%: 1
11 | 1146 |  | Electrical Test Plan Definition | 0 | 0.75 | 24 | 18 | 10%: 15; 25%: 4; 80%: 2
12 | 1147 |  | Electrical Test Plan Review | 0 | 0.75 | 16 | 12 | 10%: 10; 25%: 3; 80%: 2
13 | 1148 |  | Electrical Test Execution Support | 0 | 0.75 | 24 | 18 | 10%: 15; 25%: 4; 80%: 2
14 | 1149 |  | Electrical Test Report Creation | 0 | 0.75 | 16 | 12 | 10%: 10; 25%: 3; 80%: 2
15 | 1150 |  | Electrical Test Report Review | 0 | 0.75 | 8 | 6 | 10%: 5; 25%: 2; 80%: 1

## Release Effort
| SELECT >>> | R1 | 8 | Sys Eng | SW Dev | Sum HW | Sum Mech | Testing |  |  |  | 20% | 5%
Feature |  |  | Feasible within Project Constraints | Project Effort [h] | [12 empty] | Countermeasure | Due Date
Feature Name | Feature Content | Description |  | System Engineering | SW Development | HW Development | Mech Development | Testing | Fusa Development | Cybersec Development | Quality Assurance | Problem Resolution Management | Change Request Management | Configuration Management | Purchasing | Project Management
Accelerometer driver implementation |  | 6 axis to 3 axis |  | 16 | 30 |  |  | 24 |  |  | 160 | 14 | 4 | 380 | 80 | 425
eCS Algo |  | > Acceleration evaluation > Crash signal evaluation |  | 74 | 217 |  |  | 166 |  |  |  | 92 | 23
Solenoid control |  | > Lock/Unlock implementation > Lock/Unlock counters |  | 55 | 148 |  |  | 114 |  |  |  | 64 | 16
Solenoid Diagnostic |  | > Failure detection mechanism for solenoid |  | 65 | 189 |  |  | 146 |  |  |  | 80 | 20
Wake-up by wire | Buckle+SBR | > Wake-up/Sleep strategy > Compute seat occupancy information |  | 81 | 244 |  |  | 186 |  |  |  | 103 | 26
Bootloader | [11 empty] | 0 | 0
COM Matrix integration |  | > OEM arxml / com matrix integration > eCS status information based on the com matrix > SBR & Buckle Status |  | 140 | 420 |  |  | 324 |  |  |  | 177 | 45
CAN Stack |  | Implementation according to Autosar 4.3 CAN FD specification. |  | 58 | 162 |  |  | 126 |  |  |  | 70 | 18
Network Management |  |  |  | 100 | 297 |  |  | 231 |  |  |  | 126 | 32
AUTOSAR & OS |  | Implementation according to Autosar 4.3 specification. |  | 210 | 660 |  |  | 510 |  |  |  | 276 | 69
Self-Tests |  |  |  | 192 | 594 |  |  | 460 |  |  |  | 250 | 63
ECU Fault Detection |  | Fault handling |  | 126 | 396 |  |  | 306 |  |  |  | 166 | 42
ECU-External Specific Diag |  | (UDS) > eCS specific diag services > Identifikation > Messwerte | [9 empty] | 0 | 0
ECU-Internal Specific Diag |  | (UDS) > ALV internal diagnostic services vs mem by address? | [9 empty] | 0 | 0
Error mapping strategy | [11 empty] | 0 | 0
Temperature Sensor | Accuracy Calibration Error detection |  |  | 16 | 33 |  |  | 27 |  |  |  | 16 | 4
Temperature adaptation |  |  |  | 18 | 46 |  |  | 33 |  |  |  | 20 | 5
Ageing compensation |  |  |  | 65 | 189 |  |  | 146 |  |  |  | 80 | 20
Nachlauf | Low Power Mode | Full functionality according to Audi requirements. |  | 14 | 27 |  |  | 20 |  |  |  | 13 | 4
Coding parameters | [11 empty] | 0 | 0
Calibrateable ECU | [11 empty] | 0 | 0
Variant handling |  | Handling of NVM data for different OEMs (Audi, VW) | [9 empty] | 0 | 0
UNECE | [11 empty] | 0 | 0
Knockout |  | Knockout feature implementation based on Autoliv proposal | [9 empty] | 0 | 0
System context | [11 empty] | 0 | 0
Flash lock |  | Flash locking for serial life | [9 empty] | 0 | 0
Safety mechanisms | [11 empty] | 0 | 0
HW Development | [5 empty] | 960 | [5 empty] | 192 | 48
Mechanical | [6 empty] | 222 |  |  |  |  | 45 | 12
Product Validation | [11 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0 |  |  |  | Feature must be implemented by Platform, not feasible to be done by the application project. | 2022-04-23
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
|  | Total effort/discipline : |  | 1230 | 3652 | 960 | 222 | 2819 | 0 | 0 | 160 | 1784 | 451 | 380 | 80 | 425
Note on S2: Mandatory if the feature feasibility is "NO".
Note on N3: Support could also be overall, not necessarily split per feature. Recommandation is to use a percentage of each feature system development and testing effort (for example 15%).
Note on O3: Support could also be overall, not necessarily split per feature. Recommandation is to use a percentage of each feature system development and testing effort (for example 5%).
Note on P3: Support could also be split per feature, whatever fits the estimation method/schedule better, not necessarily split per feature.
Note on F33: All estimates must be based on either: - an estimation method - similar project estimate records

## Resource & Cost Feasibility
R1
Project Length [months] | Resources |  |  |  | Resource Feasible | Countermeasure | Due Date | Cost |  |  |  | Cost Feasible | Countermeasure | Due Date
|  | Effort [h] | Required | Available |  |  |  | Hourly Cost [€/h] | Required | Total Required | Total Available
4 | System Engineering | 1230 | 2.1062 | 1 | NO |  |  | 37 | 45510 | 1141212 | 1200000 | YES
| SW Development | 3652 | 6.2534 | 4.5 | NO |  |  | 37 | 135124
| HW Development | 960 | 1.6438 | 0.5 | NO |  |  | 96 | 92160
| Mech Development | 222 | 0.38014 | 0.5 | YES | More resources to be requested in the Project Kick-Off/TG0. | 2022-01-23 | 80 | 17760
| Testing | 2819 | 4.8271 | 3 | NO |  |  | 37 | 104303
| Fusa Development | 0 | 0 | 0.33 | YES |  |  | 37 | 0
| Cybersec Development | 0 | 0 | 0.33 | YES |  |  | 37 | 0
| Quality Assurance | 160 | 0.27397 | 1.5 | YES |  |  | 37 | 5920
| Problem Resolution Management | 1784 | 3.0548 | 1 | NO | The delta can be covered by the SW developers. | in place | 37 | 66008
| Change Request Management | 451 | 0.77226 | 0.5 | NO |  |  | 37 | 16687
| Configuration Management | 380 | 0.65068 | 0.5 | NO |  |  | 37 | 14060
| Purchasing | 80 | 0.13699 | 0.15 | YES |  |  | 96 | 7680
| Project Management | 425 | 0.72774 | 1 | YES |  |  | 120 | 51000
| SW Licenses |  | 1 | 1 | YES |  |  |  | 345000
| Product Sample Testing |  | 2 | 2 | YES |  |  |  | 160000
| Project Equipment |  | 1 | 1 | YES |  |  |  | 80000
| Other |  | 1 | 1 | YES |  |  |  | 0
Note on J2: Mandatory if the resource feasibility is "NO".
Note on K2: Mandatory if the resource feasibility is "NO".
Note on Q2: Mandatory if the cost feasibility is "NO".
Note on R2: Mandatory if the cost feasibility is "NO".
Note on G4: Assumption: 146 working hours per month